
[image: image1.jpg]SMMITH R HED

NATIONAL BANK OF CAMBODIA





PROJECT CONCEPT PAPER
FOR
KNOWLEDGE SHARING PROGRAM 
- SYSTEM CONSULTING -

[image: image2.jpg]3

Korea Eximbank

THE EXPORT-IMPORT BANK OF KOREA




[image: image3.jpg]MINISTRY OF STRATEGY
AND FINANCE



[image: image4.jpg]“nowledge
Sharing
Program

N





Table of Contents
1I.
Introduction


1II.
Key Issues


2III.
Project Overview


2A.
Impact


2B.
Outcome


2C.
Outputs


3D.
Activities & Methodologies


4IV.
Project Implementation Arrangements


4A.
Stakeholders


4B.
Work Division


6C.
Expected Schedule


6D.
Financing Plan


7<Attachment 1> Basic Project Information


8<Attachment 2> Project Design and Monitoring Framework


10<Attachment 3> Outline ToR for KSP Consultant




<Project concept paper for the KSP SYSTEM Consulting project>

Support for Development of Payment and Settlement Systems in Cambodia
Date: May 27, 2015
I. Introduction

1. Acknowledging the importance of sharing knowledge and experience on knowledge-based socio-economic infrastructure or system for sustainable development of partner countries, the Ministry of Strategy and Finance (“MoSF”) of the Republic of Korea (“ROK”) launched the System Consulting as a part of the Knowledge Sharing Program (“KSP”) in 2013. The System Consulting aims to provide practical support for the implementation of policy alternative by sharing highly competitive systems of the ROK to partner countries considering their current circumstances. 
2. Based on a request proposal submitted by the Royal Government of Cambodia (“RGC”), the MoSF and the RGC agreed to implement KSP System Consulting Project on the payment and settlement systems development. Under the supervision of the MoSF, the Export-Import bank of Korea (“Korea EXIMbank”)—a government agency for KSP, prepared 2015 KSP System Consulting Project to help the National Bank of Cambodia (“NBC”) develop payment and settlement systems. The impact, outcome, outputs, activities, implementation arrangements, and financing plan are based on consultations with the NBC.
II. Key Issues
3. Except in cases of major financial crisis, Cambodian economy has shown GDP growth of 6-8% in average since its adoption of open market economy in 1989. Though traditionally an agricultural economy, other sectors in Cambodia such as garment industry and tourism have grown rapidly and the growth rate of non-agricultural sectors exceeded that of the agricultural sector. With economic goal of achieving sustainable economic growth greater than 7%, developing private sector and reliable financial system to support it is one of the major strategies of RGC to develop its economy according to the National Strategic Development Plan 2014-2018. RGC aims to bring the public financial system up to the international standards to enhance the economic growth and increase efficiency of private operations. 
4. However, Cambodia is still heavily dependent on paper-based payment instruments and lacks alternative forms of payment and settlement systems. RGC recognized the need for an efficient, reliable payment and settlement systems on which it can establish a sound monetary system. “Developing a safe and efficient payment and settlement system” is one of the key priorities according to the Financial Sector Development Strategy 2006-2015. In 2005, RGC enacted the Negotiable Instruments and Payments Systems Law providing comprehensive legal framework for the development of negotiable instruments such as checks, bills of exchange, and interbank securities transactions. In 2012, NBC launched the National Clearing System to build efficiency and to expand services such as inter-bank transfers. 
5. Korea, which successfully developed diversified non-paper-based payments for both the large-value payments and smaller payments in past decades, could provide useful insight and guidance in developing payment and settlement systems in RGC. Korea’s non-paper based payment instruments have grown steadily since the 1980s with development of interbank funds transfer systems such as Interbank Funds Transfer System and the Interbank CD/ATM System. The Bank of Korea (“BOK”) has created and operated the BOK Financial Wire Network (“BOK-Wire”) since 1994 for large-value payment and launched BOK-Wire+ in 2005 to meet the needs of increased transaction. Over 120 institutions including banks, securities companies, and insurance companies are part of the network. Most of the retail payment systems such as mobile and internet banking, mobile payment services, credit card payment system, and direct debit service are run by Korea Financial Telecommunications and Clearings Institute (“KFTC”). The transaction value of KFTC exceeded USD 1.6 billion in 2013 with per-transaction cost less than USD 0.0085. Such achievements in payment and settlement systems were made possible by combination of legal and institutional support as well as technical and infrastructural development.
6. To share Korea’s best practices in more depth, the Korea EXIMbank will conduct the KSP Consulting Project ‘Support for Development of Payment and Settlement Systems in Cambodia’ (“the Project”) in 2015. The Project will help the partner country to identify and develop necessary payment and settlement systems, which will eventually support the socio-economic development of Cambodia. The Korea EXIMbank will be in charge of preparation and implementation of the Project in active cooperation with the NBC.
III. Project Overview

A.    Impact
7. The project aims to improve payment and settlement systems of the RGC by adopting knowledge and experiences from the Korean best practices. 

B.    Outcome
8. The intended outcome of the Project is to develop and disseminate best practice of Korea on the successful development and management of payment and settlement systems, and its implications to the partner country. 
C. Outputs 
9. The outputs of the project will be (i) Analysis of current payment and settlement systems in Cambodia, (ii) Comparative study of payment and settlement systems development of Korea with Cambodia, (iii) Concept design and implementation plan, and (iv) Capacity Building Workshop and Final Dissemination Seminar.
D.    Activities & Methodologies
The following activities are expected to be conducted: 

10. (Activity 1) Analysis of current payment and settlement systems in Cambodia. The study will include following contents of the partner country: (i) current market demand for the payment and settlement systems, (ii) relevant infrastructure for operation of payment and settlement systems, (iii) institutional and organizational status and capacity, (iv) Cambodia’s budget or investment plan for developing payment and settlement systems, (v) existing laws and regulations concerning payment and settlement systems, and in what level and extent that these laws has been developed and implemented, and (v) required payment and settlement service models such as shared mobile banking, internet banking service and mobile payment service, card processing facility, certificate authority and direct debit service.
11. (Activity 2) Conducting comparative study on Korean experiences and its implication to Cambodia. For the better cooperation, comparative study between Korea and Cambodia will be conducted in order to find the area where Korean experience could be implemented to the partner country. The study will include, but are not limited to, following dimensions of the Korean case: (i) development history of payment and settlement systems, (ii) relevant laws, regulations and government policies, (iii) organizational and systematic arrangements, (iv) relevant technical and infrastructural support, (v) current system and services, and (vi) lessons learned from the case of Korea. Experiences of relevant organizations such as BOK, KFTC, and the Financial Services Commission will be introduced in the study. Combining the analysis of the partner country and the case study of Korea, the comparative study will provide policy implication and recommendations developing payment and settlement systems in Cambodia.
12. (Activity 3) Conceptual design and action plan for developing payment and settlement systems in Cambodia. The conceptual design will provide technical solution regarding (i) functional analysis of the system, (ii) architectural design of the system, (iii) identification of system requirements, (iv) institutional and organizational requirements, (v) policy on the information security, and (v) the specifications on the necessary hardware, software, network, and other physical equipments. The action plan will comprise financing plan, implementation and operation plan, and feasibility analysis to provide NBC a business plan where costs, schedule, and implementation methods are specified.
13. (Activity 4) Holding a Capacity Building Workshop. In reference to the results delivered from studies conducted, the Korea EXIMbank will come up with the agenda for the Capacity Building Workshop with a focus on Korean knowledge and experience in (i) development of payment and settlement systems, (ii) relevant legal systems and regulations, (iii) implementation of the payment and settlement systems, (iv) institutional and organizational coordination and arrangement, (v) benefits derived from the development and implementation of payment and settlement systems, and (vi) challenges and lesson learned during the process of the development. The Korea EXIMbank will progressively cooperate with Korean experts of the concerned field and reflect their opinions into the agenda. 
The Korea EXIMbank will host the Capacity Building Workshop in Seoul, Korea, tentatively in November, 2015. The workshop will last for more or less 5 days [TBD]. 
14. (Activity 5) Final Dissemination Seminar. Derived from the outcomes of the Project, the Korea EXIMbank will draw up the agenda for the Dissemination Seminar in Cambodia, and disseminate the project outputs and Korea’s best practice on developing payment and settlement systems for national and local stakeholders, experts of concerned sectors, and participating parties of the Project. 
IV. Project Implementation Arrangements

A.    Stakeholders

15. The Korea EXIMbank will be in charge of the management of the KSP System Consulting Project. The Korea EXIMbank will employ consultants: a team of a firm consultant. The selection and engagement of consultants will be carried out in line with the agreement on the Terms of Reference (“ToR”) for KSP consultants between the Korea EXIMbank and the RGC. The following staffs of each party will lead the organization and management of the activities:

· Korea EXIMbank: 
· Ms. Dong-Hee Yoo, (Project Leader, KSP Team): donghee.yoo@koreaeximbank.go.kr 
· Ms. Chan Mi Kim, (Project Officer, KSP Team): bye1003@koreaexim.go.kr 


· NBC: 
· Mr. Kormoly Kimpty, (Deputy Director General): Kimty.komoly@nbc.org.kh
B.    Work Division

16. The Korea EXIMbank will be a sole fund provider for the Project, but the NBC will also have duties to support EXIMbank’s activities by providing data, information, or other kinds of resources relevant to the Project when requested by EXIMbank and its consultants. More importantly, both parties agree that the results of the Project are to be utilized to enhance the policies, regulations, or the system in Cambodia to function better, and the Korean system, the payment and settlement systems in this case, will be considered as a to-be model when a follow-up plan is designed after the Project.
The organization of activities and specific responsibilities are as follows:

	Activities
(Milestones)
	NBC
	Korea EXIMbank (KSP Consultants) 
	Funding Sources

	Activity 1:

Analysis of current payment and settlement systems in Cambodia
	Support the implementation of the activity by providing relevant information and reviewing the work produced by KSP

	Implement the activity

	Funded by Korea EXIMbank

	Activity 2:
Conducting comparative study on Korean experiences and its implication to Cambodia
	Support the implementation of the activity by providing relevant information and reviewing the work produced by KSP
 
	Implement the activity

	Funded by Korea EXIMbank 


	Activity 3:
Conceptual design and action plan for developing payment and settlement systems in Cambodia
	Support the implementation of the activity by providing relevant information and reviewing the work produced by KSP

	Implement the activity

	Funded by Korea EXIMbank 


	Activity 4:
Capacity Building Workshop in Seoul, Korea
	Support invitation of  experts and officials of the relevant field;

	Finalize the workshop agenda;
Support the logistics for guest speakers and workshop participants;

Invite guest speakers of the relevant field

	Funded by Korea EXIMbank 


	Activity 5:
Final Dissemination Seminar
	Provide assistance in terms of logistics;

Support invitation of experts and officials of the relevant field

	Design and deliver the seminar;
Support the logistics for seminar participants
	Funded by Korea EXIMbank 
In-kind contributions by NBC



C. Expected Schedule 

17. This System Consulting project will be implemented from May 2015 to December 2015. The proposed milestones and implementation schedule are as follows:

	Activities (Milestones)
	Expected Date

	Consultation on the project contents with the NBC
	May 2015

	Confirmation of PCP and ToR, and selection of KSP consultant
	June 2015

	Inception Workshop (Inception Report)
	July 2015

	Activity 1, 2, 3 (Interim Report)
· Analysis of current payment and settlement systems in Cambodia 
· Conducting comparative study on Korean experiences and its implication to Cambodia
· Conceptual design and action plan for developing payment and settlement systems in Cambodia
	October 2015
August 2015
September 2015
October 2015


	Activity 4
Capacity Building Workshop
	November 2015

	Activity 5
Final Dissemination Seminar (Final Report)
	December 2015

	Project Completion Report
	December 2015 


D. Financing Plan 

18. This System Consulting project is estimated to cost USD 150,000 of which all will be financed on a grant basis by KSP. The NBC will provide in-kind contributions as necessary. 
	Expenditure
	Budget (USD)

	KSP Contribution
	150,000

	
	Personnel
	90,000

	
	Travel, Meeting & Workshops
	40,000

	
	Miscellaneous
	20,000

	Total
	150,000


<Attachment 1>: Basic Project Information
<Attachment 2>: Project Design and Monitoring Framework
<Attachment 3>: Outline ToR for KSP consultant
<Attachment 1>
Basic Project Information
	Project Title:
	Support for Development of Payment and Settlement Systems in Cambodia

	Project Type:
	System Consulting 

	Project Duration:
	May 2015 – December 2015 (8 months)

	Project Budget:
	USD 150,000 (KSP: USD 150,000)

	Stakeholders:
	Korea EXIMbank, NBC

	Person in Charge:
	Korea EXIMbank: Ms. Dong-Hee Yoo (Project Team Leader), Chan Mi Kim (Project Officer), KSP Team
NBC: Mr. Kormoly Kimpty (Deputy Director General)

	Project Activities
	Activity 1:
· Analysis of current payment and settlement systems in Cambodia 
Activity 2:
· Conducting comparative study on Korean experiences and its implication to Cambodia
Activity 3:
· Conceptual design and action plan for developing payment and settlement systems in Cambodia
Activity 4:
· Capacity Building Workshops in Seoul, Korea
Activity 5:
· Final Dissemination Seminar in Cambodia



<Attachment 2>
Project Design and Monitoring Framework
	Design Summary
	Target/ Indicators
	Data Sources/ Reporting Mechanisms
	Assumptions/ Risks

	Impact: 
Improved payment and settlement systems of RGC by adopting knowledge and experiences from successful cases
	- At least X% reduction in transaction cost in Y years
(baseline & assessment tool for satisfaction level need be confirmed at implementation stage)
	- Official report or statistical publication regarding payment and settlement systems by the partner country or other international organizations
	A: Partner country’s commitment to payment and settlement systems development and improvement


	Outcomes:
Development and management of payment and settlement systems in RGC by sharing best practice of Korea
	- Implementation of proposed transaction system
-Development of reliable payment and settlement systems for retail, and mobile transactions reaching at least M% of mobile users

	- Statistics and reports of relevant organizations and corporations (ex. Mobile service provider)
- Partner country’s report or statistical publication regarding payment and settlement systems
- KSP Consulting Project Ex-post Evaluation Survey
	A: Partner country’s acceptance of the recommendations provided by the KSP Consulting Project
R: Lack of resources for the initial set up

	Outputs:
1. Analysis of current payment and settlement systems in Cambodia
2. Comparative study on Korean experiences and its implication to Cambodia
3. Conceptual design and action plan for developing payment and settlement systems in Cambodia
4. Capacity Building Workshop in Seoul, Korea
5. Final Dissemination Seminar in Cambodia
	- Capacity Building Workshop and Dissemination Seminar
- Completion of the Final Report by the end of 2015
	- Project Inception Report

- Project Interim Report

- Project Final Report

- PPMR(Project Performance Monitoring Report) & PCR (Project Completion report)

	A: Active and cooperative stakeholders
R: Discordance in project timeframe between NBC and KSP;
Delay of the project

	Activities with Milestones: 
1. Confirmation of PCP& ToR (May 2015)
2. Selection of KSP consultants (Jun. 2015)
3. Inception Workshop and Inception Report (Jul. 2015)

4. Analysis of current payment and settlement systems in Cambodia (Activity 1) (Aug. 2015)
5. Conducting comparative study on Korean experiences, and its implication to the partner countries (Activity 2) (Sep. 2015)
6. Conceptual design and action plan for developing payment and settlement systems in Cambodia (Activity 3) (Oct. 2015)
7. Interim Report (Oct. 2015) 
8. Capacity Building Workshop (Activity 4) (Nov. 2015) 
9. Final Dissemination Seminar and Final Report (Activity 5) (Dec. 2015)
10. Project Completion Report (Dec. 2015)
	Inputs:
KSP: USD 150,000

	
	Note: NBC will provide counterpart support in the form of staff, reports, documents, and other in-kind contributions


<Attachment 3>
Outline Terms of Reference for KSP Consultants

Support for Development of Payment and Settlement Systems in Cambodia
I. Introduction

1.
The consultants’ support is required to conduct activities in accordance with key milestones and produce required outputs/outcomes described in the Project Concept Paper for the project, Support for Development of Payment and Settlement Systems in Cambodia, thereby covering all scope of work and having major events such as workshops. 

2.
To ensure effective assistance to the Korea EXIMbank, the consultants will be required to (i) work and liaise directly with the Korea EXIMbank, (ii) ensure good coordination with the National Bank of Cambodia (“NBC”) team, and (iii) keep the Korea EXIMbank informed of all developments in a timely manner. The assignments are subject to change in agreement with the Korea EXIMbank.
3. 
The purpose of this case study is to show case and benchmark best practice in South Korea in developing payment and settlement systems. Effective payment and settlement systems are the basis of open market system with developed industries. The Royal Government of Cambodia (“RGC”) aims to develop its economy, particularly the private sector, and understands the need to develop reliable payment and settlement systems to support further economic development. In this regard, Korea has successfully transformed from paper-based system to more sophisticated payment and settlement systems ranging from credit cards to mobile banking. The lessons learned from the Korean case, if properly documented, could be of use to RGC.
II. Detailed Tasks

The following activities are expected to be conducted: 

4. (Activity 1) Analysis of current payment and settlement systems in Cambodia. The study will include following contents of the partner country: (i) current market demand for the payment and settlement systems, (ii) relevant infrastructure for operation of payment and settlement systems, (iii) institutional and organizational status and capacity, (iv) Cambodia’s budget or investment plan for developing payment and settlement systems, (v) existing laws and regulations concerning payment and settlement systems, and in what level and extent that these laws has been developed and implemented, and (v) required payment and settlement service models such as shared mobile banking, internet banking service and mobile payment service, card processing facility, certificate authority and direct debit service.
5. (Activity 2) Conducting comparative study on Korean experiences and its implication to Cambodia. For the better cooperation, comparative study between Korea and Cambodia will be conducted in order to find the area where Korean experience could be implemented to the partner country. The study will include, but are not limited to, following dimensions of the Korean case: (i) development history of payment and settlement systems, (ii) relevant laws, regulations and government policies, (iii) organizational and systematic arrangements, (iv) relevant technical and infrastructural support, (v) current system and services, and (vi) lessons learned from the case of Korea. Experiences of relevant organizations such as BOK, KFTC, and the Financial Services Commission will be introduced in the study. Combining the analysis of the partner country and the case study of Korea, the comparative study will provide policy implication and recommendations developing payment and settlement systems in Cambodia.
6. (Activity 3) Conceptual design and action plan for developing payment and settlement systems in Cambodia. The conceptual design will provide technical solution regarding (i) functional analysis of the system, (ii) architectural design of the system, (iii) identification of system requirements, (iv) institutional and organizational requirements, (v) policy on the information security, and (v) the specifications on the necessary hardware, software, network, and other physical equipments. The action plan will comprise financing plan, implementation and operation plan, and feasibility analysis to provide NBC a business plan where costs, schedule, and implementation methods are specified.
7. (Activity 4) Holding a Capacity Building Workshop. In reference to the results delivered from studies conducted, the Korea EXIMbank will come up with the agenda for the Capacity Building Workshop with a focus on Korean knowledge and experience in (i) development of payment and settlement systems, (ii) relevant legal systems and regulations, (iii) implementation of the payment and settlement systems, (iv) institutional and organizational coordination and arrangement, (v) benefits derived from the development and implementation of payment and settlement systems, and (vi) challenges and lesson learned during the process of the development. The Korea EXIMbank will progressively cooperate with Korean experts of the concerned field and reflect their opinions into the agenda. 
The Korea EXIMbank will host the Capacity Building Workshop in Seoul, Korea, tentatively in November, 2015. The workshop will last for more or less 5 days [TBD]. 
(Activity 5) Final Dissemination Seminar. Derived from the outcomes of the Project, the Korea EXIMbank will draw up the agenda for the Dissemination Seminar in Cambodia, and disseminate the project outputs and Korea’s best practice on developing payment and settlement systems for national and local stakeholders, experts of concerned sectors, and participating parties of the Project.
III. Outputs/Deliverables and timeline
9.
The following outputs/deliverables are expected in a designated schedule:
· Inception Report (July 2015)

· Interim Report (October 2015)

· Capacity Building Workshop (November 2015)

· Final Dissemination Seminar (December 2015)
· Final Report (December 2015)
· Executive summary

· Project overview

· Analysis of current payment and settlement systems in Cambodia
· Case study on Korea’s experience in developing payment and settlement systems
· Conceptual design and action plan for developing payment and settlement systems in Cambodia
· A summary of capacity building activities and outcomes

· Project Completion Report (December 2015)

*Please note that the estimated schedule indicated above may be subject to change.

	Activities (Milestones)
	Expected Date

	Mobilization of KSP consultant
	June 2015

	Inception Workshop (Inception Report)
	July 2015

	Activity 1, 2, 3 (Interim Report)
· Analysis of current payment and settlement systems in Cambodia 
· Conducting comparative study on Korean experiences and its implication to Cambodia
· Conceptual design and action plan for developing payment and settlement systems in Cambodia
	October 2015
August 2015
September 2015
October 2015


	Activity 4
Capacity Building Workshop
	November 2015

	Activity 5
Final Dissemination Seminar (Final Report)
	December 2015

	Project Completion Report
	December 2015 


IV. Costs & Estimated Financial Plan
10.
The KSP budget for this assignment is USD 150,000. It will cover expenses for all the activities mentioned above, including travel and accommodation expenses for consultants and administration. 
V. Consultancy Requirements

A.    Characteristics

· The Consultant will be a Korean firm

· Contract Duration : June 2015 – December 2015
· Place(s) of work: Based in Korea, with several missions to Cambodia when necessary
B.     Qualifications

· Extensive experience of consulting services in the issue of planning, designing, and developing payment and settlement systems
· Experience of being involved in payment and settlement related projects in developing countries, Cambodia in particular
· In-depth knowledge in laws and regulations associated to payment and settlement systems development
· Considering the given-time constraint and corresponding work schedule, a consulting firm should present its plan and methodology how to effectively conduct researches
· Demonstrate ability to work harmoniously with government and international officials
· An excellent communication skill in English is essential
� The reason for focus on mobile transaction is based on the fact that mobile broadband use is dominant, whereas internet take-up rates have been very low in Cambodia. According to the UNICEF statistics, there are 132 mobile phones per every 100 population while there are only 4.9 internet users per every 100 population in 2012.





PAGE  

