STANDARD BIDDING DOCUMENTS

UNDER THE EDCF LOAN

Procurement of Plant

Design, Supply, and Installation

July 2025

Abbreviations

BDS .....................Bid Data Sheet

CB ......….............Competitive Bidding

EDCF……….......Economic Development Cooperation Fund

ELI ………..........Eligibility Form

EXP………..........Experience Form

FIN………...........Financial Data Form

GC ……………...General Conditions

IFB ………..........Invitation for Bids

ITB ……..............Instructions to Bidders

Incoterms……….International Commercial Terms

JVA......................Joint Venture or Association/Consortium

CON.....................Historical Contract Non-Performance and Pending Litigation Form

PC ………….......Particular Conditions7

SBD ....................Standard Bidding Document

Glossary

| The Bank | The Export-Import Bank of Korea, which has been entrusted by the Government of the Republic of Korea with the operation and management of the EDCF |
| --- | --- |
| Borrower | The party to the Loan Agreement to which the Bank has agreed to make the Loan |
| Contractor | The legal entity that is party to and performs a Plant contract, the other party to the contract being the “Employer” |
| Consultant EDCF Guidelines | the legal entity employed by the Employer to provide services in accordance with the terms and conditions of the Loan Agreement between the Borrower and the Bank, including: (i) pre-investment studies; (ii) detailed engineering and design; and/or (iii) project implementation, which may involve supervision of project execution The Economic Development Cooperation Fund which is the fund established by the government of the Republic of Korea under the Economic Development Cooperation Fund Act of the Republic of Korea The most recent version of the Guidelines for Procurement under the EDCF Loan, as amended or revised from time to time |
| Employer | One of the two parties to a plant contract, the other party being the “Contractor” |
| Joint Venture | An ad hoc association of firms that pool their resources and skills to undertake a large or complex contract in the role of “Contractor,” with all firms (partners in the JVA) being legally liable, jointly and severally, for the execution of the contract in the event of a partner’s withdrawal |
| Korean Won | Korea Won or the sign “\” means the lawful currency of the Republic of Korea |
| Loan | The Loan provided for in the Loan Agreement |
| Management Contractor | A firm, acting in the role of “Contractor,” that does not normally perform contract construction work directly, but manages the work of other (sub)contractors, while bearing full responsibility and risk for price, quality, and timely performance of the works contract |
| Specialist Subcontractors | A specialist enterprise engaged for highly specialized processes such as chemical grouting or underwater repair work which cannot be provided by the main Contractor |
| Prequalification | An assessment made by the Employer of the appropriate level of experience and capacity of firms expressing interest in undertaking a particular contract before inviting them to bid |
| Postqualification | An assessment of the appropriate level of experience and capacity of firms made by the Employer during the evaluation of bids to ensure that the lowest-evaluated, responsive, eligible bidder is qualified to perform the contract |
| US Dollar | US Dollar or the sign “US$” means the lawful currency of the United States of America. |
| Writing | For the purpose of this document, any authenticated handwritten, typed, or printed communication, including telex, cable, electronic mail, and facsimile transmission, with proof of receipt when, and in the form, requested by the sender |

Foreword

These Standard Bidding Documents (SBDs) have been prepared by the Export-Import Bank of Korea for procurement of Plant through Competitive Bidding (CB) in projects that are financed in whole or in part from the resources of the Economic Development Cooperation Fund (EDCF) of the Republic of Korea. They are consistent with the May 2024 revised edition of the Guidelines for Procurement under the EDCF Loan.

The use of these SBDs is required as the documents have been developed through broad international practice and experience, and comply with the Guidelines for Procurement under the EDCF Loan. The Model Form of International Contract for Process Plant Construction published by the Engineering Advancement Association of Japan (ENAA) has been incorporated to standardize bidding documents on an international basis.

These SBDs are appropriate for single-stage procurement of Plant, e.g. where special processes or closely integrated manufacturing are involved, and contain separate documents applicable for bidding with or without a preceded Prequalification exercise. The Project Executing Agency should note that the initial section on how to prepare the Invitation for Bids (IFB) is neither a part of the Bidding Document nor a Contract Document. The provisions in Section I, Instructions to Bidders (ITB), and Section VII, General Conditions, must be used with their text unchanged to facilitate perusal by Bidders and review by the Export-Import Bank of Korea. Any data and provisions that these sections require for a specific procurement and contract shall be included respectively in Section II, Bid Data Sheet (BDS), and Section VIII, Particular Conditions of Contract.

Those wishing to submit comments or questions on these SBDs or to obtain additional information on procurement under projects financed by the Export-Import Bank of Korea are encouraged to contact:

Economic Development Cooperation Fund Group

The Export-Import Bank of Korea

38, Eunhaeng-ro, Yeongdeungpo-gu

Seoul, 07242, Korea

E-mail: procurement@koreaexim.go.kr

TEL: (82-2) 3779-6114

http://www.koreaexim.go.kr

SBD for Procurement of Plant

Summary

INVITATION FOR BIDS (IFB)

PART 1 – BIDDING PROCEDURES

[Single-Stage One-Envelope Procedure]

Section I.	Instructions to Bidders (ITB): Single-Stage One-Envelope Procedure

This Section provides relevant information to help Bidders prepare their bids. Information is also provided on the submission, opening, and evaluation of bids and on the award of Contracts. Section I contains provisions that are to be used without modification.

Section II.	Bid Data Sheet (BDS): Single-Stage One-Envelope Procedure

This Section consists of provisions that are specific to each procurement and that supplement the information or requirements included in Section I, Instructions to Bidders.

[Single-Stage Two-Envelope Procedure]

Section I.	Instructions to Bidders (ITB): Single-Stage Two-Envelope Procedure

This Section provides relevant information to help Bidders prepare their bids. Information is also provided on the submission, opening, and evaluation of bids and on the award of Contracts.  Section I contains provisions that are to be used without modification.

Section II.	Bid Data Sheet (BDS): Single-Stage Two-Envelope Procedure

This Section consists of provisions that are specific to each procurement and that supplement the information or requirements included in Section I, Instructions to Bidders.

[Following Sections applicable for both One & Two-Envelope Procedures]

Section III.	Evaluation and Qualification Criteria (alternative Section III to be used when Prequalification has taken place before bidding)

This Section contains the criteria to determine the lowest evaluated bid and to ascertain the continued qualification of the Bidder to perform the contract.

Section III.	Evaluation and Qualification Criteria (alternative Section III to be used when Prequalification has not taken place before bidding)

This Section contains the criteria to determine the lowest evaluated bid and the qualifications of the Bidder to perform the contract.

Section IV.	Bidding Forms (alternative Section IV to be used when Prequalification has taken place before bidding)

This Section contains the forms which are to be completed by the Bidder and submitted as part of this Bid.

Section IV.	Bidding Forms (alternative Section IV to be used when Prequalification has not taken place before bidding)

This Section contains the forms which are to be completed by the Bidder and submitted as part of this Bid.

Section V.	Eligible Countries

This Section contains information regarding eligible countries.

PART 2 – EMPLOYER’S REQUIREMENTS

Section VI.	Employer’s Requirements

This Section contains the Specification, the Drawings, and supplementary information that describe the Plant and Installation Services to be procured.

PART 3 – CONDITIONS OF CONTRACT AND CONTRACT FORMS

Section VII.	General Conditions (GC)

This Section contains the general clauses to be applied in all contracts.  The text of the clauses in this Section shall not be modified.

Section VIII.	Particular Conditions (PC)

This Section includes clauses specific to each contract that modify or supplement Section VII, General Conditions of Contract.

Section IX.	Contract Forms

This Section contains forms which, once completed, will form part of the Contract. The forms for Performance Security and Advance Payment Security, when required, shall only be completed by the successful Bidder after contract award.

BIDDING DOCUMENT

Issued on: ____________________

For the

Procurement of

[Insert: identification of the Plant (Design, Supply & Installation)]

CB No.: [Insert: CB number]

Project: [Insert: name of Project]

Employer: [Insert: name of Employer]

<<Note>>

This is a sample cover page for the actual Bidding Document. The parameters filled in should all be identical to the ones used in the Invitation for Bids (IFB) and the Bid Data Sheet (BDS).

Table of Contents

Invitation for Bids (IFB)	1

PART 1 – Bidding Procedures	3

[Single-Stage One-Envelope Procedure]

Section I. Instructions to Bidders  (Single-Stage: One-Envelope)	4

Section II. Bid Data Sheet (Single Stage: One-Envelope)	34

[Single-Stage Two-Envelope Procedure]

Section I. Instructions to Bidders (Single-Stage: Two-Envelope)	43

Section II. Bid Data Sheet (Single Stage: Two-Envelope)	75

[Following Sections applicable for both One & Two-Envelope Procedures]

Section III. Evaluation and Qualification Criteria  (Following Prequalification)	84

Section III: Evaluation and Qualification Criteria (Without Prequalification)	92

Section IV. Bidding Forms (Following Prequalification)	108

Section IV. Bidding Forms  (Without Prequalification)	165

Section V. Eligible Countries	226

PART 2 – Employer’s Requirements	227

Section VI. Employer’s Requirements	228

PART 3 – Conditions of Contract and Contract Forms	253

Section VII. General Conditions	254

Section VIII: Particular Conditions	340

Section IX: Contract Forms	346

Invitation for Bids (IFB)

<<Note>>

In accordance with the Guidelines for Procurement under the EDCF Loan (as defined in Section 2.03), the Invitation for Bids (IFB) shall be advertised in English, in at least one newspaper of general circulation (in an English language newspaper if possible) in the Borrower’s country. Notification shall be given in sufficient time to enable prospective bidders to obtain the Bidding Documents, and prepare and submit their responses. A copy of the IFB shall be promptly submitted to the Export-Import Bank of Korea for advertisement on its Procurement Notices Web site.

The Invitation for Bids provides information that enables potential bidders to decide whether to participate. Apart from a summary description of the Plant, the Invitation for Bids should also indicate any important bid evaluation criteria or qualification requirement (for example, a requirement for a minimum level of experience in similar works for which the Invitation for Bids is issued).

It is critical that the content of the IFB must be consistent with the information contained in Section II, Bid Data Sheet (BDS). In particular, the dates, times, and place for bid submission and opening and the amount required for bid security in the IFB must be carefully checked to ensure consistency with the BDS.

Invitation for Bids (IFB)

Employer: [insert the name of the Employer’s agency]

Project: [insert name of project]

Contract title: [insert the name of the contract]

Country: [insert country where IFB is issued]

Loan Agreement No. and Title: [insert number and Loan Agreement title]

IFB No.: [insert number]

Issued on: [insert issuing date of the IFB]1

- The [insert: Name of Borrower] has received2 (or where appropriate, “has applied for”) a Loan from the Export-Import Bank of Korea from the resources of the Economic Development Cooperation Fund (EDCF) of the Republic of Korea in the amount of [insert: Amount in US Dollars] toward the cost of [insert: Name of Project] and intends to apply a portion of the proceeds of this loan to payments under the contract for [insert: Name of Contract and Contract No.]3.

- The Project Executing Agency now invites sealed bids from eligible bidders for [insert: brief description of Plant requirements, including facilities, location, delivery period, etc.]4.

- Bidding will be conducted through Competitive Bidding (CB) procedures specified in the Guideline for Procurement under EDCF Loan, and is open to all eligible bidders that meet the following minimum qualification criteria. [insert: eligibility of bidders and key qualification criteria relating to specific experience and capabilities]5.

- Interested eligible Bidders may obtain further information from [insert: the name of Project Executing Agency] and inspect the bidding documents at the address below6 from [insert: office hours]7.

- A complete set of bidding documents may be purchased by any interested Bidders on the submission of a written application to the address below and upon payment of a nonrefundable fee of [insert: amount in local currency or in a convertible currency]8. The method of payment will be [insert: method of payment]9. The document will be sent by [insert: delivery procedure]10.

- Bids must be delivered to the address below at or before [insert: time and date]. All bids must be accompanied by a bid security of [insert: fixed amount or minimum percentage of bid price]11. Late bids shall be rejected. Bids will be opened in the presence of the Bidder’s representatives who choose to attend at the address below12 at [insert: time and date].

- The [insert: the name of Employer] will not be responsible for any costs or expenses incurred by Bidders in connection with the preparation or delivery of Bids.

[insert: name of office]

[insert: name of officer]

[insert: postal address] and/or [insert: street address]

[insert: telephone number, indicate country and city code]

[insert: facsimile number and/or e-mail address]

PART 1 – Bidding Procedures

Section I. Instructions to Bidders 
(Single-Stage: One-Envelope)

Table of Clauses

A.	General	6

1.	Scope of Bid	6

2.	Source of Funds	6

3.	Fraud and Corruption	6

4.	Eligible Bidders	9

5.	Eligible Plant and Installation Services	11

B.	Contents of Bidding Document	11

6.	Sections of Bidding Document	11

7.	Clarification of Bidding Document, Site Visit, Pre-Bid Meeting	12

8.	Amendment of Bidding Document	13

C.	Preparation of Bids	13

9.	Cost of Bidding	13

10.	Language of Bid	13

11.	Documents Comprising the Bid	13

12.	Letter of Bid and Schedules	14

13.	Alternative Bids	14

14.	Documents Establishing the Eligibility of Plant and Installation Services	15

15.	Documents Establishing the Eligibility and Qualifications of the Bidder	15

16.	Documents Establishing Conformity of the Plant and Installation Services	15

17.	Technical Proposal, Subcontractors	16

18.	Bid Prices and Discounts	16

19.	Currencies of Bid and Payment	19

20.	Period of Validity of Bids	19

21.	Bid Security/Bid Securing Declaration	20

22.	Format and Signing of Bid	21

D.	Submission and Opening of Bids	22

23.	Submission, Sealing and Marking of Bids	22

24.	Deadline for Submission of Bids	22

25.	Late Bids	23

26.	Withdrawal, Substitution, and Modification of Bids	23

27.	Bid Opening	23

E.	Evaluation and Comparison of Bids	24

28.	Confidentiality	24

29.	Clarification of Bids	25

30.	Deviations, Reservations, and Omissions	25

31.	Preliminary Examination of Bids	25

32.	Determination of Responsiveness	25

33.	Nonmaterial Nonconformities	26

34.	Correction of Arithmetical Errors	27

35.	Conversion to Single Currency	27

36.	Evaluation and Comparison of Bids	27

37.	Eligibility and Qualification of the Bidder	29

38.	Employer’s Right to Accept Any Bid, and to Reject Any or All Bids	30

F.	Award of Contract	30

39.	Award Criteria	30

40.	Standstill Period	31

41.	Notification of Intention to Award	31

42.	Notification of Award	31

43.	Debriefing by the Employer	31

44.	Signing of Contract	32

45.	Performance Security	33

46.	Procurement-related Complaint	33

| ##### General |  |
| --- | --- |
| Scope of Bid | - In connection with the Invitation for Bids indicated in the Bid Data Sheet (BDS), the Employer, as indicated in the BDS, issues this Bidding Document for the Design, Supply and Installation of Plant as specified in Section VI (Employer’s Requirements). The name, identification, and number of lots (contracts) of the Competitive bidding (CB) are provided in the BDS. |
|  | - Throughout this Bidding Document: the term “in writing” means communicated in written form and delivered against receipt; except where the context requires otherwise, words indicating the singular also include the plural and words indicating the plural also include the singular; and “day” means calendar day. |
| Source of Funds | - The Borrower or Recipient (hereinafter called “Borrower”) indicated in the BDS has applied for or received financing (hereinafter called “funds”) from the Export-Import Bank of Korea (hereinafter called the “Bank”) toward the cost of the project named in the BDS. The Borrower intends to apply a portion of the funds to eligible payments under the contract(s) for which this Bidding Document is issued. |
|  | - Payments by the Bank will be made only at the request of the Borrower and upon approval by the Bank in accordance with the terms and conditions of Loan Agreement between the Borrower and Bank (hereinafter called “the Loan Agreement”), and will be subject in all respects to the terms and conditions of that Loan Agreement. No party other than the Borrower shall derive any rights from the Loan Agreement or have any claim to the funds. The Loan Agreement prohibits a withdrawal from the loan account for the purpose of any payment to persons or entities, or for any import of goods, if such payment or import, to the knowledge of the Bank, is prohibited by decision of the Bank. No party other than the Borrower shall derive any rights from the Loan Agreement or have any claim to the funds. |
| Fraud and Corruption | - It is the Bank’s policy to require that Borrowers (including beneficiaries of EDCF Loans), as well as bidders, suppliers, and contractors under contracts financed by EDCF Loans, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Bank: - defines, for the purposes of this provision, the terms set forth below as follows: - “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence the action of a public official in the procurement process or in contract execution; and - “fraudulent practice” means a misrepresentation or omission of facts in order to influence a procurement process or the execution of a contract; - shall reject a proposal for award and declare a firm ineligible to enter into the contract in question if it determines that the bidder recommended for award has engaged in corrupt, fraudulent practices or any other integrity violations in competing for the contract; - shall declare a firm ineligible, for a period determined by the Bank, to participate in any bid for, to be awarded, and to enter into a contract related to the project in question if it at any time determines that the firm has engaged in corrupt, fraudulent practices or any other integrity violations in competing for, or in executing, a contract financed by an EDCF Loan; - notwithstanding the sub-paragraph (b) and (c), shall declare a firm ineligible, even after the end of a period determined by the Bank, to participate in any bid for, to be awarded, and to enter into a contract related to the project in question if it at any time determines that the firm has engaged in corrupt, fraudulent practices or any other integrity violations in competing for, or in executing, the contract of the project; - shall recognize a firm as ineligible to participate in any bid for, to be awarded, and to enter into a contract financed by an EDCF loan if the firm is debarred under the cross debarment decision by Multilateral Development Banks. Such period of ineligibility shall not exceed two (2) years from (and including) the date on which the cross debarment is imposed. With regard to the participation in the bid, the base date of determination on the debarment status is the date of the deadline for submission of bids; and - shall recognize a firm as ineligible to participate in any bid for, to be awarded, and to enter into a contract financed by an EDCF loan if such firm constitutes any of the inappropriate business entities defined in the ‘Act on Contracts to which the State is a Party’, ‘Act on Contracts to Which a Local Government is a Party’, and ‘Act on the Management of Public Institutions’ of the Republic of Korea. Such period of ineligibility shall be equated to the sanction period decided by the Korean government and public institutions. With regard to the participation in the bid, the base date of determination on the sanction status is the date of the deadline for submission of bids. - All Bidders, consultants, contractors, suppliers, and other third parties engaged or involved in Bank-related activities have a duty to cooperate fully in any screening or investigation when requested by the Bank to do so. Such cooperation includes, but is not limited to, the following: - being available to be interviewed and replying fully and truthfully to all questions asked; - providing the Bank with any items requested that are within the party’s control including, but not limited to, documents and other physical objects; - upon written request by the Bank, authorizing other related entities to release directly to the Bank such information that is specifically and materially related, directly or indirectly, to the said entities or issues which are the subject of the investigation; - cooperating with all reasonable requests to search or physically inspect their person and/or work areas, including files, electronic databases, and personal property used on Bank activities, or that utilizes Bank’s Information and Communications Technology (ICT) resources or systems (including mobile phones, personal electronic devices, and electronic storage devices such as external disk drives); - cooperating in any testing requested by the Bank, including but not limited to, fingerprint identification, handwriting analysis, and physical examination and analysis; and - preserving and protecting confidentiality of all information discussed with, and as required by, the Bank. - All Bidders, consultants, contractors and suppliers shall ensure that, in its contract with its sub-consultants, subcontractors, and other third parties engaged or involved in Bank-related activities, such sub-consultants, subcontractors, and other third parties similarly undertake the foregoing duty to cooperate fully in any screening or investigation when requested by the Bank to do so. - Bidders (including all parties/partners and the Representative in case of JVA) shall submit the original signed form (with certificate of corporate seal registration in Korean and certificate of business registration in English) of the “Declaration of participation in Economic Development Cooperation Fund (EDCF) financed projects” as attached in the last page of Section IV (Bidding Forms Following/Without Prequalification) to the Bank (see the address specified in the BDS) by mail or in person at or before the Deadline for bid submission in the BDS or submit a copy of the original signed form to the Employer along with the Bid upon the submission of the Bid. Bidders who fail to submit the original signed form to the Bank and to include the copy of it in the Bid, as set forth above, shall not be substantially responsive subject to ITB Clause 32. In case of discrepancy between English version and its Korean translation of the “Declaration of Participation in Economic Development Cooperation Fund (EDCF) financed projects”, the English version shall prevail. - Furthermore, Bidders shall be aware of the provision stated in GC 9.6 and GC 42.2.1 (c) of the General Conditions. |
| Eligible Bidders | - A Bidder may be a natural person, private entity, or government-owned entity subject to ITB 4.5 - or any combination of such entities in the form of a joint venture or association/consortium (JVA) under an existing agreement or with the intent to enter into such an agreement supported by a letter of intent. In the case of a JVA: - all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms; and - the JVA shall nominate a Representative who shall have the authority to conduct all business for and on behalf of any and all the partners of the JVA during the bidding process and, in the event the JVA is awarded the Contract, during contract execution. |
|  | - A Bidder, and all partners constituting the Bidder, shall have the nationality of an eligible country as defined under the Guidelines; Guidelines for Procurement under the EDCF Loan (hereinafter referred to as the Guidelines), subject to the restrictions specified in Section V (Eligible Countries). A Bidder shall be deemed to have the nationality of a country if the Bidder is a citizen or is constituted, incorporated, or registered, and operates in conformity with the provisions of the laws of that country. This criterion shall also apply to the determination of the nationality of proposed subcontractors or suppliers for any part of the Contract, including related services. |
|  | - A Bidder shall not have a conflict of interest. All Bidders found to have a conflict of interest shall be disqualified. A Bidder may be considered to have a conflict of interest with one or more parties in this bidding process if: - they have controlling partners in common; - they receive or have received any direct or indirect subsidy from any of them; - they have the same legal representative for purposes of this bid; - they have a relationship with each other, directly or through common third parties, that puts them in a position to have access to material information about or improperly influence the bid of another Bidder, or influence the decisions of the Employer regarding this bidding process; - a Bidder participates in more than one bid in this bidding process, either individually or as a partner in a JVA, except for alternative offers permitted under ITB 13. Participation by a Bidder in more than one bid will result in the disqualification of all Bids in which the party is involved. However, this does not limit the inclusion of the same subcontractor in more than one Bid; - a Bidder, JVA partner, associates, parent company or any affiliated entity, participated as a consultant in the preparation of the feasibility study, basic/detailed design or technical specifications, and other documents to be used for the procurement of the Plant and Installation Services that are the subject of the Bid; - a Bidder was affiliated with a firm or entity that has been hired (or is proposed to be hired) by the Employer or Borrower as Project Manager for the Contract; or - a Bidder would be providing goods, works, or non-consulting services resulting from or directly related to consulting services for the preparation or implementation of the project specified in the BDS ITB 2.1 that it provided or were provided by any affiliate that directly or indirectly controls, is controlled by, or is under common control with that firm. |
|  | - A firm that has been determined to be ineligible by the Bank in relation to the Bank Guidelines on preventing and combating Fraud and Corruption (see ITB 3) in Projects Financed by EDCF shall not be eligible to participate in any bid for, to be awarded, and to enter into a contract. |
|  | - Government-owned entities in the Borrower’s country shall be eligible only if they can establish that they (i) are legally and financially autonomous, (ii) operate under commercial law, and (iii) are not dependent agencies of the Employer. - A Bidder shall not be under suspension from bidding by the Employer as the result of the execution of a Bid-Securing Declaration. |
|  | - Bidders shall provide such evidence of their continued eligibility satisfactory to the Employer, as the Employer shall reasonably request. |
|  | - In case a Prequalification process has been conducted prior to the bidding process, this bidding is open only to prequalified Bidders. |
| Eligible Plant and Installation Services | - The Plant and Installation Services to be supplied under the Contract and financed by the Bank may have their origin in any country in accordance with Section V (Eligible Countries). |
|  | - For purposes of ITB 5.1 above, “origin” means the place where the plant, or component parts thereof are mined, grown, produced, or manufactured, and from which the services are provided. Plant components are produced when, through manufacturing, processing, or substantial or major assembling of components, a commercially recognized product results that is substantially in its basic characteristics or in purpose or utility from its components. |
| Contents of Bidding Document |  |
| Sections of Bidding Document | - The Bidding Document consists of Parts 1, 2, and 3, which include all the sections indicated below, and should be read in conjunction with any Addenda issued in accordance with ITB 8. PART 1 Bidding Procedures Section I - Instructions to Bidders (ITB) Section II - Bid Data Sheet (BDS) Section III - Evaluation and Qualification Criteria Section IV - Bidding Forms Section V - Eligible Countries PART 2 Employer’s Requirements Section VI - Employer’s Requirements PART 3 Conditions of Contract and Contract Forms Section VII - General Conditions (GC) Section VIII - Particular Conditions (PC) Section IX - Contract Forms |
|  | - The Invitation for Bids (IFB) issued by the Employer is not part of the Bidding Document. |
|  | - The Employer is not responsible for the completeness of the Bidding Document and its addenda, if they were not obtained directly from the source stated by the Employer in the Invitation for Bids. |
|  | - The Bidder is expected to examine all instructions, forms, terms, and specifications in the Bidding Document. Failure to furnish all information or documentation required by the Bidding Document may result in the rejection of the Bid. |
| Clarification of Bidding Document, Site Visit, Pre-Bid Meeting | - A prospective Bidder requiring any clarification on the Bidding Document shall contact the Employer in writing at the Employer’s address indicated in the BDS, or raise his enquiries during the pre-bid meeting if provided for in accordance with ITB 7.4. The Employer will respond to any request for clarification, provided that such request is received no later than twenty-one (21) days prior to the deadline for submission of bids. The Employer’s response shall be in writing with copies to all Bidders who have acquired the Bidding Document in accordance with ITB 6.3, including a description of the inquiry but without identifying its source. Should the Employer deem it necessary to amend the Bidding Document as a result of a request for clarification, it shall do so following the procedure under ITB 8 and ITB 24.2. |
|  | - The Bidder is advised to visit and examine the site where the Plant is to be installed and its surroundings and obtain for itself on its own responsibility all information that may be necessary for preparing the Bid and entering into a contract for the provision of Plant and Installation Services. The costs of visiting the site shall be at the Bidder’s own expense. |
|  | - The Bidder and any of its personnel or agents will be granted permission by the Employer to enter its premises and lands for the purpose of such visit, but only upon the express condition that the Bidder, its personnel, and agents, will release and indemnify the Employer and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection. |
|  | - The Bidder’s designated representative is invited to attend a pre-bid meeting, if provided for in the BDS. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage. |
|  | - The Bidder is requested, as far as possible, to submit any questions in writing, to reach the Employer not later than one week before the meeting. |
|  | - Minutes of the pre-bid meeting, including the text of the questions raised, without identifying the source, and the responses given, together with any responses prepared after the meeting, will be transmitted promptly to all Bidders who have acquired the Bidding Document in accordance with ITB 6.3. Any modification to the Bidding Document that may become necessary as a result of the pre-bid meeting shall be made by the Employer exclusively through the issue of an addendum pursuant to ITB 8 and not through the minutes of the pre-bid meeting. |
|  | - Nonattendance at the pre-bid meeting will not be a cause for disqualification of a Bidder. |
| Amendment of Bidding Document | - At any time prior to the deadline for submission of Bids, the Employer may amend the Bidding Document by issuing addenda. |
|  | - Any addendum issued shall be part of the Bidding Document and shall be communicated in writing to all who have obtained the Bidding Document from the Employer in accordance with ITB 6.3. The Bidders are required to immediately acknowledge receipt of any such amendment, and it will be assumed that the information contained therein will have been taken into account by the Bidder in its bid. |
|  | - To give prospective Bidders reasonable time in which to take an addendum into account in preparing their Bids, the Employer may, at its discretion, extend the deadline for the submission of Bids, pursuant to ITB 24.2. |
| #### Preparation of Bids |  |
| Cost of Bidding | - The Bidder shall bear all costs associated with the preparation and submission of its Bid, and the Employer shall in no case be responsible or liable for those costs, regardless of the conduct or outcome of the bidding process. |
| Language of Bid | - The Bid, as well as all correspondence and documents relating to the bid exchanged by the Bidder and the Employer, shall be written in the English. Supporting documents and printed literature that are part of the Bid may be in another language provided they are accompanied by an accurate translation of the relevant passages into English, in which case, for purposes of interpretation of the Bid, such translation shall govern. |
| Documents Comprising the Bid | - The Bid submitted by the Bidder shall comprise the following: - Letter of Bid; - completed schedules as required, including Price Schedules, in accordance with ITB 12 and ITB 18; - Bid Security or Bid-Securing Declaration, in accordance with ITB 21; - alternative Bids, if permissible, in accordance with ITB 13; - written confirmation authorizing the signatory of the Bid to commit the Bidder, in accordance with ITB 22.2; - documentary evidence in accordance with ITB 14.1, that the Plant and Installation Services offered by the Bidder in its Bid or in any alternative bid, if permitted, are eligible; - documentary evidence in accordance with ITB 15, establishing the Bidder’s eligibility and qualifications to perform the contract if its bid is accepted; - Technical Proposal in accordance with ITB 17; - documentary evidence in accordance with ITB 16, that the Plant and Installation Services offered by the Bidder conform to the Bidding Document; - list of subcontractors, in accordance with ITB 17.2; and - any other document required in the BDS. - In addition to the requirements under ITB 11.1, Bids submitted by a JVA shall include a copy of the JVA Agreement entered into by all partners. Alternatively, a Letter of Intent to execute a JVA Agreement in the event of a successful Bid shall be signed by all partners and submitted with the Bid, together with a copy of the proposed agreement. |
| Letter of Bid and Schedules | - The Letter of Bid, including the appropriate Price Schedules, shall be prepared using the relevant forms furnished in Section IV (Bidding Forms). The forms must be completed without any alterations to the text, and no substitutes shall be accepted except as provided under ITB 22.2. All blank spaces shall be filled in with the information requested. |
| Alternative Bids | - Unless otherwise indicated in the BDS, alternative bids shall not be considered. |
|  | - When alternative times for completion are explicitly invited, a statement to that effect will be included in the BDS, as will the method of evaluating different times for completion. |
|  | - Except as provided under ITB 13.4 below, Bidders wishing to offer technical alternatives to the Employer’s requirements as described in the Bidding Document must also provide: (i) a price at which they are prepared to offer a Plant meeting the Employer’s requirements; and (ii) all information necessary for a complete evaluation of the alternatives by the Employer, including drawings, design calculations, technical specifications, breakdown of prices, and proposed installation methodology and other relevant details. Only the technical alternatives, if any, of the lowest evaluated Bidder conforming to the basic technical requirements shall be considered by the Employer. |
|  | - When specified in the BDS, Bidders are permitted to submit alternative technical solutions for specified parts of the facilities, and such parts will be identified in the BDS, as will the method for their evaluation, and described in Section VI (Employer’s Requirements). |
| Documents Establishing the Eligibility of Plant and Installation Services | - To establish the eligibility of the Plant and Installation Services in accordance with ITB 5, Bidders shall complete the country of origin declarations in the Price Schedule Forms, included in Section IV (Bidding Forms). |
| Documents Establishing the Eligibility and Qualifications of the Bidder | - In accordance with Section III (Evaluation and Qualification Criteria) to establish that the Bidder continues to meet criteria used at the time of Prequalification, the Bidder shall provide in the corresponding information sheets included in Section IV (Bidding Forms), updated information on any assessed aspect that changed from that time, or if post-qualification applies, the Bidder shall provide the information requested in the corresponding information sheets included in Section IV (Bidding Forms). |
| Documents Establishing Conformity of the Plant and Installation Services | - The documentary evidence of the conformity of the Plant and Installation Services to the Bidding Document may be in the form of literature, drawings, and data and shall furnish: (a) a detailed description of the essential technical and performance characteristics of the Plant and Installation Services, including the functional guarantees of the proposed Plant and Installation Services, in response to the specification; (b) a list giving full particulars, including available sources, of all spare parts and special tools necessary for the proper and continuing functioning of the plant for the period indicated in the BDS, following completion of Plant and Installation Services in accordance with provisions of the contract; and (c) a commentary on the Employer’s Specifications and adequate evidence demonstrating the substantial responsiveness of the Plant and Installation Services to those specifications. Bidders shall note that standards for workmanship, materials, and equipment designated by the Employer in the Bidding Document are intended to be descriptive (establishing standards of quality and performance) only and not restrictive. The Bidder may substitute alternative standards, brand names, and/or catalog numbers in its Bid, provided that it demonstrates to the Employer’s satisfaction that the substitutions are substantially equivalent or superior to the standards designated in the Specifications. |
| Technical Proposal, Subcontractors | - The Bidder shall furnish a Technical Proposal including a statement of work methods, equipment, personnel, schedule, safety plan and any other information as stipulated in Section IV (Bidding Forms), in sufficient detail to demonstrate the adequacy of the Bidders’ proposal to meet the work requirements and the completion time. - For major items of Plant and Installation Services as listed by the Employer in Section III (Evaluation and Qualification Criteria), which the Bidder intends to purchase or subcontract, the Bidder shall give details of the name and nationality of the proposed Subcontractors, including Manufacturers, for each of those items. In addition, the Bidder shall include in its Bid information establishing compliance with the requirements specified by the Employer for these items. Bidders are free to list more than one Subcontractor against each item of the plant and services. Quoted rates and prices will be deemed to apply to whichever Subcontractor is appointed, and no adjustment of the rates and prices will be permitted. - The Bidder shall be responsible for ensuring that any Subcontractor proposed complies with the requirements of ITB 4, and that any Plant or Installation Services to be provided by the Subcontractor comply with the requirements of ITB 5 and ITB 16.1. |
| Bid Prices and Discounts | - Unless otherwise specified in the BDS and/or Section VI (Employer’s Requirements), Bidders shall quote for the entire Plant and Installation Services on a “single responsibility” basis such that the total Bid price covers all the Contractor’s obligations mentioned in or to be reasonably inferred from the Bidding Document in respect of the design, manufacture, including procurement and subcontracting (if any), delivery, construction, installation, and completion of the plant. This includes all requirements under the Contractor’s responsibilities for testing, pre-commissioning and commissioning of the plant and, where so required by the Bidding Document, the acquisition of all permits, approvals, and licenses, etc.; the operation, maintenance, and training services and such other items and services as may be specified in the Bidding Document, all in accordance with the requirements of the General Conditions. Items against which no price is entered by the Bidder will not be paid for by the Employer when executed and shall be deemed to be covered by the prices for other items. - Bidders are required to quote the price for the commercial, contractual, and technical obligations outlined in the Bidding Document. |
|  | - Bidders shall give a breakdown of the prices in the manner and detail called for in the Price Schedules included in Section IV (Bidding Forms). Where no different Price Schedules are included in the Bidding Document, Bidders shall present their prices in the following manner: Separate numbered Schedules included in Section IV (Bidding Forms) shall be used for each of the following elements. The total amount from each Schedule (Nos. 1 to 4) shall be summarized in a Grand Summary (Schedule No. 5) giving the total bid price(s) to be entered in the Letter of Bid. Absence of the total bid price in the Letter of Bid may result in the rejection of the Bid. Schedule No. 1: Plant and Mandatory Spare Parts Supplied from Abroad Schedule No. 2: Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country Schedule No. 3: Design Services Schedule No. 4: Installation and Other Services Schedule No. 5 Grand Summary (Schedule Nos. 1 to 4) Schedule No. 6: Recommended Spare Parts Bidders shall note that the plant and mandatory spare parts included in Schedule Nos. 1 and 2 above exclude materials used for civil, building, and other construction works. All such materials shall be included and priced under Schedule No. 4, Installation and Other Services. - In the Schedules, Bidders shall give the required details and a breakdown of their prices as follows: (a) Plant to be Supplied from Abroad (Schedule No. 1): - the price of the plant shall be quoted carriage and insurance paid (CIP)-named place of destination basis specified in the BDS; - all customs duties and other taxes paid or payable in the Employer’s country on the plant if the contract is awarded to the Bidder; and - the total price for the plant. (b) Plant Supplied from Within the Employer’s Country (Schedule No. 2): - the price of the plant shall be quoted on an EXW Incoterm basis (ex-works, ex-factory, ex-warehouse, ex-showroom, as applicable), including all customs duties and sales and other taxes already paid or payable on the components and raw material used in the manufacture or assembly of plant quoted ex-works or ex-factory, or on the previously imported plant of foreign origin quoted ex-warehouse, ex-showroom; - sales tax and other taxes payable in the Employer’s country on the plant if the contract is awarded to the Bidder; and - the total price for the plant. (c) Design Services. (Schedule No. 3). Rates or prices shall include all taxes, duties, levies, and charges payable in the Employer’s country as of twenty-eight (28) days prior to the deadline for submission of Bids. (d) Installation and Other Services (Schedule No. 4) shall be quoted separately and shall include rates or prices for local transportation to named place of final destination as specified in the BDS, insurance, and other services incidental to delivery of the plant, all labor, contractor’s equipment, temporary works, materials, consumables, and all matters and things of whatsoever nature, including operations and maintenance services, the provision of operations and maintenance manuals, training, etc., where identified in the Bidding Document, as necessary for the proper execution of the installation and other services, including all taxes, duties, levies and charges payable in the Employer’s country as of 28 days prior to the deadline for submission of bids. (e) Recommended spare parts (Schedule No. 6) shall be quoted separately as specified in either subparagraph (a) or (b) above in accordance with the origin of the spare parts. - The current edition of Incoterms, published by the International Chamber of Commerce shall govern. |
|  | - The prices shall be either fixed or adjustable as specified in the BDS. (a) In the case of Fixed Price, prices quoted by the Bidder shall be fixed during the Bidder’s performance of the contract and not subject to variation on any account. A Bid submitted with an adjustable price quotation will be treated as nonresponsive and rejected. (b) In the case of Adjustable Price, prices quoted by the Bidder shall be subject to adjustment during performance of the contract to reflect changes in the cost elements such as labor, material, transport and contractor’s equipment in accordance with the procedures specified in the corresponding Appendix to the Contract Agreement. A Bid submitted with a fixed price quotation will not be rejected, but the price adjustment will be treated as zero. Bidders are required to indicate the source of labor and material indices in the corresponding Form in Section IV (Bidding Forms). |
|  | - If so indicated in BDS 1.1, Bids are being invited for individual lots (contracts) or for any combination of lots (packages). Bidders wishing to offer any price reduction (discount) for the award of more than one contract shall specify in their Letter of Bid the price reductions applicable to each package, or alternatively, to individual contracts within the package, and the manner in which the price reductions will apply. - Bidders wishing to offer any unconditional discount shall specify in their Letter of Bid the offered discounts and the manner in which price discounts will apply. |
| Currencies of Bid and Payment | - The bidder shall quote the bid price in the currency specified in the BDS. - Bidders may be required by the Employer to justify, to the Employer’s satisfaction, their local and foreign currency requirements, and to substantiate that the amounts included in the unit rates and prices and shown in the Schedule of Adjustment Data in the Appendix to Bid are reasonable, in which case a detailed breakdown of the foreign currency requirements shall be provided by Bidders. - Notwithstanding ITB 19.1 above, a portion of the contract price may be stated in US Dollars within the amount of the Loan to be disbursed in US Dollars under the Provisions of the Loan Agreement. |
| Period of Validity of Bids | - Bids shall remain valid for the period specified in the BDS after the bid submission deadline date prescribed by the Employer. A bid valid for a shorter period shall be rejected by the Employer as nonresponsive. |
|  | - In exceptional circumstances, prior to the expiration of the bid validity period, the Employer may request Bidders to extend the period of validity of their Bids. The request and the responses shall be made in writing. If a bid security is requested in accordance with ITB 21, it shall also be extended twenty-eight (28) days beyond the deadline of the extended bid validity period. A Bidder may refuse the request without forfeiting its bid security. A Bidder granting the request shall not be required or permitted to modify its Bid, except as provided in ITB 20.3. - If the award is delayed by a period exceeding fifty-six (56) days beyond the expiry of the initial Bid validity specified in accordance with ITB 20.1, the Contract price shall be determined as follows: - in the case of fixed price contracts, the Contract price shall be the Bid price adjusted by the factor or factors specified in the BDS; - in the case of adjustable price contracts, to determine the Contract Price, the fixed portion of the Bid Price shall be adjusted by the factor specified in the BDS; or - in any case, Bid evaluation shall be based on the Bid price without taking into consideration the applicable correction from those indicated above. |
| Bid Security/Bid Securing Declaration | - The Bidder shall furnish as part of its bid, either a bid-securing declaration or a bid security as specified in the BDS, in original form. In the case of a bid security, the amount and currency shall be as specified in the BDS. - A Bid-Securing Declaration shall use the form included in Section IV (Bidding Forms). |
|  | - If a bid security is specified pursuant to ITB 21.1, the bid security shall be a demand guarantee in any of the following forms at the Bidder’s option: - an unconditional bank guarantee issued by a bank or surety; - an irrevocable letter of credit; - a cashier’s or certified check; or - another security indicated in the BDS, from a reputable source from an eligible country. In the case of a bank guarantee, the bid security shall be submitted using either the Bid Security Form included in Section IV (Bidding Forms) or another form acceptable to the Employer. The form must include the complete name of the Bidder. The bid security shall be valid for twenty-eight (28) days beyond the original validity period of the Bid, or beyond any period of extension if requested under ITB 20.2. |
|  | - If a bid security is specified pursuant to ITB 21.1, any bid not accompanied by a substantially responsive bid security or Bid-Securing Declaration shall be rejected by the Employer as nonresponsive. |
|  | - If a bid security is specified pursuant to ITB 21.1, the bid security of unsuccessful Bidders shall be returned as promptly as possible upon the successful Bidder’s furnishing of the performance security pursuant to ITB 45. |
|  | - The bid security of the successful Bidder shall be returned as promptly as possible once the successful Bidder has signed the Contract and furnished the required performance security. |
|  | - The bid security may be forfeited or the Bid-Securing Declaration executed: - If a Bidder withdraws its bid during the period of bid validity specified by the Bidder on the Letter of Bid Form, except as provided in ITB 20.2; or - If the successful Bidder fails to: - sign the Contract in accordance with ITB 44; or - furnish a performance security in accordance with ITB 45. |
|  | - The Bid Security or the Bid-Securing Declaration of a JVA shall be in the name of the JVA that submits the Bid. If the JVA has not been legally constituted into a legally enforceable JVA at the time of bidding, the Bid Security or the Bid Securing Declaration shall be in the names of all future members as named in the letter of intent referred to in ITB 4.1 and ITB 11.2. - If a Bid Security is not required in the BDS: and - If a Bidder withdraws its bid prior to the expiry date of the Bid validity specified by the Bidder on the Letter of Bid, or any extended date provided by the Bidder; or - If the successful Bidder fails to: - sign the Contract in accordance with ITB 44; or - furnish a performance security in accordance with ITB 45, the Borrower may, if provided for in the BDS, declare the Bidder disqualified to be awarded a contract by the Employer for a period of time as stated in the BDS. |
| Format and Signing of Bid | - The Bidder shall prepare one original set of the documents comprising the bid as described in ITB 11 and clearly mark it “ORIGINAL.” Alternative Bids, if permitted in accordance with ITB 13, shall be clearly marked “ALTERNATIVE.” In addition, the Bidder shall submit copies of the Bid, in the number specified in the BDS and clearly mark them “COPY.” In the event of any discrepancy between the original and the copies, the original shall prevail. |
|  | - The original and all copies of the Bid shall be typed or written in indelible ink and shall be signed by a person duly authorized to sign on behalf of the Bidder. This authorization shall consist of a written confirmation as specified in the BDS and shall be attached to the Bid. The name and position held by each person signing the authorization must be typed or printed below the signature. All pages of the Bid, except for un-amended printed literature, where entries or amendments have been made shall be signed or initialed by the person signing the Bid. |
|  | - A Bid submitted by a JVA shall comply with the following requirement: - Unless not required in accordance with ITB 4.1, be signed so as to be legally binding on all partners; and - Include the Representative’s authorization referred to in ITB 4.1(b), consisting of a power of attorney signed by those legally authorized to sign on behalf of the JVA. |
|  | - Any amendments such as interlineations, erasures, or overwriting shall be valid only if they are signed or initialed by the person signing the Bid. |
| Submission and Opening of Bids |  |
| Submission, Sealing and Marking of Bids | - Bidders may submit their Bids by mail or by hand. When so specified in the BDS, the Bidders shall have the option of submitting their Bids electronically. Procedures for submission, sealing and marking are as follows: - Bidders submitting Bids by mail or by hand shall enclose the original and each copy of the Bid, including alternative Bids, if permitted in accordance with ITB 13, in separate sealed envelopes, duly marking the envelopes as “Original,” “Alternative,” and “Copy.” These envelopes containing the original and the copies shall then be enclosed in one single envelope. The rest of the procedure shall be in accordance with ITB 23.2 to ITB 23.3; and - The Bidders submitting Bids electronically shall follow the electronic bid submission procedure specified in the BDS. |
|  | - The inner and outer envelopes shall: - bear the name and address of the Bidder; - be addressed to the Employer in accordance with ITB 24.1; - bear the specific identification of this bidding process indicated in the BDS 1.1; and - bear a warning not to open before the time and date for bid opening. - If all envelopes are not sealed and marked as required, the Employer will assume no responsibility for the misplacement or premature opening of the Bid. |
| Deadline for Submission of Bids | - Bids must be received by the Employer at the address and no later than the date and time indicated in the BDS. |
|  | - The Employer may, at its discretion, extend the deadline for the submission of bids by amending the Bidding Document in accordance with ITB 8, in which case all rights and obligations of the Employer and Bidders previously subject to the deadline shall thereafter be subject to the deadline as extended. |
| Late Bids | - The Employer shall not consider any Bid that arrives after the deadline for submission of Bids, in accordance with ITB 24. Any Bid received by the Employer after the deadline for submission of Bids shall be declared late, rejected, and returned unopened to the Bidder. |
| Withdrawal, Substitution, and Modification of Bids | - A Bidder may withdraw, substitute, or modify its Bid after it has been submitted by sending a written notice, duly signed by an authorized representative, and shall include a copy of the authorization in accordance with ITB 22.2 (except for withdrawal notices, which do not require copies). The corresponding substitution or modification of the Bid must accompany the respective written notice. All notices must be: - prepared and submitted in accordance with ITB 22 and ITB 23 (except for withdrawal notices, which do not require copies), and in addition, the respective envelopes shall be clearly marked “WITHDRAWAL,” “SUBSTITUTION,” “MODIFICATION”; and - received by the Employer prior to the deadline prescribed for submission of Bids, in accordance with ITB 24. |
|  | - Bids requested to be withdrawn in accordance with ITB 26.1 shall be returned unopened to the Bidders. |
|  | - No Bid may be withdrawn, substituted, or modified in the interval between the deadline for submission of Bids and the expiration of the period of bid validity specified by the Bidder on the Letter of Bid or any extension thereof. |
| Bid Opening | - The Employer shall open the Bids in public at the address, on the date, and time specified in the BDS in the presence of Bidder’s designated representatives and anyone who choose to attend. Any specific electronic bid opening procedures required if electronic bidding is permitted in accordance with ITB 23.1, shall be as specified in the BDS. |
|  | - First, envelopes marked “WITHDRAWAL” shall be opened and read out and the envelope with the corresponding Bid shall not be opened, but returned to the Bidder. No bid withdrawal shall be permitted unless the corresponding withdrawal notice contains a valid authorization to request the withdrawal and is read out at bid opening. Next, envelopes marked “SUBSTITUTION” shall be opened and read out and exchanged with the corresponding Bid being substituted. The substituted Bid shall not be opened, but returned to the Bidder. No bid substitution shall be permitted unless the corresponding substitution notice contains a valid authorization to request the substitution and is read out at bid opening. Envelopes marked “MODIFICATION” shall be opened and read out with the corresponding Bid. No bid modification shall be permitted unless the corresponding modification notice contains a valid authorization to request the modification and is read out at bid opening. Only envelopes that are opened and read out at bid opening shall be considered further. |
|  | - All other envelopes shall be opened one at a time, reading out the name of the Bidder and whether there is a modification; the Bid Price(s), including any discounts and alternative Bids; the presence of a bid security, or a Bid-Securing Declaration, if required; and any other details as the Employer may consider appropriate. Only discounts and alternative Bids read out at bid opening shall be considered for evaluation. Unless otherwise specified in the BDS, all pages of the Letter of Bid and Price Schedules are to be initialed by at least three representatives of the Employer attending the bid opening. No Bid shall be rejected at bid opening except for late Bids, in accordance with ITB 25.1. |
|  | - The Employer shall prepare a record of the bid opening that shall include, as a minimum: the name of the Bidder and whether there is a withdrawal, substitution, or modification; the Bid Price, per contract if applicable, including any discounts and alternative Bids; and the presence or absence of a bid security or a Bid-Securing Declaration, if one was required. The Bidders’ representatives who are present shall be requested to sign the record. The omission of a Bidder’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall be distributed to all Bidders who submitted Bids on time, and posted online when electronic bidding is permitted. |
| Evaluation and Comparison of Bids |  |
| Confidentiality | - Information relating to the examination, clarification, and evaluation of bids and proposals concerning awards shall not be disclosed to Bidders or any other persons not officially concerned with the Bidding process until information on Contract award is communicated to all Bidders in accordance with ITB 42. |
|  | - Any attempt by a Bidder to influence the Employer in the evaluation of the Bids or Contract award decisions may result in the rejection of its Bid. |
|  | - Notwithstanding ITB 28.2, from the time of bid opening to the time of Contract award, if any Bidder wishes to contact the Employer on any matter related to the bidding process, it should do so in writing. |
| Clarification of Bids | - To assist in the examination, evaluation, and comparison of the Bids, and qualification of the Bidders, the Employer may, at its discretion, ask any Bidder for a clarification of its Bid. Any clarification submitted by a Bidder that is not in response to a request by the Employer shall not be considered. The Employer’s request for clarification and the response shall be in writing. No change in the prices or substance of the Bid shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the Bids, in accordance with ITB 34. |
|  | - If a Bidder does not provide clarifications of its Bid by the date and time set in the Employer’s request for clarification, its Bid may be rejected. |
| Deviations, Reservations, and Omissions | - During the evaluation of Bids, the following definitions apply: - “Deviation” is a departure from the requirements specified in the Bidding Document; - “Reservation” is the setting of limiting conditions or withholding from complete acceptance of the requirements specified in the Bidding Document; and - “Omission” is the failure to submit part or all of the information or documentation required in the Bidding Document. |
| Preliminary Examination of Bids | - The Employer shall examine the bids to confirm that all documents and technical documentation requested in ITB Clause 11 have been provided, and to determine the completeness of each document submitted. - The Employer shall confirm that the following documents and information have been provided in the Bid. If any of these documents or information is missing, the offer shall be rejected: - Letter of Bid, in accordance with ITB Sub-Clause 12; - Written confirmation of authorization to commit the Bidder; - Price Schedules, in accordance with ITB Sub-Clause 12; or - Bid Security or Bid Securing Declaration, in accordance with ITB Clause 21, if applicable. |
| Determination of Responsiveness | - The Employer’s determination of a bid’s responsiveness is to be based on the contents of the Bid itself, as defined in ITB 11. |
|  | - A substantially responsive Bid is one that meets the requirements of the Bidding Document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that, - if accepted, would: - affect in any substantial way the scope, quality, or performance of the Plant and Installation Services specified in the Contract; or - limit in any substantial way, inconsistent with the Bidding Document, the Employer’s rights or the Bidder’s obligations under the proposed Contract; or - if rectified, would unfairly affect the competitive position of other Bidders presenting substantially responsive Bids. |
|  | - The Employer shall examine the technical aspects of the Bid submitted in accordance with ITB 17, Technical Proposal, in particular, to confirm that all requirements of Section VI (Employer’s Requirements) have been met without any material deviation, reservation, or omission. |
|  | - If a Bid is not substantially responsive to the requirements of the Bidding Document, it shall be rejected by the Employer and may not subsequently be made responsive by correction of the material deviation, reservation, or omission. |
| Nonmaterial Nonconformities | - Provided that a Bid is substantially responsive, the Employer may waive any nonconformities in the Bid that do not constitute a material deviation, reservation, or omission. |
|  | - Provided that a Bid is substantially responsive, the Employer may request that the Bidder submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the Bid related to documentation requirements. Requesting information or documentation on such nonconformities shall not be related to any aspect of the price of the Bid. Failure of the Bidder to comply with the request may result in the rejection of its Bid. |
|  | - Provided that a Bid is substantially responsive, the Employer shall rectify quantifiable nonmaterial nonconformities related to the Bid Price. To this effect, the Bid Price shall be adjusted, for comparison purposes only, to reflect the price of a missing or nonconforming item or component. The adjustment shall be made using the method indicated in Section III (Evaluation and Qualification Criteria). |
| Correction of Arithmetical Errors | - Provided that the Bid is substantially responsive, the Employer shall correct arithmetical errors on the following basis: - where there are errors between the total of the amounts given under the column for the price breakdown and the amount given under the Total Price, the amounts given under the column for the price breakdown shall prevail and the Total Price will be corrected accordingly; - where there are errors between the total of the amounts of Schedule Nos. 1 to 4 and the amount given in Schedule No. 5 (Grand Summary), the total of the amounts of Schedule Nos. 1 to 4 shall prevail and the Schedule No. 5 (Grand Summary) will be corrected accordingly; - if there is a discrepancy between the grand total price given in Schedule No. 5 (Grand Summary) and the bid amount in item (e) of the Letter of Bid, the grand total price given in Schedule No. 5 (Grand Summary) will prevail and the bid amount in item (e) of the Letter of Bid will be corrected; and - if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetical error, in which case the amount in figures shall prevail subject to (a), (b) and (c) above. |
|  | - If the Bidder that submitted the lowest evaluated Bid does not accept the correction of errors, its Bid shall be disqualified and its bid security may be forfeited, or its Bid-Securing Declaration executed. |
| Conversion to Single Currency | - For evaluation and comparison purposes, the Employer shall convert all bid prices expressed in amounts in various currencies into an amount in a single currency specified in the BDS, using the selling exchange rates established by the source and on the date specified in the BDS. |
| Evaluation and Comparison of Bids | - The Employer shall use the criteria and methodologies indicated in this clause. No other evaluation criteria or methodologies shall be permitted. |
|  | - Technical Evaluation The Employer will carry out a detailed technical evaluation of the Bids not previously rejected as being substantially nonresponsive, to determine whether the technical aspects are in compliance with the Bidding Document. The Bid that does not meet required minimum acceptable standards of completeness, consistency and detail, and the specified minimum and/or maximum requirements for specified functional guarantees will be treated as nonresponsive and hence rejected. To reach such a determination, the Employer will examine and compare the technical aspects of the bids on the basis of the information supplied by the Bidders, taking into account the following: - overall completeness and compliance with the Employer’s Requirements; deviations from the Employer’s Requirements; conformity of the Plant and Installation Services offered with specified performance criteria; suitability of the Plant and Installation Services offered in relation to the environmental and climatic conditions prevailing at the site; and quality, function and operation of any process control concept included in the Bid. The Bid that does not meet minimum and/or maximum acceptable standards of completeness, consistency and detail will be rejected for nonresponsiveness; - type, quantity, and long-term availability of mandatory and recommended spare parts and maintenance services; and - other relevant factors, if any, listed in Section III (Evaluation and Qualification Criteria). |
|  | - Where alternative technical solutions have been allowed in accordance with ITB 13, and offered by the Bidder, the Employer will make a similar evaluation of the alternatives. Where alternatives have not been allowed but have been offered, they shall be ignored. |
|  | - Economic Evaluation I. To evaluate a Bid, the Employer shall consider the following: - the bid price, excluding provisional sums and the provision, if any, for contingencies in the Price Schedules; - price adjustment for correction of arithmetical errors in accordance with ITB 34.1; - price adjustment due to discounts offered in accordance with ITB 18.7; - price adjustment due to quantifiable nonmaterial nonconformities in accordance with ITB 33.3; - converting the amount resulting from applying (a) to (d) above, if relevant, to a single currency in accordance with ITB 35; and - the evaluation factors indicated in Section III (Evaluation and Qualification Criteria). II. The Employer’s evaluation of a Bid will exclude and not take into account: - in the case of Plant and Mandatory Spare Parts (Schedule No. 1) supplied from abroad, all taxes and duties, applicable in the Employer’s country and payable on the Plant and Mandatory Spare Parts if the Contract is awarded to the Bidder; and - in the case of Plant and Mandatory Spare Parts (Schedule No. 2) supplied from within the Employer’s country, sales and other taxes, applicable in the Employer’s country and payable on the Plant and Mandatory Spare Parts if the Contract is awarded to the Bidder. |
|  | - If price adjustment is allowed in accordance with ITB 18.6, the estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in bid evaluation. |
|  | - If this Bidding Document allows Bidders to quote separate prices for different lots (contracts), and the award to a single Bidder of multiple lots (contracts), the methodology to determine the lowest evaluated price of the lot (contract) combinations, including any discounts offered in the Letter of Bid, is specified in Section III (Evaluation and Qualification Criteria). |
|  | - If the Bid, which results in the lowest Evaluated Bid Price, is seriously unbalanced or front loaded in the opinion of the Employer or the Bid is significantly lower than the Employer’s estimates, the Employer may require the Bidder to produce detailed price analyses for any or all items of the Price Schedules, to demonstrate the internal consistency of those prices with the methods and time schedule proposed. After evaluation of the price analyses, taking into consideration the terms of payments, the Employer may require that the amount of the performance security be increased at the expense of the Bidder to a level sufficient to protect the Employer against financial loss in the event of default of the successful Bidder under the Contract. - The Employer shall compare all substantially responsive Bids to determine the lowest evaluated Bid, in accordance with ITB 36.4. |
| Eligibility and Qualification of the Bidder | - The Employer shall determine to its satisfaction whether the Bidder that is selected as having submitted the lowest evaluated cost and substantially responsive Bid is eligible and either continues to meet (if Prequalification applies) or meets (if post-qualification applies) the qualifying criteria specified in Section III (Evaluation and Qualification Criteria). |
|  | - The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB 15. The determination shall not take into consideration the qualifications of other firms such as the Bidder’s subsidiaries, parent entities, affiliates, subcontractors (other than Specialist Subcontractors if permitted in the bidding document), or any other firm(s) different from the Bidder. |
|  | - An affirmative determination shall be a prerequisite for award of the Contract to the Bidder. A negative determination shall result in disqualification of the Bid, in which event the Employer shall proceed to the next lowest evaluated Bid to make a similar determination of that Bidder’s qualifications to perform satisfactorily. |
|  | - The capabilities of the manufacturers and subcontractors proposed in its Bid for the major items of Plant and Installation Services to be used by the lowest evaluated Bidder will also be evaluated for acceptability in accordance with Section III (Evaluation and Qualification Criteria). Their participation should be confirmed with a letter of intent between the parties, as needed. Should a manufacturer or subcontractor be determined to be unacceptable, the Bid will not be rejected, but the Bidder will be required to propose, without changing its bid price, an acceptable substitute manufacturer or subcontractor meeting the minimum technical specifications stated in Section VI (Employer’s Requirements). If a Bidder does not provide an acceptable substitute manufacturer or subcontractor by the date and time set in the Employer’s request for substitution of manufacturer or subcontractor, its Bid may be rejected. |
|  | - Prior to signing the Contract, the corresponding Appendix to the Contract Agreement shall be completed, listing the approved manufacturers or subcontractors for each item concerned. |
| Employer’s Right to Accept Any Bid, and to Reject Any or All Bids | - The Employer reserves the right to accept or reject any Bid, and to annul the bidding process and reject all Bids at any time prior to contract award, without thereby incurring any liability to Bidders. In case of annulment, all Bids submitted and specifically, bid securities, shall be promptly returned to the Bidders. |
| Award of Contract |  |
| Award Criteria | - The Employer shall award the Contract to the Bidder whose offer has been determined successful in line with ITB 36 and ITB 37 above to be the lowest evaluated Bid and is substantially responsive to the Bidding Document, provided further that the Bidder is determined to be eligible and qualified to perform the Contract satisfactorily. |
| Standstill Period | - If the Standstill Period is applied as specified in the BDS, the Contract shall not be awarded earlier than the expiry of the Standstill Period. The Standstill Period shall be ten (10) Business Days unless extended in accordance with ITB 43.1. The Standstill Period commences the day after the date the Employer has transmitted to each Bidder the Notification of Intention to Award the Contract. In case where only one Bid is submitted, or in case of direct contracting, the Standstill Period shall not apply. |
| Notification of Intention to Award | - If the Standstill Period is applied in accordance with ITB 40.1, the Employer shall send to each Bidder the Notification of Intention to Award the Contract, using the applicable form included in Section IX. Contract Forms, as per the instructions specified in the BDS. |
| Notification of Award | - Prior to the expiration of the period of bid validity, the Employer shall notify the successful Bidder, in writing, using the Notification of Award form included in Section IX. Contract Forms, that its bid has been accepted. At the same time, the Employer shall also notify unsuccessful Bidders of the results of the bidding including the following information: - name of each Bidder who submitted a Bid; - bid prices as read out at bid opening; - name and evaluated prices of each bid that was evaluated; - name of Bidders whose Bids were rejected and the reasons for their rejection; and - name of the winning Bidder, and the price it offered, as well as the duration and summary scope of the contract awarded. - Until a formal contract is prepared and executed, the notification of award shall constitute a binding Contract. - Notwithstanding the foregoing, if the Standstill Period is applied, the Employer shall, prior to the expiration of the period of bid validity and upon expiry of the Standstill Period specified in ITB 40.1 or any extension thereof, and upon satisfactorily addressing any Complaint that has been filed within the Standstill Period, notify the successful Bidder, in writing, using the Notification of Award form included in Section IX. Contract Forms, that its Bid has been accepted. |
| Debriefing by the Employer | - If the Standstill Period is applied, upon receipt of the Employer’s Notification of Intention to Award referred to in ITB 41.1, an unsuccessful Bidder has three (3) Business Days to make a written request to the Employer for a debriefing. The Employer shall provide a debriefing to all unsuccessful Bidders whose request is submitted in compliance with the procedures as set forth in the BDS and is received within this deadline. - Where a request for debriefing is received within the deadline, the Employer shall provide a debriefing within five (5) Business Days, unless the Employer decides, for justifiable reasons, to provide the debriefing outside this timeframe. In that case, the standstill period shall automatically be extended until five (5) Business Days after such debriefing is provided. If more than one debriefing is so delayed, the standstill period shall not end earlier than five (5) Business Days after the last debriefing takes place. The Employer shall promptly inform, by the quickest means available, all Bidders of the extended standstill period. - Where a request for debriefing is received by the Employer later than the three (3)-Business Day deadline, the Employer should provide the debriefing as soon as practicable, and normally no later than fifteen (15) Business Days from the date of publication of the Contract award. Requests for debriefing received outside the three (3)-day deadline shall not lead to extension of the standstill period. - In a non-Standstill situation where the Standstill Period is not applied, the Employer shall promptly respond either in writing and/or in a debriefing meeting (at the option of the Employer) to any unsuccessful Bidder who, after notification of award in accordance with ITB 42.1, requests in writing the grounds on which its bid was not selected. - Debriefings of unsuccessful Bidders may be done in writing or verbally. The Bidder shall bear their own costs of attending such a debriefing meeting. |
| Signing of Contract | - Promptly after Notification of Award, the Employer shall send the successful Bidder the Contract Agreement. |
|  | - Within twenty-eight (28) days of receipt of the Contract Agreement, the successful Bidder shall sign, date, and return it to the Employer. - Notwithstanding ITB 44.2 above, in case signing of the Contract Agreement is prevented by any export restrictions attributable to the Employer, to the country of the Employer, or to the use of the Plant and Installation Services to be supplied, where such export restrictions arise from trade regulations from a country supplying those Plant and Installation Services, the Bidder shall not be bound by its Bid, always provided, however, that the Bidder can demonstrate to the satisfaction of the Employer and of the Bank that signing of the Contract Agreement has not been prevented by any lack of diligence on the part of the Bidder in completing any formalities, including applying for permits, authorizations and licenses necessary for the export of the Plant and Installation Services under the terms of the Contract. |
| Performance Security | - Within twenty-eight (28) days of the receipt of notification of award from the Employer, the successful Bidder shall furnish the Performance Security in accordance with the Conditions of Contract, subject to ITB 36.7, using for that purpose the Performance Security Form included in Section IX Contract forms, or another Form acceptable to the Employer. - Failure of the successful Bidder to submit the above-mentioned Performance Security or sign the Contract shall constitute sufficient grounds for the annulment of the award and forfeiture of the bid security or execution of the Bid-Securing Declaration. In that event, the Employer may award the Contract to the next lowest evaluated Bidder whose offer is substantially responsive and is determined by the Employer to be qualified to perform the Contract satisfactorily. |
| Procurement-related Complaint | - Procurement-related Complaint (hereinafter called the “Complaint”) shall be submitted in compliance with the procedures as set forth in the BDS. - When so submitted to the Employer, the Employer shall address Complaints promptly and fairly. - Any Complaint shall identify the name, contact details (i.e. telephone number and e-mail address), address of the complainant, the complainant’s interest in the relevant procurement, the specific project, the source and nature of the Complaint, any previous communication between the complainant and the Employer on the matters addressed in the Complaint, the alleged inconsistency with the applicable procurement rules, and any other relevant information. - If the sources of information related to the Complaint and the identity of the complainant are not clear, detailed information with supporting documents shall be submitted at the request of the Employer. Should such information not be provided appropriately, the Complaint shall not be received. - If the Standstill Period is applied in accordance with ITB 40.1, Complaints following the submission of a Bid must be submitted to the Employer within the Standstill Period or any extension thereof (where applicable in accordance with ITB Sub-Clause 43.1 (a)), and received by the Employer before the Standstill Period ends. |

Section II. Bid Data Sheet
(Single Stage: One-Envelope)

The following specific data for the Facilities to be procured shall complement, supplement, or amend the provisions in the Instructions to Bidders (ITB). Whenever there is a conflict, the provisions herein shall prevail over those in ITB.

[Instructions for completing the Bid Data Sheet are provided, as needed, in the notes in italics mentioned for the relevant ITB.]

| A. General |  |
| --- | --- |
| ITB 1.1 | The number of the Invitation for Bids (IFB) is: [Insert number of the Invitation for Bids] |
| ITB 1.1 | The Employer is: [Insert name of the Employer] |
| ITB 1.1 | The name of the competitive bidding (CB) is: [Insert name of the CB] The identification number of the CB is: [Insert number of the CB] [The following text is to be included and the corresponding information inserted only if the contract is to be bid simultaneously with other contracts on a “slice and package” basis. Otherwise omit.] The number and identification of lots (contracts) comprising this CB is: [Insert number and identification of lots (contracts)] |
| ITB 2.1 | The Borrower is: [Insert name of the Borrower and statement of relationship with the Employer, if different from the Borrower. This insertion should correspond to the information provided in the Invitation for Bids] |
|  | The name of the Project is: [Insert name of the project] |
| ITB 3.4 | Address for the Bank: 38 Eunhaengno (16-1 Yeouido-dong), Yeongdeungpo-gu, Seoul, Korea 07242 TEL: 82-2-3779-xxxx FAX: 82-2-3779-xxxx E-Mail: xxxxxxx@koreaexim.go.kr Attention: |
| ITB 4.3 (f) | For a Bidder who participated as a consultant in the preparation of the feasibility study, this provision does not limit the participation of a Bidder if participating solely for the purpose of serving as a consultant under a turnkey or design and build contract. |
| ITB 4.5 | This clause shall be [Insert “applied” or “deleted” in accordance with the restrictions regarding nationality of Eligible Bidder specified in ITB 4.2] |
| B. Contents of Bidding Document |  |
| ITB 7.1 | For clarification purposes only, the Employer’s address is: [Insert the corresponding information as required below. This address may be the same as or different from that specified under provision ITB 23.1 for bid submission.] Attention: [Insert name and room number of Project Officer.] Address: [Insert street address and number.] Floor/Room number: [Insert floor and room number, if applicable.] City: [Insert name of city or town.] ZIP Code: [Insert postal (ZIP) code, if applicable.] Country: [Insert name of country.] Telephone: [Insert telephone number, including country and city codes.] Facsimile number: [Insert fax number, including country and city codes.] E-mail: [Insert email address of Project Officer.] |
| ITB 7.4 | A Pre-Bid meeting [Insert “will” and insert the date, time and place information in the spaces provided below if a pre-bid meeting will take place, taking into consideration that the meeting should take place no later than four weeks before the deadline for bid submission. Otherwise, insert “will not” and insert “Not Applicable” in the spaces provided below for the date, time and place.] takes place at the following date, time and place: Date: Time: Place: A site visit conducted by the Employer [Insert “shall be” or “shall not be.”] organized. |
| C. Preparation of Bids |  |
| ITB 11.1 (k) | The Bidder shall submit with its bid the following additional documents in its Bid: [Specify any additional document not already listed in ITB 11.1 that must be submitted with the Bid.] |
| ITB 13.1 | [The following provision should be included and the required corresponding information inserted only if alternative bids will be considered. Otherwise omit.] Alternative bids [Insert “shall be”] permitted. |
| ITB 13.2 | Alternative times for completion [Insert “will be” or “will not be”, as appropriate] permitted. [Alternative times for completion should be permitted when the Employer sees potential net benefits in different times for completion; they also have merit for contracts bid on a “slice and package” basis.] If alternatives times for completion are permitted, the evaluation method will be as specified in Section III (Evaluation and Qualification Criteria). |
| ITB 13.4 | Alternative technical solutions shall be permitted for the following parts of the Plant and Installation Services: [Insert parts of the Plant] as further detailed in the Specification. If alternative technical solutions are permitted, the evaluation method will be as specified in Section III (Evaluation and Qualification Criteria). |
| ITB 16.1(b) | The period following completion of Plant and Installation Services during which spare parts, special tools etc. shall be available, is [insert number of years as appropriate, normally two (2) years] __________________. |
| ITB 18.1 | [Choose one of the following options as appropriate.] Bidders shall quote for the entire Plant and Installation Services on a single responsibility basis. [or] Bidders shall quote for the following components or services on a single responsibility basis: [insert list of components or services] ________________________________________________ [and/or] The following components or services will be provided under the responsibility of the Employer: [insert list of components or services] ________________________________________________ |
| ITB 18.4 | In accordance with the Loan Agreement, all taxes, duties and levies, including but not limited to import duties and Value-Added Tax, imposed on goods, works, Plant and Installation Services to be used in [insert the name of the Borrower’s country], provided and/or purchased from any countries by the Contractor, subcontractors and/or local suppliers of any countries under the Loan Agreement for the implementation of the Contract shall be [choose one of the following: “exempted,” “reimbursed,” “paid by the Employer on behalf of the Contractor” as appropriate.] |
| ITB 18.4 (a) and (d) | Place of destination: [insert named place of destination as per Incoterm used] Final destination (Project Site): ___________ [insert final destination, if different from named place of destination] |
| ITB 18.5 | The Incoterms edition is: [insert relevant edition]. |
| ITB 18.6 | The prices quoted by the Bidder shall be [insert “fixed” or “adjustable.”] [If prices are to be adjustable, insert: “The formula for adjusting the prices and explanatory details are specified in the Special Conditions of Contract (SCC) Clause 11.2 and Appendix 2 of Contract Agreement. Bidder shall fill out the Tables of Adjustment Data in Section IV (Bidding Forms).”] [Use “Adjustable” where the contract period is of long duration (generally exceeds eighteen (18) months). Prices payable to the contractor shall be subject to price adjustment during the performance of the contract.] [If prices shall be fixed, the Tables of Adjustment Data in Section IV (Bidding Forms) shall be removed.] |
| ITB 19.1 | [Insert one of the followings in accordance with Loan Agreement.] [If the Loan is denominated in Korean Won.] The bid price shall be stated in US Dollars. However, the contract price shall be stated in Korean Won converted by using the exchange rate which is the average of the telegraphic transfer selling rates on the Korean Won against the US Dollar as quoted and publicly displayed by the Bank, during the one month period from the sixteenth (16th) day of two calendar months prior to the month when the contract is signed, to the fifteen (15th) day of one calendar month prior thereto. [If the Loan is denominated in US Dollars, Euro, or any other currency apart from the Korean Won.] The bid price shall be stated in [Insert the currency according to the Loan Agreement.] |
| ITB 20.1 | The bid validity period shall be [Insert a number of days that is a multiple of seven counting as of the deadline for bid submission.] days. [This period should be realistic, allowing sufficient time to evaluate the bids, bearing in mind the complexity of the Plant and the time required for obtaining references, clarifications, clearances, and approvals (including the Bank’s “No Objection”) and for notification of the award. Normally the validity period should not exceed one hundred and twenty (120) days.] |
| ITB 20.3 (a) | The bid price shall be adjusted by the following factor(s): _____________ [The local currency portion of the Contract price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the Contract price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.] Note: If Adjustable Price is applied in accordance with BDS 18.6; Not Applicable. |
| ITB 20.3 (b) | The fixed portion of the Bid Price shall be adjusted by the following factor(s): _____________ [The local currency portion of the fixed portion of the Contract price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the fixed portion of the Contract price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.] Note: If there is no fixed portion of the Bid price, or the entire price is fixed; Not Applicable. |
| ITB 21.1 | [If a bid security shall be required, a Bid-Securing Declaration shall not be required, and vice versa.] A bid security [Insert “shall be” or “shall not be”] required. A Bid-Securing Declaration [Insert “shall be” or “shall not be”] required. If a bid security shall be required, the amount and currency of the Bid Security shall be: [If a bid security is required, insert amount and currency of the bid security. Otherwise insert “Not Applicable”.] |
| ITB 21.3(a) | The bid security shall be issued by a bank, insurance company, or financial institution in the Employer’s country or Contractor's country whose credit rating is equal or above A- (A3) (equivalent) rated by an international credit rating agency (e.g., S&P, Fitch, or Moody's). [The credit rating may be adjusted based on the financial situations in either the Employer’s or the Contractor’s country] |
| ITB 21.3 (d) | Other types of acceptable securities: ____________________________________________________________ [Insert name of other acceptable securities. Insert “None” if no bid security is required under provision ITB 21.1 or if bid security is required but no other forms of bid securities besides those listed in ITB 21.3 (a) through (c) are acceptable.] |
| ITB 21.9 | [Delete if not applicable: The following provision should be included and the required corresponding information inserted only if a bid security is not required under provision ITB 21.1 and the Employer wishes to declare the Bidder ineligible for a period of time should the Bidder perform any of the actions mentioned in provision ITB 21.9 (a) and (b). Otherwise omit.] If the Bidder incurs any of the actions prescribed in ITB 21.9 (a) or (b), the Borrower will declare the Bidder ineligible to be awarded a contract by the Employer for a period of ________ [Insert period of time] years. |
| ITB 22.1 | In addition to the original of the bid, the number of copies is: [Insert number of copies] ____________. |
| ITB 22.2 | The written confirmation of authorization to sign on behalf of the Bidder shall consist of: [Insert the name and description of the documentation required to demonstrate the authority of the signatory to sign the bid]. |
| D. Submission and Opening of Bids |  |
| ITB 23.1 | Bidders [insert “shall” or “shall not”] have the option of submitting their bids electronically. |
| ITB 23.1 (b) | [The following provision should be included and the required corresponding information inserted only if Bidders have the option of submitting their bids electronically. Otherwise omit.] The electronic bidding submission procedures shall be: [Insert a description of the electronic bidding submission procedures.] |
| ITB 24.1 | For bid submission purposes only, the Employer’s address is: [This address may be the same as or different from that specified under provision ITB 7.1 for clarifications.] Attention: [Insert full name of person, if applicable.] Street Address: [Insert street address and number.] Floor/Room number: [Insert floor and room number, if applicable.] City: [Insert name of city or town.] ZIP Code: [Insert postal (ZIP) code, if applicable.] Country: [Insert name of country.] [The time allowed for the preparation and submission of bids shall be determined with due consideration of the particular circumstances of the Project and the size and complexity of the contract. Where large works or complex items of equipment are involved, the period from the date of the invitation to bid or the date of availability of bidding documents, whichever is later, shall be generally not less than ninety (90) days to enable prospective bidders to conduct investigations at the site before submitting their bids.] The deadline for bid submission is: Date: [Insert day, month and year, i.e. 15 June 2020] Time: [Insert time, and identify if a.m. or p.m., i.e. 10:30 a.m.] [The date and time should be the same as those provided in the Invitation for Bids, unless subsequently amended pursuant to ITB 24.2.] |
| ITB 27.1 | The Bid opening shall take place at: Street Address: [Insert street address and number] Floor/Room number: [Insert floor and room number, if applicable.] City: [Insert name of city or town Country: [Insert name of country] Date: [Insert day, month, and year, i.e. 15 June 2020] Time: [Insert time, and identify if a.m. or p.m., i.e. 10:30 a.m.] [The date and time should be the same as those given for the deadline for submission of bids in accordance with ITB 24] |
| ITB 27.1 | [The following provision should be included and the required corresponding information inserted only if Bidders have the option of submitting their bids electronically. Otherwise omit.] The electronic bid opening procedures shall be: [Insert a description of the electronic bid opening procedures.] |
| ITB 27.3 | The Letter of Bid and Price Schedules shall be initialed by _______ [insert number] representatives of the Employer conducting Bid opening. __________ [Insert procedure: Example: Each Bid shall be initialed by all representatives and shall be numbered, any modification to the unit or total price shall be initialed by the Representative of the Employer, etc.] |
| E. Evaluation and Comparison of Bids |  |
| ITB 35.1 | The currency that shall be used for Bid evaluation and comparison purposes to convert (at the selling exchange rate) all Bid prices expressed in various currencies into a single currency is: ____________ [Insert name of currency] The source of exchange rate shall be: ___________ [Insert name of the source of exchange rates (e.g., the Central Bank in the Employer’s Country).] The date for the exchange rate shall be: [insert day, month and year, e.g. 15 June, 2020 not earlier than twenty-eight (28) days prior to the deadline for submission of the Bids, nor later than the original date for the expiry of bid validity specified in accordance with ITB BDS 20.1]. |
| F. Award of Contract |  |
| ITB 40.1 | The Standstill Period [insert “shall” or “shall not”] be applied. |
| ITB 41.1 | The Notification of Intention to Award the Contract shall contain, at a minimum, the following information: (a) the name and address of the Bidder submitting the successful Bid; (b) the contract price of the successful Bid; (c) the names of all Bidders who submitted Bids, and their Bid prices as readout, and as evaluated; and (d) a statement of the reason(s) why the Bid was unsuccessful, unless the price information in (c) above already reveals the reason. |
| ITB 45.1 | The Performance Security and the Advance Payment Security shall be in the form attached hereto in Section IX (Contract Forms), or another form acceptable to the Employer. The both of the Securities shall be issued by a bank, insurance company, or financial institution in the Employer’s country or the Contractor's country whose credit rating is equal or above A- (A3) (equivalent) rated by an international credit rating agency (e.g., S&P, Fitch, or Moody's). [The credit rating may be adjusted based on the financial situations in either the Employer’s or the Contractor’s country] |
| ITB 43.1/46.1 | Any Complaint related to the Procurement shall be submitted in writing, to: Attention: __________________ Title/position: _____________________ Employer: ________________________ E-mail address: ____________________ Facsimile number: ________________ Any Complaint related to fraud or corruption associated with the Employer or any interested party in the Procurement process shall be submitted in writing, to: Attention: __________________ Title/position: _____________________ Anti-Corruption Unit*: ________________________ E-mail address: ____________________ Facsimile number: ________________ [* Any entity vested with the authority to address matters of fraud or corruption within the Employer’s parent ministry, the ministry responsible for administering the EDCF Loan, or the government body overseeing public procurement.] |

Section I. Instructions to Bidders
(Single-Stage: Two-Envelope)

Table of Clauses

A.	General	45

1.	Scope of Bid	45

2.	Source of Funds	45

3.	Fraud and Corruption	45

4.	Eligible Bidders	48

5.	Eligible Plant and Installation Services	50

B.	Contents of Bidding Document	50

6.	Sections of Bidding Document	50

7.	Clarification of Bidding Document, Site Visit, Pre-Bid Meeting	51

8.	Amendment of Bidding Document	52

C.	Preparation of Bids	52

9.	Cost of Bidding	52

10.	Language of Bid	52

11.	Documents Comprising the Bid	52

12.	Letter of Bid and Schedules	53

13.	Alternative Bids	53

14.	Documents Establishing the Eligibility of Plant and Installation Services	54

15.	Documents Establishing the Eligibility and Qualifications of the Bidder	54

16.	Documents Establishing Conformity of the Plant and Installation Services	54

17.	Technical Proposal, Subcontractors	55

18.	Bid Prices and Discounts	55

19.	Currencies of Bid and Payment	58

20.	Period of Validity of Bids	58

21.	Bid Security/Bid Securing Declaration	59

22.	Format and Signing of Bid	60

D.	Submission and Opening of Bids	61

23.	Submission, Sealing and Marking of Bids	61

24.	Deadline for Submission of Bids	62

25.	Late Bids	62

26.	Withdrawal, Substitution, and Modification of Bids	62

27.	Bid Opening	63

E.	Evaluation and Comparison of Bids	65

28.	Confidentiality	65

29.	Clarification of Bids	65

30.	Deviations, Reservations, and Omissions	66

31.	Preliminary Examination of Technical Bids	66

32.	Responsiveness of Technical Bids	66

33.	Nonmaterial Nonconformities	67

34.	Detailed Evaluation of Technical Bids	67

35.	Eligibility and Qualification of the Bidder	68

36.	Correction of Arithmetical Errors	69

37.	Conversion to Single Currency	69

38.	Evaluation and Comparison of Price Bids	69

39.	Employer’s Right to Accept Any Bid, and to Reject Any or All Bids	71

F.	Award of Contract	71

40.	Award Criteria	71

41.	Standstill Period	71

42.	Notification of Intention to Award	71

43.	Notification of Award	71

44.	Debriefing by the Employer	72

45.	Signing of Contract	73

46.	Performance Security	73

47.	Procurement- related Complaint	73

| - General |  |
| --- | --- |
| - Scope of Bid | - In connection with the Invitation for Bids indicated in the Bid Data Sheet (BDS), the Employer, as indicated in the BDS, issues this Bidding Document for the Design, Supply and Installation of Plant as specified in Section VI (Employer’s Requirements). The name, identification, and number of lots (contracts) of the Competitive bidding (CB) are provided in the BDS. |
|  | - Throughout this Bidding Document, - the term “in writing” means communicated in written form and delivered against receipt; - except where the context requires otherwise, words indicating the singular also include the plural and words indicating the plural also include the singular; and - “day” means calendar day. |
| - Source of Funds | - The Borrower or Recipient (hereinafter called “Borrower”) indicated in the BDS has applied for or received financing (hereinafter called “funds”) from the Export-Import Bank of Korea (hereinafter called the “Bank”) toward the cost of the project named in the BDS. The Borrower intends to apply a portion of the funds to eligible payments under the contract(s) for which this Bidding Document is issued. |
|  | - Payments by the Bank will be made only at the request of the Borrower and upon approval by the Bank in accordance with the terms and conditions of Loan Agreement between the Borrower and Bank (hereinafter called “the Loan Agreement”), and will be subject in all respects to the terms and conditions of that Loan Agreement. No party other than the Borrower shall derive any rights from the Loan Agreement or have any claim to the funds. The Loan Agreement prohibits a withdrawal from the loan account for the purpose of any payment to persons or entities, or for any import of goods, if such payment or import, to the knowledge of the Bank, is prohibited by decision of the Bank. No party other than the Borrower shall derive any rights from the Loan Agreement or have any claim to the funds. |
| Fraud and Corruption | - It is the Bank’s policy to require that Borrowers (including beneficiaries of EDCF Loans), as well as bidders, suppliers, and contractors under contracts financed by EDCF Loans, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the Bank; - defines, for the purposes of this provision, the terms set forth below as follows: - “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence the action of a public official in the procurement process or in contract execution. - “fraudulent practice” means a misrepresentation or omission of facts in order to influence a procurement process or the execution of a contract. - shall reject a proposal for award and declare a firm ineligible to enter into the contract in question if it determines that the Bidder recommended for award has engaged in corrupt or fraudulent practices or any other integrity violations in competing for the contract; - shall declare a firm ineligible, for a period determined by the Bank, to participate in any bid for, to be awarded, and to enter into a contract related to the project in question if it at any time determines that the firm has engaged in corrupt, fraudulent practices or any other integrity violations in competing for, or in executing, a contract financed by an EDCF Loan; - notwithstanding the sub-paragraph (b) and (c), shall declare a firm ineligible, even after the end of a period determined by the Bank, to participate in any bid for, to be awarded, and to enter into a contract related to the project in question if it at any time determines that the firm has engaged in corrupt, fraudulent practices or any other integrity violations in competing for, or in executing, the contract of the project; - shall recognize a firm as ineligible to participate in any bid for, to be awarded, and to enter into a contract financed by an EDCF loan if the firm is debarred under the cross debarment decision by Multilateral Development Banks. Such period of ineligibility shall not exceed two (2) years from (and including) the date on which the cross debarment is imposed. With regard to the participation in the bid, the base date of determination on the debarment status is the date of the deadline for submission of bids; - shall recognize a firm as ineligible to participate in any bid for, to be awarded, and to enter into a contract financed by an EDCF loan if such firm constitutes any of the inappropriate business entities defined in the ‘Act on Contracts to which the State is a Party’, ‘Act on Contracts to Which a Local Government is a Party’, and ‘Act on the Management of Public Institutions’ of the Republic of Korea. Such period of ineligibility shall be equated to the sanction period decided by the Korean government and public institutions. With regard to the participation in the bid, the base date of determination on the sanction status is the date of the deadline for submission of bids; |
|  | - All Bidders, consultants, contractors, suppliers, and other third parties engaged or involved in Bank-related activities have a duty to cooperate fully in any screening or investigation when requested by Bank to do so. Such cooperation includes, but is not limited to, the following: - being available to be interviewed and replying fully and truthfully to all questions asked; - providing Bank with any items requested that are within the party’s control including, but not limited to, documents and other physical objects; - upon written request by Bank, authorizing other related entities to release directly to Bank such information that is specifically and materially related, directly or indirectly, to the said entities or issues which are the subject of the investigation; - cooperating with all reasonable requests to search or physically inspect their person and/or work areas, including files, electronic databases, and personal property used on Bank activities, or that utilizes Bank’s Information and Communications Technology (ICT) resources or systems (including mobile phones, personal electronic devices, and electronic storage devices such as external disk drives); - cooperating in any testing requested by Bank, including but not limited to, fingerprint identification, handwriting analysis, and physical examination and analysis; and - preserving and protecting confidentiality of all information discussed with, and as required by, the Bank. - All Bidders, consultants, contractors and suppliers shall ensure that, in its contract with its sub-consultants, subcontractors, and other third parties engaged or involved in Bank-related activities, such sub-consultants, subcontractors, and other third parties similarly undertake the foregoing duty to cooperate fully in any screening or investigation when requested by the Bank to do so. - Bidders (including all parties/partners and the Representative in case of JVA) shall submit the original signed form (with certificate of corporate seal registration in Korean and certificate of business registration in English) of the “Declaration of participation in Economic Development Cooperation Fund (EDCF) financed projects” as attached in the last page of Section IV (Bidding Forms Following/Without Prequalification) to the Bank (see the address specified in the BDS) by mail or in person at or before the Deadline for bid submission in the BDS and submit a copy of the original signed form to the Employer along with the Bid upon the submission of the Bid. Bidders who fail to submit the original signed form to the Bank or to include the copy of it in the Bid, as set forth above, shall not be substantially responsive subject to ITB Clause 32. In case of discrepancy between English version and its Korean translation of the “Declaration of Participation in Economic Development Cooperation Fund (EDCF) financed projects”, the English version shall prevail. - Furthermore, Bidders shall be aware of the provision stated in GC 9.6 and GC 42.2.1 (c) of the General Conditions. |
| Eligible Bidders | - A Bidder may be a natural person, private entity, or government-owned entity subject to ITB 4.5 - or any combination of such entities in the form of a joint venture or association/consortium (JVA) under an existing agreement or with the intent to enter into such an agreement supported by a letter of intent. In the case of a JVA: - all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms, and - the JVA shall nominate a Representative who shall have the authority to conduct all business for and on behalf of any and all the partners of the JVA during the bidding process and, in the event the JVA is awarded the Contract, during contract execution. |
|  | - A Bidder, and all parties constituting the Bidder, shall have the nationality of an eligible country as defined under the Guidelines; Guidelines for Procurement under the EDCF Loan (hereinafter referred to as the Guidelines), subject to the restrictions specified in Section V (Eligible Countries). A Bidder shall be deemed to have the nationality of a country if the Bidder is a citizen or is constituted, incorporated, or registered, and operates in conformity with the provisions of the laws of that country. This criterion shall also apply to the determination of the nationality of proposed subcontractors or suppliers for any part of the Contract, including related services. |
|  | - A Bidder shall not have a conflict of interest. All Bidders found to have a conflict of interest shall be disqualified. A Bidder may be considered to have a conflict of interest with one or more parties in this bidding process if: - they have controlling partners in common; - they receive or have received any direct or indirect subsidy from any of them; - they have the same legal representative for purposes of this bid; - they have a relationship with each other, directly or through common third parties, that puts them in a position to have access to material information about or improperly influence the bid of another Bidder, or influence the decisions of the Employer regarding this bidding process; - a Bidder participates in more than one bid in this bidding process, either individually or as a partner in a Joint Venture, except for alternative offers permitted under ITB 13. This will result in the disqualification of all Bids in which the party is involved. However, this does not limit the inclusion of the same subcontractor in more than one Bid; - a Bidder, JVA partner, associates, parent company or any affiliated entity, participated as a consultant in the preparation of the feasibility study, basic/detailed design or technical specifications, and other documents to be used for the procurement of the Plant and Installation Services that are the subject of the Bid; - a Bidder was affiliated with a firm or entity that has been hired (or is proposed to be hired) by the Employer or Borrower as Project Manager for the Contract; or - a Bidder would be providing goods, works, or non-consulting services resulting from or directly related to consulting services for the preparation or implementation of the project specified in the BDS ITB 2.1 that it provided or were provided by any affiliate that directly or indirectly controls, is controlled by, or is under common control with that firm. |
|  | - A firm that has been determined to be ineligible by the Bank in relation to the Bank Guidelines on preventing and combating Fraud and Corruption (see ITB 3) in Projects Financed by EDCF shall not be eligible to participate in any bid for, to be awarded, and to enter into a contract. - Government-owned entities in the Borrower’s country shall be eligible only if they can establish that they (i) are legally and financially autonomous, (ii) operate under commercial law, and (iii) are not dependent agencies of the Employer. - A Bidder shall not be under suspension from bidding by the Employer as the result of the execution of a Bid-Securing Declaration. |
|  | - Bidders shall provide such evidence of their continued eligibility satisfactory to the Employer, as the Employer shall reasonably request. |
|  | - In case a Prequalification process has been conducted prior to the bidding process, this bidding is open only to prequalified Bidders. |
| Eligible Plant and Installation Services | - The Plant and Installation Services to be supplied under the Contract and financed by the Bank may have their origin in any country in accordance with Section V (Eligible Countries). |
|  | - For purposes of ITB 5.1 above, “origin” means the place where the plant, or component parts thereof are mined, grown, produced, or manufactured, and from which the services are provided. Plant components are produced when, through manufacturing, processing, or substantial or major assembling of components, a commercially recognized product results that is substantially in its basic characteristics or in purpose or utility from its components. |
| Contents of Bidding Document |  |
| Sections of Bidding Document | - The Bidding Document consists of Parts 1, 2, and 3, which include all the sections indicated below, and should be read in conjunction with any Addenda issued in accordance with ITB 8. PART 1 Bidding Procedures Section I - Instructions to Bidders (ITB) Section II - Bid Data Sheet (BDS) Section III - Evaluation and Qualification Criteria Section IV - Bidding Forms Section V - Eligible Countries PART 2 Employer’s Requirements Section VI - Employer’s Requirements PART 3 Conditions of Contract and Contract Forms Section VII - General Conditions (GC) Section VIII - Particular Conditions (PC) Section IX - Contract Forms |
|  | - The Invitation for Bids (IFB) issued by the Employer is not part of the Bidding Document. |
|  | - The Employer is not responsible for the completeness of the Bidding Document and their addenda, if they were not obtained directly from the source stated by the Employer in the Invitation for Bids. |
|  | - The Bidder is expected to examine all instructions, forms, terms, and specifications in the Bidding Document. Failure to furnish all information or documentation required by the Bidding Document may result in the rejection of the Bid. |
| Clarification of Bidding Document, Site Visit, Pre-Bid Meeting | - A prospective Bidder requiring any clarification on the Bidding Document shall contact the Employer in writing at the Employer’s address indicated in the BDS, or raise his enquiries during the pre-bid meeting if provided for in accordance with ITB 7.4. The Employer will respond to any request for clarification, provided that such request is received no later than twenty-one (21) days prior to the deadline for submission of bids. The Employer’s response shall be in writing with copies to all Bidders who have acquired the Bidding Document in accordance with ITB 6.3, including a description of the inquiry but without identifying its source. Should the Employer deem it necessary to amend the Bidding Document as a result of a request for clarification, it shall do so following the procedure under ITB 8 and ITB 24.2. |
|  | - The Bidder is advised to visit and examine the Site where the plant is to be installed and its surroundings and obtain for itself on its own responsibility all information that may be necessary for preparing the Bid and entering into a contract for the provision of plant and services. The costs of visiting the site shall be at the Bidder’s own expense. |
|  | - The Bidder and any of its personnel or agents will be granted permission by the Employer to enter its premises and lands for the purpose of such visit, but only upon the express condition that the Bidder, its personnel, and agents, will release and indemnify the Employer and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection. |
|  | - The Bidder’s designated representative is invited to attend a pre-bid meeting, if provided for in the BDS. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage. |
|  | - The Bidder is requested, as far as possible, to submit any questions in writing, to reach the Employer not later than one week before the meeting. |
|  | - Minutes of the pre-bid meeting, including the text of the questions raised, without identifying the source, and the responses given, together with any responses prepared after the meeting, will be transmitted promptly to all Bidders who have acquired the Bidding Document in accordance with ITB 6.3. Any modification to the Bidding Document that may become necessary as a result of the pre-bid meeting shall be made by the Employer exclusively through the issue of an addendum pursuant to ITB 8 and not through the minutes of the pre-bid meeting. |
|  | - Nonattendance at the pre-bid meeting will not be a cause for disqualification of a Bidder. |
| Amendment of Bidding Document | - At any time prior to the deadline for submission of Bids, the Employer may amend the Bidding Document by issuing addenda. |
|  | - Any addendum issued shall be part of the Bidding Document and shall be communicated in writing to all who have obtained the Bidding Document from the Employer in accordance with ITB 6.3. The Bidders are required to immediately acknowledge receipt of any such amendment, and it will be assumed that the information contained therein will have been taken into account by the Bidder in its bid. |
|  | - To give prospective Bidders reasonable time in which to take an addendum into account in preparing their Bids, the Employer may, at its discretion, extend the deadline for the submission of Bids, pursuant to ITB 24.2. |
| Preparation of Bids |  |
| Cost of Bidding | - The Bidder shall bear all costs associated with the preparation and submission of its Bid, and the Employer shall in no case be responsible or liable for those costs, regardless of the conduct or outcome of the bidding process. |
| Language of Bid | - The Bid, as well as all correspondence and documents relating to the bid exchanged by the Bidder and the Employer, shall be written in the English. Supporting documents and printed literature that are part of the Bid may be in another language provided they are accompanied by an accurate translation of the relevant passages into English, in which case, for purposes of interpretation of the Bid, such translation shall govern. |
| Documents Comprising the Bid | - The Bid shall comprise two envelopes submitted simultaneously, one containing the Technical Bid and the other the Price Bid, both envelopes enclosed together in an outer single envelope. - The Technical Bid submitted by the Bidder shall comprise the following: - Letter of Technical Bid; - Bid Security or Bid-Securing Declaration, in accordance with ITB 21; - alternative Bids, if permissible, in accordance with ITB 13; - written confirmation authorizing the signatory of the Bid to commit the Bidder, in accordance with ITB 22.2; - documentary evidence in accordance with ITB 14.1, that the Plant and Installation Services offered by the Bidder in its Bid or in any alternative Bid, if permitted, are eligible; - documentary evidence in accordance with ITB 15, establishing the Bidder’s eligibility and qualifications to perform the contract if its Bid is accepted; - Technical Proposal in accordance with ITB 17; - documentary evidence in accordance with ITB 16, that the Plant and Installation Services offered by the Bidder conform to the Bidding Document; - In the case of a bid submitted by a JVA, the Bid shall include a copy of the JVA Agreement entered into by all partners. Alternatively, a Letter of Intent to execute a JVA Agreement in the event of a successful Bid shall be signed by all partners and submitted with the Bid, together with a copy of the proposed agreement; - list of subcontractors, in accordance with ITB 17.2; and - any other document required in the BDS. - The Price Bid submitted by the Bidder shall comprise the following: - Letter of Price Bid; - completed schedules as required, including Price Schedules, in accordance with ITB 12 and ITB 18; - alternative price Bids, at Bidder’s option and if permissible, in accordance with ITB 13; and - any other document required in the BDS. |
| Letter of Bid and Schedules | - The Letter of Technical Bid and Price Bid, and Schedules, and all documents listed ITB 11, shall be prepared using the relevant forms furnished in Section IV (Bidding Forms). The forms must be completed without any alterations to the test, and no substitutes shall be accepted. All blank spaces shall be filled in with the information requested. |
| Alternative Bids | - Unless otherwise indicated in the BDS, alternative bids shall not be considered. |
|  | - When alternative times for completion are explicitly invited, a statement to that effect will be included in the BDS, as will be the method of evaluating different times for completion. |
|  | - Except as provided under ITB 13.4 below, Bidders wishing to offer technical alternatives to the Employer’s requirements as described in the Bidding Document must also provide: (i) a price at which they are prepared to offer a Plant meeting the Employer’s requirements; and (ii) all information necessary for a complete evaluation of the alternatives by the Employer, including drawings, design calculations, technical specifications, breakdown of prices, and proposed installation methodology and other relevant details. Only the technical alternatives, if any, of the lowest evaluated Bidder conforming to the basic technical requirements shall be considered by the Employer. |
|  | - When specified in the BDS, Bidders are permitted to submit alternative technical solutions for specified parts of the facilities, and such parts will be identified in the BDS, as will the method for their evaluation, and described in Section VI (Employer’s Requirements). |
| Documents Establishing the Eligibility of Plant and Installation Services | - To establish the eligibility of the Plant and Installation Services in accordance with ITB 5, Bidders shall complete the country of origin declarations in the Price Schedule Forms, included in Section IV (Bidding Forms). |
| Documents Establishing the Eligibility and Qualifications of the Bidder | - In accordance with Section III (Evaluation and Qualification Criteria) to establish that the Bidder continues to meet criteria used at the time of Prequalification, the Bidder shall provide in the corresponding information sheets included in Section IV (Bidding Forms), updated information on any assessed aspect that changed from that time, or if post-qualification applies, the Bidder shall provide the information requested in the corresponding information sheets included in Section IV (Bidding Forms). |
| Documents Establishing Conformity of the Plant and Installation Services | - The documentary evidence of the conformity of the Plant and Installation Services to the Bidding Document may be in the form of literature, drawings, and data and shall furnish: (a) a detailed description of the essential technical and performance characteristics of the Plant and Installation Services, including the functional guarantees of the proposed Plant and Installation Services, in response to the specification; (b) a list giving full particulars, including available sources, of all spare parts and special tools necessary for the proper and continuing functioning of the plant for the period indicated in the BDS, following completion of Plant and Installation Services in accordance with provisions of the contract; and (c) a commentary on the Employer’s Specifications and adequate evidence demonstrating the substantial responsiveness of the Plant and Installation Services to those specifications. Bidders shall note that standards for workmanship, materials, and equipment designated by the Employer in the Bidding Document are intended to be descriptive (establishing standards of quality and performance) only and not restrictive. The Bidder may substitute alternative standards, brand names, and/or catalog numbers in its Bid, provided that it demonstrates to the Employer’s satisfaction that the substitutions are substantially equivalent or superior to the standards designated in the Specifications. |
| Technical Proposal, Subcontractors | - The Bidder shall furnish a Technical Proposal including a statement of work methods, equipment, personnel, schedule, safety plan, and any other information as stipulated in Section IV (Bidding Forms), in sufficient detail to demonstrate the adequacy of the Bidders’ proposal to meet the work requirements and the completion time. - For major items of Plant and Installation Services as listed by the Employer in Section III (Evaluation and Qualification Criteria), which the Bidder intends to purchase or subcontract, the Bidder shall give details of the name and nationality of the proposed Subcontractors, including Manufacturers, for each of those items. In addition, the Bidder shall include in its Bid information establishing compliance with the requirements specified by the Employer for these items. Bidders are free to list more than one Subcontractor against each item of the plant and services. Quoted rates and prices will be deemed to apply to whichever Subcontractor is appointed, and no adjustment of the rates and prices will be permitted. - The Bidder shall be responsible for ensuring that any Subcontractor proposed complies with the requirements of ITB 4, and that any plant or services to be provided by the Subcontractor comply with the requirements of ITB 5 and ITB 16.1. |
| Bid Prices and Discounts | - Unless otherwise specified in the BDS and/or Section VI (Employer’s Requirements), Bidders shall quote for the entire Plant and Installation Services on a “single responsibility” basis such that the total Bid price covers all the Contractor’s obligations mentioned in or to be reasonably inferred from the Bidding Document in respect of the design, manufacture, including procurement and subcontracting (if any), delivery, construction, installation, and completion of the plant. This includes all requirements under the Contractor’s responsibilities for testing, pre-commissioning and commissioning of the plant and, where so required by the Bidding Document, the acquisition of all permits, approvals, and licenses, etc.; the operation, maintenance, and training services and such other items and services as may be specified in the Bidding Document, all in accordance with the requirements of the General Conditions. Items against which no price is entered by the Bidder will not be paid for by the Employer when executed and shall be deemed to be covered by the prices for other items. - Bidders are required to quote the price for the commercial, contractual, and technical obligations outlined in the Bidding Document. |
|  | - Bidders shall give a breakdown of the prices in the manner and detail called for in the Price Schedules included in Section IV (Bidding Forms). Where no different Price Schedules are included in the Bidding Document, Bidders shall present their prices in the following manner: Separate numbered Schedules included in Section IV (Bidding Forms) shall be used for each of the following elements. The total amount from each Schedule (Nos. 1 to 4) shall be summarized in a Grand Summary (Schedule No. 5) giving the total bid price(s) to be entered in the Letter of Price Bid. Absence of the total bid price in the Letter of Price Bid may result in the rejection of the Bid. Schedule No. 1: Plant and Mandatory Spare Parts Supplied from Abroad Schedule No. 2: Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country Schedule No. 3: Design Services Schedule No. 4: Installation and Other Services Schedule No. 5 Grand Summary (Schedule Nos. 1 to 4) Schedule No. 6: Recommended Spare Parts Bidders shall note that the plant and mandatory spare parts included in Schedule Nos. 1 and 2 above exclude materials used for civil, building, and other construction works. All such materials shall be included and priced under Schedule No. 4, Installation and Other Services. |
|  | - In the Schedules, Bidders shall give the required details and a breakdown of their prices as follows: - Plant to be Supplied from Abroad (Schedule No. 1): - the price of the plant shall be quoted carriage and insurance paid (CIP)-named place of destination basis specified in the BDS; - all customs duties and other taxes paid or payable in the Employer’s country on the plant if the contract is awarded to the Bidder; and - the total price for the plant. - Plant Supplied from Within the Employer’s Country (Schedule No. 2): - the price of the plant shall be quoted on an EXW Incoterm basis (ex works, ex factory, ex warehouse, ex showroom, as applicable), including all customs duties and sales and other taxes already paid or payable on the components and raw material used in the manufacture or assembly of plant quoted ex works or ex factory, or on the previously imported plant of foreign origin quoted ex warehouse, ex showroom; - sales tax and other taxes payable in the Employer’s country on the plant if the contract is awarded to the Bidder, and - the total price for the plant. - Design Services. (Schedule No. 3). Rates or prices shall include all taxes, duties, levies, and charges payable in the Employerʼs country as of twenty-eight (28) days prior to the deadline for submission of Bids. - Installation and Other Services (Schedule No. 4) shall be quoted separately and shall include rates or prices for local transportation to named place of final destination as specified in the BDS, insurance, and other services incidental to delivery of the plant, all labor, contractor’s equipment, temporary works, materials, consumables, and all matters and things of whatsoever nature, including operations and maintenance services, the provision of operations and maintenance manuals, training, etc., where identified in the Bidding Document, as necessary for the proper execution of the installation and other services, including all taxes, duties, levies, and charges payable in the Employer’s country as of 28 days prior to the deadline for submission of bids. - Recommended spare parts (Schedule No. 6) shall be quoted separately as specified in either subparagraph (a) or (b) above in accordance with the origin of the spare parts. |
|  | - The current edition of Incoterms, published by the International Chamber of Commerce shall govern. |
|  | - The prices shall be either fixed or adjustable as specified in the BDS. (a) In the case of Fixed Price, prices quoted by the Bidder shall be fixed during the Bidder’s performance of the contract and not subject to variation on any account. A Bid submitted with an adjustable price quotation will be treated as nonresponsive and rejected. (b) In the case of Adjustable Price, prices quoted by the Bidder shall be subject to adjustment during performance of the contract to reflect changes in the cost elements such as labor, material, transport and contractor’s equipment in accordance with the procedures specified in the corresponding appendix to the Contract Agreement. A Bid submitted with a fixed price quotation will not be rejected, but the price adjustment will be treated as zero. Bidders are required to indicate the source of labor and material indices in the corresponding Form in Section IV (Bidding Forms). - If so indicated in BDS 1.1, Bids are being invited for individual lots (contracts) or for any combination of lots (packages). Bidders wishing to offer any price reduction (discount) for the award of more than one contract shall specify in their Letter of Bid the price reductions applicable to each package, or alternatively, to individual contracts within the package, and the manner in which the price reductions will apply. - Bidders wishing to offer any unconditional discount shall specify in their Letter of Price Bid the offered discounts and the manner in which price discounts will apply. |
| Currencies of Bid and Payment | - The bidder shall quote the bid price in the currency specified in the BDS. - Bidders may be required by the Employer to justify, to the Employer’s satisfaction, their local and foreign currency requirements, and to substantiate that the amounts included in the unit rates and prices and shown in the Schedule of Adjustment Data in the Appendix to Bid are reasonable, in which case a detailed breakdown of the foreign currency requirements shall be provided by Bidders. - Notwithstanding ITB 19.1 above, a portion of the contract price may be stated in US Dollars within the amount of the Loan to be disbursed in US Dollars under the Provisions of the Loan Agreement. |
| Period of Validity of Bids | - Bids shall remain valid for the period specified in the BDS after the bid submission deadline date prescribed by the Employer. A bid valid for a shorter period shall be rejected by the Employer as nonresponsive. |
|  | - In exceptional circumstances, prior to the expiration of the bid validity period, the Employer may request Bidders to extend the period of validity of their Bids. The request and the responses shall be made in writing. If a bid security is requested in accordance with ITB 21, it shall also be extended twenty-eight (28) days beyond the deadline of the extended bid validity period. A Bidder may refuse the request without forfeiting its bid security. A Bidder granting the request shall not be required or permitted to modify its Bid, except as provided in ITB 20.3. - If the award is delayed by a period exceeding fifty-six (56) days beyond the expiry of the initial Bid validity specified in accordance with ITB 20.1, the Contract price shall be determined as follows: - in the case of fixed price contracts, the Contract price shall be the Bid price adjusted by the factor or factors specified in the BDS; - in the case of adjustable price contracts, to determine the Contract Price, the fixed portion of the Bid Price shall be adjusted by the factor specified in the BDS; or - in any case, Bid evaluation shall be based on the Bid price without taking into consideration the applicable correction from those indicated above. |
| Bid Security/Bid Securing Declaration | - The Bidder shall furnish as part of its bid, either a bid-securing declaration or a bid security as specified in the BDS, in original form. In the case of a bid security, the amount and currency specified in the BDS. - A Bid-Securing Declaration shall use the form included in Section IV (Bidding Forms). |
|  | - If a bid security is specified pursuant to ITB 21.1, the bid security shall be a demand guarantee in any of the following forms at the Bidder’s option: - an unconditional bank guarantee issued by a bank or surety; - an irrevocable letter of credit; - a cashier’s or certified check; or - another security indicated in the BDS, from a reputable source from an eligible country. In the case of a bank guarantee, the bid security shall be submitted using either the Bid Security Form included in Section IV (Bidding Forms) or another form acceptable to the Employer. The form must include the complete name of the Bidder. The bid security shall be valid for twenty-eight (28) days beyond the original validity period of the Bid, or beyond any period of extension if requested under ITB 20.2. |
|  | - If a bid security is specified pursuant to ITB 21.1, any bid not accompanied by a substantially responsive bid security or Bid-Securing Declaration shall be rejected by the Employer as nonresponsive. |
|  | - If a bid security is specified pursuant to ITB 21.1, the bid security of unsuccessful Bidders shall be returned as promptly as possible upon the successful Bidder’s furnishing of the performance security pursuant to ITB 46. |
|  | - The bid security of the successful Bidder shall be returned as promptly as possible once the successful Bidder has signed the Contract and furnished the required performance security. |
|  | - The bid security may be forfeited or the Bid-Securing Declaration executed: - If a Bidder withdraws its bid during the period of bid validity specified by the Bidder on the Letter of Bid Form, except as provided in ITB 20.2; or - If the successful Bidder fails to: - sign the Contract in accordance with ITB 45; or - furnish a performance security in accordance with ITB 46. |
|  | - The Bid Security or the Bid-Securing Declaration of a JVA shall be in the name of the JVA that submits the Bid. If the JVA has not been legally constituted into a legally enforceable JVA at the time of bidding, the Bid Security or the Bid Securing Declaration shall be in the names of all future members as named in the letter of intent referred to in ITB 4.1 and ITB 11.2. - If a Bid Security is not required in the BDS: and - If a Bidder withdraws its bid prior to the expiry date of the Bid validity specified by the Bidder on the Letter of Technical Bid and on the Letter of Price Bid, or any extended date provided by the Bidder; or - If the successful Bidder fails to: - sign the Contract in accordance with ITB 45; or - furnish a performance security in accordance with ITB 46, the Borrower may, if provided for in the BDS, declare the Bidder disqualified to be awarded a contract by the Employer for a period of time as stated in the BDS. |
| Format and Signing of Bid | - The Bidder shall prepare one original of the Technical Bid and one original of the Price Bid comprising the Bid as described in ITB 11 and clearly mark it “ORIGINAL – TECHNICAL BID” and “ORIGINAL – PRICE BID.” Alternative bids, if permitted in accordance with ITB 13, shall be clearly marked “ALTERNATIVE.” In addition, the Bidder shall submit copies of the Technical and Price Bids, in the number specified in the BDS, and clearly mark each of them “COPY.” In the event of any discrepancy between the original and the copies, the original shall prevail. |
|  | - The original and all copies of the Bid shall be typed or written in indelible ink and shall be signed by a person duly authorized to sign on behalf of the Bidder. This authorization shall consist of a written confirmation as specified in the BDS and shall be attached to the Bid. The name and position held by each person signing the authorization must be typed or printed below the signature. All pages of the Bid, except for un-amended printed literature, where entries or amendments have been made shall be signed or initialed by the person signing the Bid. |
|  | - A Bid submitted by a JVA shall be comply with the following requirement: - Unless not required in accordance with ITB 4.1, be signed so as to be legally binding on all partners; and - Include the Representative’s authorization referred to in ITB 4.1(b), consisting of a power of attorney signed by those legally authorized to sign on behalf of the JVA. |
|  | - Any amendments such as interlineations, erasures, or overwriting shall be valid only if they are signed or initialed by the person signing the Bid. |
| Submission and Opening of Bids |  |
| Submission, Sealing and Marking of Bids | - The Bidder may submit their Bids by mail or by hand. When so specified in the BDS, Bidders shall have the option of submitting their Bids electronically. Procedures for submission, sealing and marking are as follows: - Bidders submitting Bids by mail or by hand shall enclose the original and each copy of the Bid, including alternative Bids, if permitted in accordance with ITB 13, in separate sealed envelopes, duly marking the envelopes as “ORIGINAL - TECHNICAL BID,” “ORIGINAL - PRICE BID” and “COPY NO… - TECHNICAL PROPOSAL” and “COPY NO… - PRICE PROPOSAL.” These envelopes containing the original and the copies shall then be enclosed in one single envelope. The rest of the procedure shall be in accordance with ITB 23.2 to ITB 23.6. - Bidders submitting Bids electronically shall follow the electronic bid submission procedures specified in the BDS. |
|  | - The inner and outer envelopes shall: - bear the name and address of the Bidder; - be addressed to the Employer in accordance with ITB 24.1; and - bear the specific identification of this bidding process indicated in the BDS 1.1. |
|  | - The outer envelopes and the inner envelopes containing the Technical Bid shall bear a warning not to open before the time and date for the opening of Technical Bid, in accordance with ITB 27.1. - The inner envelopes containing the Price Bid shall bear a warning not to open until advised by the Employer in accordance with ITB 27.7. - Alternative Bids, if permissible in accordance with ITB 13, shall be prepared, sealed, marked, and delivered in accordance with the provisions of ITB 22 and ITB 23, with the inner envelopes marked in addition “ALTERNATIVE NO….” as appropriate. - If all envelopes are not sealed and marked as required, the Employer will assume no responsibility for the misplacement or premature opening of the bid. |
| Deadline for Submission of Bids | - Bids must be received by the Employer at the address and no later than the date and time indicated in the BDS. |
|  | - The Employer may, at its discretion, extend the deadline for the submission of bids by amending the Bidding Document in accordance with ITB 8, in which case all rights and obligations of the Employer and Bidders previously subject to the deadline shall thereafter be subject to the deadline as extended. |
| Late Bids | - The Employer shall not consider any Bid that arrives after the deadline for submission of Bids, in accordance with ITB 24. Any Bid received by the Employer after the deadline for submission of Bids shall be declared late, rejected, and returned unopened to the Bidder. |
| Withdrawal, Substitution, and Modification of Bids | - A Bidder may withdraw, substitute, or modify its Bid after it has been submitted by sending a written notice, duly signed by an authorized representative, and shall include a copy of the authorization in accordance with ITB 22.2 (except for withdrawal notices, which do not require copies). The corresponding substitution or modification of the Bid must accompany the respective written notice. All notices must be: - prepared and submitted in accordance with ITB 22 and ITB 23 (except for withdrawal notices, which do not require copies), and in addition, the respective envelopes shall be clearly marked “WITHDRAWAL,” “SUBSTITUTION,” “MODIFICATION;” and - received by the Employer prior to the deadline prescribed for submission of Bids, in accordance with ITB 24. |
|  | - Bids requested to be withdrawn in accordance with ITB 26.1 shall be returned unopened to the Bidders. |
|  | - No Bid may be withdrawn, substituted, or modified in the interval between the deadline for submission of Bids and the expiration of the period of bid validity specified by the Bidder on the Letter of Technical Bid and on the Letter of Price Bid or any extension thereof. |
| Bid Opening | - The Employer shall open the Technical Bids in public at the address, on the date, and time specified in the BDS in the presence of Bidder’s designated representatives and anyone who choose to attend. Any specific electronic bid opening procedures required if electronic bidding is permitted in accordance with ITB 23.1, shall be as specified in the BDS. The Price Bids will remain unopened and will be held in custody of the Employer until the specified time of their opening. |
|  | - First, envelopes marked “WITHDRAWAL” shall be opened and read out and the envelope with the corresponding bid shall not be opened, but returned to the Bidder. No bid withdrawal shall be permitted unless the corresponding withdrawal notice contains a valid authorization to request the withdrawal and is read out at bid opening. - Second, outer envelopes marked “SUBSTITUTION” shall be opened. The inner envelopes containing the Substitution Technical Bid and/or Substitution Price Bid shall be exchanged for the corresponding envelopes being substituted, which are to be returned to the Bidder unopened. Only the Substitution Technical Bid, if any, shall be opened, read out, and recorded. Substitution Price Bid will remain unopened in accordance with ITB 27.1. No envelope shall be substituted unless the corresponding Substitution Notice contains a valid authorization to request the substitution and is read out and recorded at bid opening. - Next, outer envelopes marked “MODIFICATION” shall be opened. No Technical Bid and/or Price Bid shall be modified unless the corresponding Modification Notice contains a valid authorization to request the modification and is read out and recorded at the opening of Technical Bids. Only the Technical Bids, both Original as well as Modification, are to be opened, read out, and recorded at the opening. Price Bids, both Original as well as Modification, will remain unopened in accordance with ITB 27.1. |
|  | - All other envelopes holding the Technical Bids shall be opened one at a time, and the following read out and recorded: (a) the name of the Bidder; (b) whether there is a modification or substitution; (c) the presence of a bid security or a Bid-Securing Declaration, if required; and (d) any other details as the Employer may consider appropriate. Only Technical Bids and alternative Technical Bids read out and recorded at bid opening shall be considered for evaluation. Unless otherwise specified in the BDS, all pages of the Letter of Technical Bid are to be initialed by at least three representatives of the Employer attending the bid opening. No bid shall be rejected at the opening of Technical Bids except for late bids, in accordance with ITB 25.1. - The Employer shall prepare a record of the opening of Technical Bids that shall include, as a minimum: the name of the Bidder and whether there is a withdrawal, substitution, or modification; and alternative Bids; and the presence or absence of a bid security or a Bid-Securing Declaration, if one was required. The Bidders’ representatives who are present shall be requested to sign the record. The omission of a Bidder’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall be distributed to all Bidders who submitted Bids on time, and posted online when electronic bidding is permitted. |
|  | - At the end of the evaluation of the Technical Bids, the Employer will invite bidders who have submitted substantially responsive Technical Bids and who have been determined as being qualified for award to attend the opening of the Price Bids. The date, time, and location of the opening of Price Bids will be advised in writing by the Employer. Bidders shall be given reasonable notice of the opening of Price Bids. - The Employer will notify Bidders in writing who have been rejected on the grounds of their Technical Bids being substantially nonresponsive to the requirements of the Bidding Document and return their Price Bids unopened. - The Employer shall conduct the opening of Price Bids of all Bidders who submitted substantially responsive Technical Bids, in the presence of Bidders` representatives who choose to attend at the address, date and time specified by the Employer. The Bidder’s representatives who are present shall be requested to sign a register evidencing their attendance. - All envelopes containing Price Bids shall be opened one at a time and the following read out and recorded; (a) The name of the Bidder; (b) whether there is a modification or substitution; (c) the Bid Prices, including any discounts and alternative offers; and (d) any other details as the Employer may consider appropriate. Only Price Bids discounts, and alternative offers read out and recorded during the opening of Price Bids shall be considered for evaluation. Unless otherwise specified in the BDS, all pages of the Letter of Price Bid and Price Schedules are to be initialed by at least three representatives of the Employer attending the bid opening. No Bid shall be rejected at the opening of the Price Bids. - The Employer shall prepare a record of the opening of Price Bids that shall include, as a minimum: the name of the Bidder, the Bid Price (per lot if applicable), any discounts, and alternative offers. The Bidders’ representatives who are present shall be requested to sign the record. The omission of a Bidder’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall be distributed to all Bidders who submitted Bids on time, and posted online when electronic bidding is permitted. |
| Evaluation and Comparison of Bids |  |
| Confidentiality | - Information relating to the examination, clarification, and evaluation of bids and proposals concerning awards shall not be disclosed to Bidders or any other persons not officially concerned with such process until the information on Contract award is communicated to all Bidders in accordance with ITB 43. |
|  | - Any attempt by a Bidder to influence the Employer in the evaluation of the Bids or Contract award decisions may result in the rejection of its Bid. |
|  | - Notwithstanding ITB 28.2, from the time of bid opening to the time of Contract award, if any Bidder wishes to contact the Employer on any matter related to the bidding process, it should do so in writing. |
| Clarification of Bids | - To assist in the examination, evaluation, and comparison of the Technical and Price Bids, and qualification of the Bidders, the Employer may, at its discretion, ask any Bidder for a clarification of its Bid. Any clarification submitted by a Bidder that is not in response to a request by the Employer shall not be considered. The Employer’s request for clarification and the response shall be in writing. No change in the substance of the Technical Bid or prices in the Price Bid shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the Bids, in accordance with ITB 36. |
|  | - If a Bidder does not provide clarifications of its Bid by the date and time set in the Employer’s request for clarification, its Bid may be rejected. |
| Deviations, Reservations, and Omissions | - During the evaluation of Bids, the following definitions apply: - “Deviation” is a departure from the requirements specified in the Bidding Document; - “Reservation” is the setting of limiting conditions or withholding from complete acceptance of the requirements specified in the Bidding Document; and - “Omission” is the failure to submit part or all of the information or documentation required in the Bidding Document. |
| - Preliminary Examination of Technical Bids | - The Employer shall examine the Technical Bid to confirm that all documents and technical documentation requested in ITB 11.2 have been provided, and to determine the completeness of each document submitted. If any of these documents or information is missing, the Bid may be rejected. - The Employer shall confirm that the following documents and information have been provided in the Technical Bid. If any of these documents or information is missing, the offer shall be rejected. (a) Letter of Technical Bid; (b) written confirmation of authorization to commit the Bidder; (c) Bid Security or Bid-Securing Declaration, if applicable; and (d) Technical Proposal in accordance with ITB 17. |
| Responsiveness of Technical Bids | - The Employer’s determination of a bid’s responsiveness is to be based on the contents of the Bid itself, as defined in ITB 11. |
|  | - A substantially responsive Technical bid is one that meets the requirements of the Bidding Document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that: - if accepted, would: - affect in any substantial way the scope, quality, or performance of the Plant and Installation Services specified in the Contract; or - limit in any substantial way, inconsistent with the Bidding Document, the Employer’s rights or the Bidder’s obligations under the proposed Contract; or - if rectified, would unfairly affect the competitive position of other Bidders presenting substantially responsive Bids. |
|  | - The Employer shall examine the technical aspects of the Bid submitted in accordance with ITB 17, Technical Proposal, in particular, to confirm that all requirements of Section VI (Employer’s Requirements) have been met without any material deviation, reservation, or omission. |
|  | - If a Bid is not substantially responsive to the requirements of the Bidding Document, it shall be rejected by the Employer and may not subsequently be made responsive by correction of the material deviation, reservation, or omission. |
| Nonmaterial Nonconformities | - Provided that a Bid is substantially responsive, the Employer may waive any nonconformities in the Bid that do not constitute a material deviation, reservation, or omission. |
|  | - Provided that a Technical Bid is substantially responsive, the Employer may request that the Bidder submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the Technical Bid related to documentation requirements. Requesting information or documentation on such nonconformities shall not be related to any aspect of the Price Bid. Failure of the Bidder to comply with the request may result in the rejection of its Bid. |
|  | - Provided that a Technical Bid is substantially responsive, the Employer shall rectify quantifiable nonmaterial nonconformities related to the Bid Price. To this effect, the Bid Price shall be adjusted, for comparison purposes only, to reflect the price of a missing or nonconforming item or component. The adjustment shall be made using the method indicated in Section III (Evaluation and Qualification Criteria). |
| Detailed Evaluation of Technical Bids | - The Employer will carry out a detailed technical evaluation of the Bids not previously rejected as being substantially nonresponsive, to determine whether the technical aspects are in compliance with the Bidding Document. The Bid that does not meet minimum acceptable standards of completeness, consistency, and detail, and the specified minimum and/or maximum requirements for specified functional guarantees, will be treated as nonresponsive and hence rejected. To reach such a determination, the Employer will examine and compare the technical aspects of the Bids on the basis of the information supplied by the Bidders, taking into account the following: - overall completeness and compliance with the Employer’s Requirements; deviations from the Employer’s Requirements; conformity of the Plant and Installation Services offered with specified performance criteria; suitability of the Plant and Installation Services offered in relation to the environmental and climatic conditions prevailing at the site; and quality, function and operation of any process control concept included in the Bid. The Bid that does not meet minimum and/or maximum acceptable standards of completeness, consistency, and detail will be rejected for nonresponsiveness; - type, quantity, and long-term availability of mandatory and recommended spare parts and maintenance services; and - other relevant factors, if any, listed in Section III (Evaluation and Qualification Criteria). - Where alternative technical solutions have been allowed in accordance with ITB 13, and offered by the Bidder, the Employer will make a similar evaluation of the alternatives. Where alternatives have not been allowed but have been offered, they shall be ignored. |
| Eligibility and Qualification of the Bidder | - The Employer shall determine to its satisfaction during the evaluation of Technical Bids whether a Bidder meets the eligibility and qualifying criteria specified in Section III (Evaluation and Qualification Criteria). - The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB 15. The determination shall not take into consideration the qualifications of other firms such as the Bidder’s subsidiaries, parent entities, affiliates, subcontractors (other than Specialist Subcontractors if permitted in the bidding document), or any other firm(s) different from the Bidder. - An affirmative determination shall be a prerequisite for the opening and evaluation of a Bidder’s Price Bid. A negative determination shall result into the disqualification of the Bid, in which event the Employer shall return the unopened Price Bid to the Bidder. - The capabilities of the manufacturers and subcontractors proposed in its Bid for the major items of Plant and Installation Services to be used by the lowest evaluated Bidder will also be evaluated for acceptability in accordance with Section III (Evaluation and Qualification Criteria). Their participation should be confirmed with a letter of intent between the parties, as needed. Should a manufacturer or subcontractor be determined to be unacceptable, the Bid will not be rejected, but the Bidder will be required to propose, without changing its bid price, an acceptable substitute manufacturer or subcontractor meeting the minimum technical specifications stated in Section VI (Employer’s Requirements). If a Bidder does not provide an acceptable substitute manufacturer or subcontractor by the date and time set in the Employer’s request for substitution of manufacturer or subcontractor, its Bid may be rejected. - Prior to signing the Contract, the corresponding Appendix to the Contract Agreement shall be completed, listing the approved manufacturers or subcontractors for each item concerned. |
| Correction of Arithmetical Errors | - During the evaluation of Price Bids, the Employer shall correct arithmetical errors on the following basis: - where there are errors between the total of the amounts given under the column for the price breakdown and the amount given under the Total Price, the amounts given under the column for the price breakdown shall prevail and the Total Price will be corrected; - where there are errors between the total of the amounts of Schedule Nos. 1 to 4 and the amount given in Schedule No. 5 (Grand Summary), the total of the amounts of Schedule Nos. 1 to 4 shall prevail and the Schedule No. 5 (Grand Summary) will be corrected accordingly; - if there is a discrepancy between the grand total price given in Schedule No. 5 (Grand Summary) and the bid amount in item (e) of the Letter of Price Bid, the grand total price given in Schedule No. 5 (Grand Summary) will prevail and the bid amount in item (e) of the Letter of Price Bid will be corrected; and - if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetical error, in which case the amount in figures shall prevail subject to (a), (b), and (c) above. |
|  | - If the Bidder that submitted the lowest evaluated Bid does not accept the correction of errors, its Bid shall be disqualified and its bid security may be forfeited, or its Bid-Securing Declaration executed. |
| Conversion to Single Currency | - For evaluation and comparison purposes, the Employer shall convert all bid prices expressed in amounts in various currencies into an amount in a single currency specified in the BDS, using the selling exchange rates established by the source and on the date specified in the BDS. |
| Evaluation and Comparison of Price Bids | - The Employer shall use the criteria and methodologies indicated in this clause. No other evaluation criteria or methodologies shall be permitted. |
|  | - I. To evaluate a Price Bid, the Employer shall consider the following: - the bid price, excluding provisional sums and the provision, if any, for contingencies in the Price Schedules; - price adjustment for correction of arithmetical errors in accordance with ITB 36.1; - price adjustment due to discounts offered in accordance with ITB 18.7 or ITB 18.8; - price adjustment due to quantifiable nonmaterial nonconformities in accordance with ITB 33.3; - converting the amount resulting from applying (a) to (d) above, if relevant, to a single currency in accordance with ITB 37; and - the evaluation factors indicated in Section III (Evaluation and Qualification Criteria). II. The Employer’s evaluation of a Bid will exclude and not take into account, - in the case of Plant and Mandatory Spare Parts (Schedule No. 1) supplied from abroad, all taxes and duties, applicable in the Employer’s country and payable on the Plant and Mandatory Spare Parts if the Contract is awarded to the Bidder; and - in the case of Plant and Mandatory Spare Parts (Schedule No. 2) supplied from within the Employer’s country, sales and other taxes, applicable in the Employer’s country and payable on the Plant and Mandatory Spare Parts if the Contract is awarded to the Bidder. |
|  | - If price adjustment is allowed in accordance with ITB 18.6, the estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in bid evaluation. |
|  | - If this Bidding Document allows Bidders to quote separate prices for different lots (contracts), and the award to a single Bidder of multiple lots (contracts), the methodology to determine the lowest evaluated price of the lot (contract) combinations, including any discounts offered in the Letter of Price Bid, is specified in Section III (Evaluation and Qualification Criteria). |
|  | - If the Bid, which results in the lowest Evaluated Bid Price, is seriously unbalanced or front loaded in the opinion of the Employer or the Bid is significantly lower than the Employer’s estimates, the Employer may require the Bidder to produce detailed price analyses for any or all items of the Price Schedules, to demonstrate the internal consistency of those prices with the methods and time schedule proposed. After evaluation of the price analyses, taking into consideration the terms of payments, the Employer may require that the amount of the performance security be increased at the expense of the Bidder to a level sufficient to protect the Employer against financial loss in the event of default of the successful Bidder under the Contract. - The Employer shall compare all substantially responsive Bids to determine the lowest evaluated Bid, in accordance with ITB 38.2. |
| Employer’s Right to Accept Any Bid, and to Reject Any or All Bids | - The Employer reserves the right to accept or reject any Bid, and to annul the bidding process and reject all Bids at any time prior to contract award, without thereby incurring any liability to Bidders. In case of annulment, all Bids submitted and specifically, bid securities, shall be promptly returned to the Bidders. |
| Award of Contract |  |
| Award Criteria | - The Employer shall award the Contract to the Bidder whose offer has been determined successful in line with ITB 34 to ITB 38 above to be the lowest evaluated Bid and is substantially responsive to the Bidding Document, provided further that the Bidder is determined to be eligible and qualified to perform the Contract satisfactorily. |
| Standstill Period | - If the Standstill Period is applied as specified in the BDS, the Contract shall not be awarded earlier than the expiry of the Standstill Period. The Standstill Period shall be ten (10) Business Days unless extended in accordance with ITB 44.1. The Standstill Period commences the day after the date the Employer has transmitted to each Bidder the Notification of Intention to Award the Contract. In case where only one Bid is submitted, or in case of direct contracting, the Standstill Period shall not apply. |
| Notification of Intention to Award | - If the Standstill Period is applied in accordance with ITB 41.1, the Employer shall send to each Bidder the Notification of Intention to Award the Contract, using the applicable form included in Section IX. Contract Forms, as per the instructions specified in the BDS. |
| Notification of Award | - Prior to the expiration of the period of bid validity, the Employer shall notify the successful Bidder, in writing, using the Notification of Award form included in Section IX. Contract Forms, that its bid has been accepted. At the same time, the Employer shall also notify unsuccessful Bidders of the results of the bidding including the following information: - name of each Bidder who submitted a Bid; - bid prices as read out at bid opening; - name and evaluated prices of each bid that was evaluated; - name of Bidders whose Bids were rejected and the reasons for their rejection; and - name of the winning Bidder, and the price it offered, as well as the duration and summary scope of the contract awarded. - Until a formal contract is prepared and executed, the notification of award shall constitute a binding Contract. - Notwithstanding the foregoing, if the Standstill Period is applied, the Employer shall, prior to the expiration of the period of bid validity and upon expiry of the Standstill Period specified in ITB 41.1 or any extension thereof, and upon satisfactorily addressing any Complaint that has been filed within the Standstill Period, notify the successful Bidder, in writing, using the Notification of Award form included in Section IX. Contract Forms, that its Bid has been accepted. |
| Debriefing by the Employer | - If the Standstill Period is applied, upon receipt of the Employer’s Notification of Intention to Award referred to in ITB 42.1, an unsuccessful Bidder has three (3) Business Days to make a written request to the Employer for a debriefing. The Employer shall provide a debriefing to all unsuccessful Bidders whose request is submitted in compliance with the procedures as set forth in the BDS and is received within this deadline. - Where a request for debriefing is received within the deadline, the Employer shall provide a debriefing within five (5) Business Days, unless the Employer decides, for justifiable reasons, to provide the debriefing outside this timeframe. In that case, the standstill period shall automatically be extended until five (5) Business Days after such debriefing is provided. If more than one debriefing is so delayed, the standstill period shall not end earlier than five (5) Business Days after the last debriefing takes place. The Employer shall promptly inform, by the quickest means available, all Bidders of the extended standstill period. - Where a request for debriefing is received by the Employer later than the three (3)-Business Day deadline, the Employer should provide the debriefing as soon as practicable, and normally no later than fifteen (15) Business Days from the date of publication of the Contract award. Requests for debriefing received outside the three (3)-day deadline shall not lead to extension of the standstill period. - In a non-Standstill situation where the Standstill Period is not applied, the Employer shall promptly respond either in writing and/or in a debriefing meeting (at the option of the Employer) to any unsuccessful Bidder who, after notification of award in accordance with ITB 43.1, requests in writing the grounds on which its bid was not selected. - Debriefings of unsuccessful Bidders may be done in writing or verbally. The Bidder shall bear their own costs of attending such a debriefing meeting. |
| Signing of Contract | - Promptly after Notification of Award, the Employer shall send the successful Bidder the Contract Agreement. |
|  | - Within twenty-eight (28) days of receipt of the Contract Agreement, the successful Bidder shall sign, date, and return it to the Employer. - Notwithstanding ITB 45.2 above, in case signing of the Contract Agreement is prevented by any export restrictions attributable to the Employer, to the country of the Employer, or to the use of the Plant and Installation Services to be supplied, where such export restrictions arise from trade regulations from a country supplying those Plant and Installation Services, the Bidder shall not be bound by its Bid, always provided, however, that the Bidder can demonstrate to the satisfaction of the Employer and of the Bank that signing of the Contact Agreement has not been prevented by any lack of diligence on the part of the Bidder in completing any formalities, including applying for permits, authorizations and licenses necessary for the export of the Plant and Installation Services under the terms of the Contract. |
| Performance Security | - Within twenty-eight (28) days of the receipt of notification of award from the Employer, the successful Bidder shall furnish the performance security in accordance with the Conditions of Contract, subject to ITB 38.5, using for that purpose the Performance Security Form included in Section IX, Contract Forms, or another form acceptable to the Employer. - Failure of the successful Bidder to submit the above-mentioned Performance Security or sign the Contract shall constitute sufficient grounds for the annulment of the award and forfeiture of the bid security or execution of the Bid-Securing Declaration. In that event, the Employer may award the Contract to the next lowest evaluated Bidder whose offer is substantially responsive and is determined by the Employer to be qualified to perform the Contract satisfactorily. |
| Procurement- related Complaint | - Bidding-related Complaint (hereinafter called the “Complaint”) shall be submitted in compliance with the procedures as set forth in the BDS. - When so submitted to the Employer, the Employer shall address Complaints promptly and fairly. - Any Complaint shall identify the name, contact details (i.e. telephone number and e-mail address), address of the complainant, the complainant’s interest in the relevant procurement, the specific project, the source and nature of the Complaint, any previous communication between the complainant and the Employer on the matters addressed in the Complaint, the alleged inconsistency with the applicable procurement rules, and any other relevant information. - If the sources of information related to the Complaint and the identity of the complainant are not clear, detailed information with supporting documents shall be submitted at the request of the Employer. Should such information not be provided appropriately, the Complaint shall not be received. - If the Standstill Period is applied in accordance with ITB 41.1, Complaints following the submission of a Bid must be submitted to the Employer within the Standstill Period or any extension thereof (where applicable in accordance with ITB Sub-Clause 44.1 (a)), and received by the Employer before the Standstill Period ends. |

Section II. Bid Data Sheet
(Single Stage: Two-Envelope)

The following specific data for the Facilities to be procured shall complement, supplement, or amend the provisions in the Instructions to Bidders (ITB). Whenever there is a conflict, the provisions herein shall prevail over those in ITB.

[Instructions for completing the Bid Data Sheet are provided, as needed, in the notes in italics mentioned for the relevant ITB.]

| A. General |  |
| --- | --- |
| ITB 1.1 | The number of the Invitation for Bids (IFB) is: [Insert number of the Invitation for Bids] |
| ITB 1.1 | The Employer is: [Insert name of the Employer] |
| ITB 1.1 | The name of the competitive bidding (CB) is: [Insert name of the CB] The identification number of the CB is: [Insert number of the CB] [The following text is to be included and the corresponding information inserted only if the contract is to be bid simultaneously with other contracts on a “slice and package” basis. Otherwise omit.] The number and identification of lots (contracts) comprising this CB is: [Insert number and identification of lots (contracts)] |
| ITB 2.1 | The Borrower is: [Insert name of the Borrower and statement of relationship with the Employer, if different from the Borrower. This insertion should correspond to the information provided in the Invitation for Bids] |
|  | The name of the Project is: [Insert name of the project] |
| ITB 3.4 | Address for the Bank: 38 Eunhaengno (16-1 Yeouido-dong), Yeongdeungpo-gu, Seoul, Korea 07242 TEL: 82-2-3779-xxxx FAX: 82-2-3779-xxxx E-Mail: xxxxxxx@koreaexim.go.kr Attention: |
| ITB 4.3 (f) | For a Bidder who participated as a consultant in the preparation of the feasibility study, this provision does not limit the participation of a Bidder if participating solely for the purpose of serving as a consultant under a turnkey or design and build contract. |
| ITB 4.5 | This clause shall be [Insert “applied” or “deleted” in accordance with the restrictions regarding nationality of Eligible Bidder specified in ITB 4.2] |
| B. Contents of Bidding Document |  |
| ITB 7.1 | For clarification purposes only, the Employer’s address is: [Insert the corresponding information as required below. This address may be the same as or different from that specified under provision ITB 23.1 for bid submission.] Attention: [insert name and room number of Project Officer] Address: [Insert street address and number.] Floor/Room number: [Insert floor and room number, if applicable.] City: [Insert name of city or town.] ZIP Code: [Insert postal (ZIP) code, if applicable.] Country: [Insert name of country.] Telephone: [Insert telephone number, including country and city codes.] Facsimile number: [Insert fax number, including country and city codes.] E-mail: [Insert email address of Project Officer.] |
| ITB 7.4 | A Pre-Bid meeting [Insert “will” and insert the date, time and place information in the spaces provided below if a pre-bid meeting will take place, taking into consideration that the meeting should take place no later than four weeks before the deadline for bid submission. Otherwise, insert “will not” and insert “Not Applicable” in the spaces provided below for the date, time and place] take place at the following date, time and place: Date: Time: Place: A site visit conducted by the Employer [Insert “shall be” or “shall not be”] organized. |
| C. Preparation of Bids |  |
| ITB 11.2 (k) | The Bidder shall submit with its Technical Bid the following additional documents in its Bid: [Specify any additional document not already listed in ITB 11.2 that must be submitted with the Bid.] |
| ITB 11.3 (d) | The Bidder shall submit with its Price Bid the following additional documents in its Bid: [Specify any additional document not already listed in ITB 11.3 that must be submitted with the Bid.] |
| ITB 13.1 | [The following provision should be included and the required corresponding information inserted only if alternative bids will be considered. Otherwise omit.] Alternative bids [Insert “shall be”] permitted. |
| ITB 13.2 | Alternative times for completion [Insert “will be” or “will not be”, as appropriate] permitted. [Alternative times for completion should be permitted when the Employer sees potential net benefits in different times for completion; they also have merit for contracts bid on a “slice and package” basis.] If alternatives times for completion are permitted, the evaluation method will be as specified in Section III (Evaluation and Qualification Criteria). |
| ITB 13.4 | Alternative technical solutions shall be permitted for the following parts of the Plant and Installation Services: [Insert parts of the Plant] as further detailed in the Specification. If alternative technical solutions are permitted, the evaluation method will be as specified in Section III (Evaluation and Qualification Criteria). |
| ITB 16.1(b) | The period following completion of Plant and Installation Services during which spare parts, special tools etc. shall be available, is [insert number of years as appropriate, normally two (2) years] __________________. |
| ITB 18.1 | [Choose one of the following options as appropriate.] Bidders shall quote for the entire Plant and Installation Services on a single responsibility basis. [or] Bidders shall quote for the following components or services on a single responsibility basis: [insert list of components or services] ________________________________________________ [and/or] The following components or services will be provided under the responsibility of the Employer: [insert list of components or services] ________________________________________________ |
| ITB 18.4 | In accordance with the Loan Agreement, all taxes, duties and levies, including but not limited to import duties and Value-Added Tax, imposed on goods, works, Plant and Installation Services to be used in [insert the name of the Borrower’s country], provided and/or purchased from any countries by the Contractor, subcontractors and/or local suppliers of any countries under the Loan Agreement for the implementation of the Contract shall be [choose one of the following: “exempted,” “reimbursed,” “paid by the Employer on behalf of the Contractor” as appropriate.] |
| ITB 18.4 (a) and (d) | Place of destination: [insert named place of destination as per Incoterm used] Final destination (Project Site): ___________ [insert final destination, if different from named place of destination] |
| ITB 18.5 | The Incoterms edition is: [insert relevant edition]. |
| ITB 18.6 | The prices quoted by the Bidder shall be [insert “fixed” or “adjustable”] [If prices are to be adjustable, insert: “The formula for adjusting the prices and explanatory details are specified in the Special Conditions of Contract (SCC) Clause 11.2 and Appendix 2 of Contract Agreement. Bidder shall fill out the Tables of Adjustment Data in Section IV (Bidding Forms).”] [Use “Adjustable” where the contract period is of long duration (generally exceeds eighteen (18) months). Prices payable to the contractor shall be subject to price adjustment during the performance of the contract.] [If prices shall be fixed, the Tables of Adjustment Data in Section IV (Bidding Forms) shall be removed.] |
| ITB 19.1 | [Insert one of the followings in accordance with Loan Agreement.] [If the Loan is denominated in Korean Won.] The bid price shall be stated in US Dollars. However, the contract price shall be stated in Korean Won converted by using the exchange rate which is the average of the telegraphic transfer selling rates on the Korean Won against the US Dollar as quoted and publicly displayed by the Bank, during the one month period from the sixteenth (16th) day of two calendar months prior to the month when the contract is signed, to the fifteen (15th) day of one calendar month prior thereto. [If the Loan is denominated in US Dollars, Euro, or any other currency apart from the Korean Won.] The bid price shall be stated in [Insert the currency according to the Loan Agreement.] |
| ITB 20.1 | The bid validity period shall be [Insert a number of days that is a multiple of seven counting as of the deadline for bid submission.] days. [This period should be realistic, allowing sufficient time to evaluate the bids, bearing in mind the complexity of the Plant and the time required for obtaining references, clarifications, clearances, and approvals (including the Bank’s “No Objection”) and for notification of the award. Normally the validity period should not exceed one hundred and twenty (120) days.] |
| ITB 20.3 (a) | The bid price shall be adjusted by the following factor(s): _____________ [The local currency portion of the Contract price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the Contract price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.] Note: If Adjustable Price is applied in accordance with BDS 18.6; Not Applicable. |
| ITB 20.3 (b) | The fixed portion of the Bid Price shall be adjusted by the following factor(s): _____________ [The local currency portion of the fixed portion of the Contract price shall be adjusted by a factor reflecting local inflation during the period of extension, and the foreign currency portion of the fixed portion of the Contract price shall be adjusted by a factor reflecting the international inflation (in the country of the foreign currency) during the period of extension.] Note: If there is no fixed portion of the Bid price, or the entire price is fixed; Not Applicable. |
| ITB 21.1 | [If a bid security shall be required, a Bid-Securing Declaration shall not be required, and vice versa.] A bid security [Insert “shall be” or “shall not be”] required. A Bid-Securing Declaration [Insert “shall be” or “shall not be”] required. If a bid security shall be required, the amount and currency of the Bid Security shall be: [If a bid security is required, insert amount and currency of the bid security. Otherwise insert “Not Applicable.”] |
| ITB 21.3(a) | The bid security shall be issued by a bank, insurance company, or financial institution in the Employer’s country or the Contractor's country whose credit rating is equal or above A- (A3) (equivalent) rated by an international credit rating agency (e.g., S&P, Fitch, or Moody's). [The credit rating may be adjusted based on the financial situations in either the Employer’s or the Contractor’s country] |
| ITB 21.3 (d) | Other types of acceptable securities: ____________________________________________________________ [Insert name of other acceptable securities. Insert “None” if no bid security is required under provision ITB 21.1 or if bid security is required but no other forms of bid securities besides those listed in ITB 21.3 (a) through (c) are acceptable.] |
| ITB 21.9 | [Delete if not applicable: The following provision should be included and the required corresponding information inserted only if a bid security is not required under provision ITB 21.1 and the Employer wishes to declare the Bidder ineligible for a period of time should the Bidder perform any of the actions mentioned in provision ITB 21.9 (a) and (b). Otherwise omit.] If the Bidder incurs any of the actions prescribed in ITB 21.9 (a) or (b), the Borrower will declare the Bidder ineligible to be awarded a contracts by the Employer for a period of ________ [Insert period of time] years. |
| ITB 22.1 | In addition to the original of the bid, the number of copies is: [Insert number of copies] ____________. |
| ITB 22.2 | The written confirmation of authorization to sign on behalf of the Bidder shall consist of: [Insert the name and description of the documentation required to demonstrate the authority of the signatory to sign the bid]. |
| D. Submission and Opening of Bids |  |
| ITB 23.1 | Bidders [insert “shall” or “shall not”] have the option of submitting their bids electronically. |
| ITB 23.1 (b) | [The following provision should be included and the required corresponding information inserted only if Bidders have the option of submitting their bids electronically. Otherwise omit.] The electronic bidding submission procedures shall be: [Insert a description of the electronic bidding submission procedures.] |
| ITB 24.1 | For bid submission purposes only, the Employer’s address is: [This address may be the same as or different from that specified under provision ITB 7.1 for clarifications.] Attention: [Insert full name of person, if applicable.] Street Address: [Insert street address and number.] Floor/Room number: [Insert floor and room number, if applicable.] City: [Insert name of city or town.] ZIP Code: [Insert postal (ZIP) code, if applicable.] Country: [Insert name of country.] [The time allowed for the preparation and submission of bids shall be determined with due consideration of the particular circumstances of the Project and the size and complexity of the contract. Where large works or complex items of equipment are involved, the period from the date of the invitation to bid or the date of availability of bidding documents, whichever is later, shall be generally not less than ninety (90) days to enable prospective bidders to conduct investigations at the site before submitting their bids.] The deadline for bid submission is: Date: [Insert day, month and year, i.e. 15 June 2020] Time: [Insert time, and identify if a.m. or p.m., i.e. 10:30 a.m.] [The date and time should be the same as those provided in the Invitation for Bids, unless subsequently amended pursuant to ITB 24.2.] |
| ITB 27.1 | The bid opening shall take place at: Street Address: [Insert street address and number] Floor/Room number: [Insert floor and room number, if applicable.] City: [Insert name of city or town Country: [Insert name of country] Date: [Insert day, month, and year, i.e. 15 June 2020] Time: [Insert time, and identify if a.m. or p.m., i.e. 10:30 a.m.] [The date and time should be the same as those given for the deadline for submission of bids in accordance with ITB 24] |
| ITB 27.1 | [The following provision should be included and the required corresponding information inserted only if Bidders have the option of submitting their bids electronically. Otherwise omit.] The electronic bid opening procedures shall be: [Insert a description of the electronic bid opening procedures.] |
| ITB 27.5 | The Letter of Bid and Price Schedules shall be initialed by _______ [insert number] representatives of the Employer conducting Bid opening. __________ [Insert procedure: Example: Each Bid shall be initialed by all representatives and shall be numbered, any modification to the unit or total price shall be initialed by the Representative of the Employer, etc.] |
| E. Evaluation and Comparison of Bids |  |
| ITB 37.1 | The currency that shall be used for Bid evaluation and comparison purposes to convert (at the selling exchange rate) all Bid prices expressed in various currencies into a single currency is: ____________ [Insert name of currency] The source of exchange rate shall be: ___________ [Insert name of the source of exchange rates (e.g., the Central Bank in the Employer’s Country).] The date for the exchange rate shall be: [insert day, month and year, e.g. 15 June, 2020 not earlier than twenty-eight (28) days prior to the deadline for submission of the Bids, nor later than the original date for the expiry of bid validity specified in accordance with ITB BDS 20.1]. |
| F. Award of Contract |  |
| ITB 41.1 | The Standstill Period [insert “shall” or “shall not”] be applied. |
| ITB 42.1 | The Notification of Intention to Award the Contract shall contain, at a minimum, the following information: (a) the name and address of the Bidder submitting the successful Bid; (b) the contract price of the successful Bid; (c) the names of all Bidders who submitted Bids, and their Bid prices as readout, and as evaluated; and (d) a statement of the reason(s) why the Bid was unsuccessful, unless the price information in (c) above already reveals the reason. |
| ITB 46.1 | The Performance Security and the Advance Payment Security shall be in the form attached hereto in Section IX (Contract Forms), or another form acceptable to the Employer. The both of the Securities shall be issued by a bank, insurance company, or financial institution in the Employer’s country or the Contractor's country whose credit rating is equal or above A- (A3) (equivalent) rated by an international credit rating agency (e.g., S&P, Fitch, or Moody's). [The credit rating may be adjusted based on the financial situations in either the Employer’s or the Contractor’s country] |
| ITB 44.1/47.1 | Any Complaint related to the Procurement shall be submitted in writing, to: Attention: __________________ Title/position: _____________________ Employer: ________________________ E-mail address: ____________________ Facsimile number: ________________ Any Complaint related to fraud or corruption associated with the Employer or any interested party in the Procurement process shall be submitted in writing, to: Attention: __________________ Title/position: _____________________ Anti-Corruption Unit*: ________________________ E-mail address: ____________________ Facsimile number: ________________ [* Any entity vested with the authority to address matters of fraud or corruption within the Employer’s parent ministry, the ministry responsible for administering the EDCF Loan, or the government body overseeing public procurement.] |

Section III. Evaluation and Qualification Criteria 
(Following Prequalification)

This Section contains all the criteria that the Employer shall use to evaluate bids and qualify Bidders. In accordance with ITB 36 and ITB 37 (for Two-envelope; substitute ITB 34, ITB 35 and ITB 38), no other factors, methods or criteria shall be used other than those specified in this bidding document. The Bidder shall provide all the information requested in the forms included in Section IV (Bidding Forms).

[The Employer shall select the criteria deemed appropriate for the procurement process, insert the appropriate wording using the samples below or other acceptable wording, and delete the text in italics.]

Table of Criteria

1.	Evaluation	85

1.1 Technical Evaluation	85

1.2 Alternative Technical Solutions	85

1.3 Economic Evaluation	85

1.4 Multiple Contracts	87

2.	Qualification	88

2.1 Update of Information	88

2.2 Financial Resources	88

2.3 Personnel	89

2.4 Equipment	90

2.5 Subcontractors/manufacturers	91

    - Evaluation

##### 1.1 Technical Evaluation

In addition to the criteria the criteria listed in ITB 36.2 (a)-(b) (for Two-envelope; substitute ITB 34.1 (a)-(b)), the following factors shall apply:

##### 1.2 Alternative Technical Solutions

The acceptability of alternative technical solutions for parts of the facilities, if permitted under ITB 13.4, will be determined as follows:

##### 1.3 Economic Evaluation

[Any adjustments in price that result from the procedures outlined below shall be added, for purposes of comparative evaluation only, to arrive at an “Evaluated Bid Price.” Bid Prices quoted by Bidders shall remain unaltered.]

In addition to the criteria listed in ITB 36.4 (a)-(f) (for Two-envelope; substitute ITB 38.2 (a)-(f)), other relevant factors are as follows:

1.3.1 Quantifiable Deviations and Omissions

[Insert: “Pursuant to ITB 33.3 and ITB 36.4(for Two envelope; substitute ITB 33.3 and ITB 38.2), the cost of all quantifiable nonmaterial nonconformities or omissions from the contractual and commercial conditions shall be evaluated. The Employer will make its own assessment of the cost of any nonmaterial nonconformities and omissions for the purpose of ensuring fair comparison of Bids.”]

1.3.2 Time Schedule

Time to complete the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement for determining the time for completion of pre-commissioning activities is: [insert number of days]…………………….. No credit will be given for earlier completion.

or [where alternative time schedule is accepted, pursuant to ITB 13.2]

Time to complete the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement for determining the time for completion of pre-commissioning activities shall be between …………………….  minimum and …………………….  maximum. The adjustment rate in the event of completion beyond the minimum period shall be …………………….  for each week of delay from that minimum period. No credit will be given for completion earlier than the minimum designated period. Bids offering a completion date beyond the maximum designated period shall be rejected.

1.3.3 Operation and Maintenance (O&M) Costs

Since the operating and maintenance costs of the facilities being procured form a major part of the life cycle cost of the facilities, these costs will be evaluated according to the principles given hereafter, including the cost of spare parts for the initial period of operation stated below and based on prices furnished by each Bidder in Price Schedule Nos. 1 and 2, as well as on past experience of the Employer or other Employers similarly placed. Such costs shall be added to the Bid Price for evaluation.

[Use one of the two options given below – delete the inapplicable option.]

Option 1:

The O&M cost factors for calculating the life cycle cost are as follows:

    - Number of years for life cycle ……………………. …………………….

    - Operating costs [Insert fuel and/or other input, unit cost for annual and total operational requirements.] ……………………. …………………………………….

    - Maintenance costs, including the cost of spare parts for the initial period of operation, and

    - A rate of …………………….  in percentage to be used to discount to present value all annual future costs calculated under (b) and (c) for the period specified in (a).

or

Option 2:

Reference to the methodology specified in the Specification or elsewhere in the Bidding Document. [Insert a reference to the methodology specified in the Specification or elsewhere in the Bidding Document.]

The price of recommended spare parts quoted in Price Schedule No. 6 shall not be considered for evaluation.

1.3.4 Functional Guarantees of the Facilities

The minimum and/or maximum requirements stated in the Specification for functional guarantees required in the Specification are:

| Functional Guarantee [as required in the Specification, e.g., performance, efficiency, consumption, etc.] | Minimum and/or Maximum Requirement [as required in the Specification] |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| … |  |

For the purposes of evaluation, for each percentage point in performance or efficiency below the norm specified in the Specification but above the minimum acceptable levels also specified there, an adjustment of [Insert amount in the currency of Bid evaluation] ……………………. will be added to the bid price. If the drop below the norm or the excess above the minimum acceptable levels is less than one percent, the adjustment will be prorated accordingly.

1.3.5 Work, Services, Facilities, etc., to be provided by the Employer

Where bids include the undertaking of work or the provision of services or facilities by the Employer in excess of the provisions allowed for in the Bidding Document, the Employer shall assess the costs of such additional work, services and/or facilities during the duration of the contract. Such costs shall be added to the Bid Price for evaluation.

1.3.6 Specific Additional Criteria

The following additional criteria will be used in the evaluation:

##### 1.4 Multiple Contracts (ITB 36.6 (for Two-envelope; substitute ITB 38.4))

If in accordance with ITB 1.1, Bids are invited for more than one lot, the contract will be awarded to the Bidder or Bidders offering a substantially responsive Bid(s) and the lowest evaluated cost to the Employer for combined lots, subject to the selected Bidder(s) meeting the required qualification criteria Section III, Evaluation and Qualification Criteria for a lot or combination of lots as the case may be.

In determining Bidder or Bidders that offer the total lowest evaluated cost to the Employer, after considering all possible combination of lots, the Employer shall apply the following steps in sequence:

    - evaluate individual lots to determine the substantially responsive Bids and corresponding evaluated costs;

    - for each lot, rank the substantially responsive Bids starting from the lowest evaluated cost for the lot;

    - apply to the evaluated costs listed in b) above, any applicable discounts/price reductions offered by a Bidder (s) for the award of multiple contracts based on the discounts and the methodology for their application offered by the respective Bidder; and

    - determine contract award on the basis of the combination of lots that offer the total lowest evaluated cost to the Employer.

    - Qualification

##### 2.1 Update of Information

The Bidder shall continue to meet the criteria used at the time of Prequalification. Updating and reassessment of the following information which was previously considered during Prequalification will be required:

    - Eligibility

    - Historical Contract Non-Performance

    - Financial Situation

The Bidder shall provide updated details for the above by using the relevant forms included in Section IV (Bidding Forms).

##### 2.2 Financial Resources

Using the relevant Forms in Section IV (Bidding Forms), the Bidder must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, lines of credit, and other financial means, other than any contractual advance payments to meet:

(i)  the following cash-flow requirement:…………………………….….…; and

(ii) the overall cash flow requirements for this contract and its current commitments.

<<Notes for the Employer>>

Indicate the cash flow requirement for a number of months (to the nearest half-month), determined as the total time needed by the Employer to pay a contractor’s invoice, allowing for (a) the actual time consumed for construction, from the beginning of the month invoiced, (b) the time needed by the Engineer to issue the monthly payment certificate, (c) the time needed by the Employer to pay the amount certified, and (d) a contingency period of one month to allow for unforeseen delays. The total period should not exceed six months. The assessment of the monthly amount should be based on a straight-line projection of the estimated cash flow requirement over the particular contract period, neglecting the effect of any advance payment and retention monies, but including contingency allowances in the estimated contract cost.

##### 2.3 Personnel

The Bidder must demonstrate that it has the personnel for the key positions that meet the following requirements.

| No. | Position | Total Work Experience (years) | Experience in Similar Position (years) |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| … |  |  |  |

The Bidder shall provide details of the proposed personnel and their experience records in the relevant Information Forms included in Section IV (Bidding Forms).

<<Notes for the Employer>>

The managerial and technical competence of a contractor is largely related to the key personnel on site. The extent to which the Bidder should demonstrate having staff with extensive experience should be limited to those requiring critical operational or technical skills. The qualification criteria should therefore refer to a limited number of such key personnel, for instance, the project or contract manager and those superintendents working under the project manager who will be responsible for major components (e.g., superintendents specialized in dredging, piling, tunneling, or earthworks, as required for each particular project).

Bidders should normally be required to name a principal candidate and an alternate for each key position. Criteria of acceptability should be based on:

(a) a minimum number of years of experience in a similar position; and

(b) a minimum number of years of experience and/or number of comparable projects carried out in a specified number of preceding years.

The requirement of specified education and academic qualifications is normally unnecessary for such positions, as contractors often employ competent staffs who have learned their profession “on the job” rather than through academic training.

It is appropriate to specify that certain positions are filled by individuals who have held posts of comparable authority for, say, three (3) years with the Bidder, so that key staffs in executive site positions have sufficient knowledge of the Bidder's management, policy, procedures, and practices to act with confidence and authority within that framework.

##### 2.4 Equipment

The Bidder must demonstrate that it has the key equipment listed hereafter.

| No. | Equipment Type and Characteristics | Min. Number required |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |

The Bidder shall provide further details of proposed items of equipment using the relevant Form in Section IV (Bidding Forms).

The Bidder shall own, or have assumed access (through hire, lease, purchase agreement, other commercial means, or approved subcontracting) to key items of equipment, in full working order, and must demonstrate that based on known commitments, they will be available for timely use in the proposed contract.

<<Notes for the Employer>>

An inventory of construction equipment represents a high capital cost overhead to a contractor. Consequently, not all competent potential bidders will maintain an inventory of high-value items that are in suitable condition for major contracts. This is particularly so with management contractors, who undertake construction projects mainly by subcontracting. In most cases Bidders can readily purchase, lease, or hire equipment; thus, it is usually unnecessary for the assessment of a contractor's qualification to depend on the contractor’s owning readily available items of equipment. The pass–fail criteria adopted should therefore be limited only to those bulky or specialized items that are critical for the type of project to be implemented, and that may be difficult for the contractor to obtain quickly. Examples may include items such as heavy lift cranes and piling barges, dredgers, tunnel boring machines, asphalt mixing plants, etc. Even in such cases, contractors may not own the specialized items of equipment, and may rely on specialist subcontractors or equipment–hire firms. The availability of such subcontractors and of the specified equipment should be subject to verification prior to contract award. The terms of any lease or hire agreement for equipment should preferably include a provision that the equipment will remain on the site (or be vested in the Employer) in the event of default of the Contractor, thereby ensuring more timely continuity of work by a replacement contractor.

##### 2.5 Subcontractors/manufacturers

Subcontractors/manufacturers for major items of supply or services(‘Specialist Subcontractors’)  identified in the Prequalification document must meet or continue to meet the minimum criteria specified therein for each item.

<<Notes for the Employer>>

The minimum criteria should be established only for major items of supply or services, not for general items. Specifically, for subcontractors, the minimum criteria should apply only to subcontractors performing a specific type of work, rather than to all subcontractors.

Subcontractors/manufacturers for the following additional major items of supply or services must meet the following minimum criteria, herein listed for that item:

| Item No. | Description of Item | Minimum Criteria to be met |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |

Failure to comply with this requirement will result in the rejection of the Subcontractor. Should a manufacturer or subcontractor be determined to be unacceptable, the Bid will not be rejected, but the Bidder will be required to propose, without changing its bid price, an acceptable substitute manufacturer or subcontractor meeting the minimum criteria in accordance with ITB 35.4.

In the case of a Bidder who offers to supply and install major items of supply under the Contract that the Bidder did not manufacture or otherwise produce, the Bidder shall provide the manufacturer’s authorization, using the form provided in Section IV (Bidding Forms), showing that the Bidder has been duly authorized by the manufacturer or producer of the related plant and equipment or component to supply and/or install that item in the Employer’s country. Failure to submit the Manufacturer’s authorization at the first instance is considered a minor, nonmaterial omission and shall be subject to clarification. However, failure of the Bidder to submit the omitted authorization shall lead to rejection of the Subcontractor or Manufacturer of the item under evaluation in accordance with ITB 37.4 (for Two-envelope; substitute ITB 35.4).

Section III: Evaluation and Qualification Criteria
(Without Prequalification)

This Section contains all the criteria that the Employer shall use to evaluate bids and qualify Bidders. In accordance with ITB 36 and ITB 37 (for Two-envelope; substitute ITB 34, ITB 35 and ITB 38), no other factors, methods or criteria shall be used other than those specified in this bidding document. The Bidder shall provide all the information requested in the forms included in Section IV (Bidding Forms).

[The Employer shall select the criteria deemed appropriate for the procurement process, insert the appropriate wording using the samples below or other acceptable wording, and delete the text in italics.]

Table of Criteria

1. Evaluation	94

1.1 Technical Evaluation	94

1.2 Alternative Technical Solutions	94

1.3 Economic Evaluation	94

1.4 Multiple Contracts	96

2. Qualification	98

2.1 Eligibility	98

2.1.1 Nationality	98

2.1.2 Conflict of Interest	98

2.1.3 EDCF Eligibility	98

2.1.4 Government-Owned Entity	98

2.2 Historical Contract Non-Performance	99

2.2.1 Suspension	99

2.2.2 Pending Litigation	99

2.3 Financial Situation	100

2.3.1 Historical Financial Performance	100

2.3.2 Average Annual Turnover	100

2.3.3 Financial Resources	101

2.4 Experience	102

2.4.1 General Experience	102

2.4.2 Specific Experience	102

(a) Contracts of Similar Size and Nature	102

(b) Experience in Key Activities	103

2.5 Personnel	105

2.6 Equipment	106

2.7 Subcontractors/manufacturers	107

#### 1. Evaluation

##### 1.1 Technical Evaluation

In addition to the criteria the criteria listed in ITB 36.2 (a)-(b) (for Two-envelope; substitute ITB 34.1 (a)-(b)), the following factors shall apply:

##### 1.2 Alternative Technical Solutions

The acceptability of alternative technical solutions for parts of the facilities, if permitted under ITB 13.4, will be determined as follows:

##### 1.3 Economic Evaluation

[Any adjustments in price that result from the procedures outlined below shall be added, for purposes of comparative evaluation only, to arrive at an “Evaluated Bid Price.” Bid Prices quoted by Bidders shall remain unaltered.]

In addition to the criteria listed in ITB 36.4 (a)-(f) (for Two-envelope; substitute ITB 38.2 (a)-(f)), other relevant factors are as follows:

1.3.1 Quantifiable Deviations and Omissions

[Insert: “Pursuant to ITB 32.3, the cost of all quantifiable nonmaterial nonconformities or omissions from the contractual and commercial conditions shall be evaluated. The Employer will make its own assessment of the cost of any nonmaterial nonconformities and omissions for the purpose of ensuring fair comparison of Bids.”]

1.3.2 Time Schedule

Time to complete the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement for determining the time for completion of pre-commissioning activities is: [insert number of days]…………………….. No credit will be given for earlier completion.

or [where alternative time schedule is accepted, pursuant to ITB 13.2]

Time to complete the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement for determining the time for completion of pre-commissioning activities shall be between …………………….  minimum and …………………….  maximum. The adjustment rate in the event of completion beyond the minimum period shall be …………………….  for each week of delay from that minimum period. No credit will be given for completion earlier than the minimum designated period. Bids offering a completion date beyond the maximum designated period shall be rejected.

1.3.3 Operation and Maintenance (O&M) Costs

Since the operating and maintenance costs of the facilities being procured form a major part of the life cycle cost of the facilities, these costs will be evaluated according to the principles given hereafter, including the cost of spare parts for the initial period of operation stated below and based on prices furnished by each Bidder in Price Schedule Nos. 1 and 2, as well as on past experience of the Employer or other Employers similarly placed. Such costs shall be added to the Bid Price for evaluation.

[Use one of the two options given below – delete the inapplicable option.]

Option 1:

The O&M cost factors for calculating the life cycle cost are as follows:

    - Number of years for life cycle ……………………. …………………….

    - Operating costs [Insert fuel and/or other input, unit cost for annual and total operational requirements.] ……………………. …………………………………….

    - Maintenance costs, including the cost of spare parts for the initial period of operation, and

    - A rate of …………………….  in percentage to be used to discount to present value all annual future costs calculated under (b) and (c) for the period specified in (a).

or

Option 2:

Reference to the methodology specified in the Specification or elsewhere in the Bidding Document. [Insert a reference to the methodology specified in the Specification or elsewhere in the Bidding Document.]

The price of recommended spare parts quoted in Price Schedule No. 6 shall not be considered for evaluation.

1.3.4 Functional Guarantees of the Facilities

The minimum and/or maximum requirements stated in the Specification for functional guarantees required in the Specification are:

| Functional Guarantee [as required in the Specification, e.g., performance, efficiency, consumption, etc.] | Minimum and/or Maximum Requirement [as required in the Specification] |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| … |  |

For the purposes of evaluation, for each percentage point in performance or efficiency below the norm specified in the Specification but above the minimum acceptable levels also specified there, an adjustment of [Insert amount in the currency of Bid evaluation] ……………………. will be added to the bid price. If the drop below the norm or the excess above the minimum acceptable levels is less than one percent, the adjustment will be prorated accordingly.

1.3.5 Work, Services, Facilities, etc., to be provided by the Employer

Where bids include the undertaking of work or the provision of services or facilities by the Employer in excess of the provisions allowed for in the Bidding Document, the Employer shall assess the costs of such additional work, services and/or facilities during the duration of the contract. Such costs shall be added to the Bid Price for evaluation.

1.3.6 Specific Additional Criteria

The following additional criteria will be used in the evaluation:

##### 1.4 Multiple Contracts (ITB 36.6 (for Two-envelope; substitute ITB 38.4))

If in accordance with ITB 1.1, Bids are invited for more than one lot, the contract will be awarded to the Bidder or Bidders offering a substantially responsive Bid(s) and the lowest evaluated cost to the Employer for combined lots, subject to the selected Bidder(s) meeting the required qualification criteria Section III, Evaluation and Qualification Criteria for a lot or combination of lots as the case may be.

In determining Bidder or Bidders that offer the total lowest evaluated cost to the Employer, after considering all possible combination of lots, the Employer shall apply the following steps in sequence:

    - evaluate individual lots to determine the substantially responsive Bids and corresponding evaluated costs;

    - for each lot, rank the substantially responsive Bids starting from the lowest evaluated cost for the lot;

    - apply to the evaluated costs listed in b) above, any applicable discounts/price reductions offered by a Bidder (s) for the award of multiple contracts based on the discounts and the methodology for their application offered by the respective Bidder; and

    - determine contract award on the basis of the combination of lots that offer the total lowest evaluated cost to the Employer.

#### 2. Qualification

##### 2.1 Eligibility

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | JVA |  |  | Submission Requirements |
|  |  | All Partners Combined* | Each Partner | One Partner |  |

* “All Partners Combined” does not take into consideration the shareholding ratio of each partner under the joint venture agreement for this bid when assessing compliance with each requirement listed below. [If this approach is not applicable, please specify the method by which the shareholding ratio will be reflected].

2.1.1 Nationality

| Nationality in accordance with ITB 4.2. | Must meet requirement | Existing or intended JVA Must meet requirement | Must meet requirement | Not applicable | Forms ELI - 1; ELI - 2 with attachments |
| --- | --- | --- | --- | --- | --- |

2.1.2 Conflict of Interest

| No conflicts of interest in accordance with ITB 4.3. | Must meet requirement | Existing or intended JVA Must meet requirement | Must meet requirement | Not applicable | Letter of Bid (for Two-envelope; substitute Letter of Technical Bid) |
| --- | --- | --- | --- | --- | --- |

2.1.3 EDCF Eligibility

| Not having been declared ineligible by the Bank, as described in ITB 4.4. | Must meet requirement | Existing or intended JVA Must meet requirement | Must meet requirement | Not applicable | Letter of Bid (for Two-envelope; substitute Letter of Technical Bid) |
| --- | --- | --- | --- | --- | --- |

2.1.4 Government-Owned Entity

| Bidder required to meet conditions of ITB 4.5. | Must meet requirement | Must meet requirement | Must meet requirement | Not applicable | Forms ELI - 1; ELI - 2 with attachments |
| --- | --- | --- | --- | --- | --- |

##### 2.2 Historical Contract Non-Performance

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | JVA |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |

2.2.1 Suspension

| Not under suspension based on execution of a Bid Securing Declaration or Proposal Securing Declaration pursuant to ITB 4.6 and ITB 21.9 | Must meet requirement | Must meet requirement | Must meet requirement | Not applicable | Letter of Bid (for Two-envelope; substitute Letter of Technical Bid) |
| --- | --- | --- | --- | --- | --- |

2.2.2 Pending Litigation

| All pending litigation shall be treated as resolved against the Bidder and so shall in total not represent more than [insert figure. The percentage should normally be written the range of 50% to 100% of a Bidder’s net worth] ------- percent (---%) of the Bidder’s net worth. | Must meet requirement by itself or as partner to past or existing JVA | Not Applicable | Must meet requirement by itself or as partner to past or existing JVA | Not applicable | Form CON - 1 |
| --- | --- | --- | --- | --- | --- |

##### 2.3 Financial Situation

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | JVA |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |

2.3.1 Historical Financial Performance

| Submission of audited balance sheets or, if not required by the law of the Bidder’s country, other financial statements acceptable to the Employer, for the last [Insert number of years in words and figures. The time period should not be less than three (3) years.] ______________ [ ] years to demonstrate the current soundness of the Bidders financial position and its prospective long-term profitability. As a minimum, a Bidder's net worth calculated as the difference between total assets and total liabilities should be positive. | Must meet requirement | Not applicable | Must meet requirement | Not applicable | Form FIN - 1 with attachments |
| --- | --- | --- | --- | --- | --- |

* The financial information provided by a Bidder should be reviewed in its entirety to allow a truly informed judgment, and the pass-fail decision on the financial position of the Bidder should be given on this basis. Any abnormal features which may lead to financial problems should alert the Employer to seek expert professional advice for further review and interpretation.

2.3.2 Average Annual Turnover

| Minimum average annual turnover in [insert the appropriate sector] of US$ [Insert US Dollar amount. The amount stated should normally not be less than 2 x V/T, the estimated annual turnover in the subject contract based on a straight-line projection of the Employer’s estimated cost(V), including contingencies, over the contract duration(T). The multiplier of two may be reduced for very large contracts but should not be less than 1.5.] ________________ calculated as total certified payments received for contracts in progress or completed, within the last [Insert number of years in words and figures. The time period is normally three (3) years or more] ______________ [ ] years. | Must meet requirement | Must meet requirement | Must meet [Insert percentage figure, usually 25%] ___ percent (__%) of the requirement | Must meet [Insert percentage figure, usually 40%] ___ percent (__%) of the requirement | Form FIN - 2 |
| --- | --- | --- | --- | --- | --- |

2.3.3 Financial Resources

| The Bidder must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, lines of credit, and other financial means, other than any contractual advance payments to meet: - the following cash-flow requirement: ……………………………… and - the overall cash flow requirements for this contract and its current commitments. | Must meet requirement | Must meet requirement | Must meet ___ percent (__%) of the requirement | Must meet ___ percent (__%) of the requirement | Form FIN – 3 and Form FIN – 4 |
| --- | --- | --- | --- | --- | --- |

* Indicate under (1) above the cash flow requirement for a number of months (to the nearest half-month), determined as the total time needed by the Employer to pay a contractor’s invoice, allowing for (a) the actual time consumed for construction, from the beginning of the month invoiced, (b) the time needed by the Engineer to issue the monthly payment certificate, (c) the time needed by the Employer to pay the amount certified, and (d) a contingency period of one month to allow for unforeseen delays. The total period should not exceed six months. The assessment of the monthly amount should be based on a straight-line projection of the estimated cash flow requirement over the particular contract period, neglecting the effect of any advance payment and retention monies, but including contingency allowances in the estimated contract cost.

##### 2.4 Experience

| Criteria | Compliance Requirements |  |  |  | Documents |
| --- | --- | --- | --- | --- | --- |
| Requirement | Single Entity | JVA |  |  | Submission Requirements |
|  |  | All Partners Combined | Each Partner | One Partner |  |

2.4.1 General Experience

| Experience in [insert appropriate sector] under contracts in the role of contractor, subcontractor, or management contractor for at least the last [Insert number of years in words and figures. The time period is normally five (5) years, but may be reduced to not less than three (3) years, in agreement with the Bank under special country circumstances such as to provide opportunities for a newly privatized industry with only a short record of experience.] ______________ [ ] years prior to the applications submission deadline. | Must meet requirement | Not applicable | Must meet requirement | Not applicable | Form EXP - 1 |
| --- | --- | --- | --- | --- | --- |

2.4.2 Specific Experience

(a) Contracts of Similar Size and Nature

| Participation as contractor, management contractor, or subcontractor, in at least [Insert number of contracts. The range should be one to three, depending on the size, value, nature, complexity of the subject contract, the exposure of the Employer to risk of contractor default, country conditions and history of similar works constructed in the past. For contracts in a developed environment with a high potential supply of construction services, three similar contracts may not limit applications, but would reduce the risk of contractor default] ____ contracts within the last [Insert number of years in words and figures. The range is normally five to ten years, and should be related to the number of similar contracts stated above and to the duration of the subject contract, e.g., ten years for two contracts of about five years’ duration, or six years for two contracts of about three years’ duration] ________ [ ] years, each with a value of at least US$ [Insert US Dollar amount, usually 80% of the estimated value of the subject contract] ________ (_________) that have been successfully or are substantially completed* and that are similar to the Plant and Installation Services. The similarity shall be based on the physical size, complexity, methods, technology and/or other characteristics as described in Section VI (Employer’s Requirements). | Must meet requirement | Must meet requirement | Not applicable | Not applicable | Form EXP - 2(a) |
| --- | --- | --- | --- | --- | --- |

* “Successfully completed” means that the work or project has met all the contractual requirements, including passing any specified tests and inspections. “Substantially completed” refers to the project being sufficiently complete to be used as intended, allowing for minor works to be completed later. In addition to the submission requirement Form EXP – 2, the Bidder shall provide the following supporting documents:

[If the Employer will consider a “Successfully or substantially completed contract” as one in which the works have been completed, insert the following text:

1. abstracts of signed contract agreements including JV agreements, and

2. Taking-Over Certificate, Contract Completion Certificate, Performance Certificate, or equivalent certificate issued by the employer of each contract or by the International Contractors Association of Korea.

,

in sufficient detail to verify the contract name, value and completion time (or substantial completion). If the documents are other than in English, an accurate certified translation of these documents in English shall be provided.]

[If the Employer will consider a “Successfully or substantially completed contract” as one in which the Contractor has completed all its obligations under the contract, insert the following text:

1. abstracts of signed contract agreement including JV agreements, and

2. Contract Completion Certificate, Performance Certificate, or equivalent certificate issued by the employer of each contract or by the International Contractors Association of Korea

,

in sufficient detail to verify the contract name, value and completion time. If the documents are other than in English, an accurate certified translation of these documents in English shall be provided.]

(b) Experience in Key Activities

| For the above or other contracts executed during the period stipulated in 2.4.2(a) above, a minimum experience in the following key activities: [Indicate, if any, of these key requirements may also be met through a specialist subcontractor.] | Must meet all requirements (can be a specialist Subcontractor) | Must meet all requirements (can be a specialist Subcontractor) | Not applicable | Not applicable | Form EXP - 2(b) |
| --- | --- | --- | --- | --- | --- |
| [List activities, as applicable] |  |  |  |  |  |

##### 2.5 Personnel

The Bidder must demonstrate that it has the personnel for the key positions that meet the following requirements.

| No. | Position | Total Work Experience (years) | Experience in Similar Position (years) |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| … |  |  |  |

The Bidder shall provide details of the proposed personnel and their experience records in the relevant Information Forms included in Section IV (Bidding Forms).

<<Notes for the Employer>>

The managerial and technical competence of a contractor is largely related to the key personnel on site. The extent to which the Bidder should demonstrate having staff with extensive experience should be limited to those requiring critical operational or technical skills. The qualification criteria should therefore refer to a limited number of such key personnel, for instance, the project or contract manager and those superintendents working under the project manager who will be responsible for major components (e.g., superintendents specialized in dredging, piling, tunneling, or earthworks, as required for each particular project).

Bidders should normally be required to name a principal candidate and an alternate for each key position. Criteria of acceptability should be based on:

(a) a minimum number of years of experience in a similar position; and

(b) a minimum number of years of experience and/or number of comparable projects carried out in a specified number of preceding years.

The requirement of specified education and academic qualifications is normally unnecessary for such positions, as contractors often employ competent staffs who have learned their profession “on the job” rather than through academic training.

It is appropriate to specify that certain positions are filled by individuals who have held posts of comparable authority for, say, three (3) years with the Bidder, so that key staffs in executive site positions have sufficient knowledge of the Bidder's management, policy, procedures, and practices to act with confidence and authority within that framework.

##### 2.6 Equipment

The Bidder must demonstrate that it has the key equipment listed hereafter.

| No. | Equipment Type and Characteristics | Min. Number required |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |

The Bidder shall provide further details of proposed items of equipment using the relevant Form in Section IV (Bidding Forms).

The Bidder shall own, or have assumed access (through hire, lease, purchase agreement, other commercial means, or approved subcontracting) to key items of equipment, in full working order, and must demonstrate that based on known commitments, they will be available for timely use in the proposed contract.

<<Notes for the Employer>>

An inventory of construction equipment represents a high capital cost overhead to a contractor. Consequently, not all competent potential bidders will maintain an inventory of high-value items that are in suitable condition for major contracts. This is particularly so with management contractors, who undertake construction projects mainly by subcontracting. In most cases Bidders can readily purchase, lease, or hire equipment; thus, it is usually unnecessary for the assessment of a contractor's qualification to depend on the contractor’s owning readily available items of equipment. The pass–fail criteria adopted should therefore be limited only to those bulky or specialized items that are critical for the type of project to be implemented, and that may be difficult for the contractor to obtain quickly. Examples may include items such as heavy lift cranes and piling barges, dredgers, tunnel boring machines, asphalt mixing plants, etc. Even in such cases, contractors may not own the specialized items of equipment, and may rely on specialist subcontractors or equipment–hire firms. The availability of such subcontractors and of the specified equipment should be subject to verification prior to contract award. The terms of any lease or hire agreement for equipment should preferably include a provision that the equipment will remain on the site (or be vested in the Employer) in the event of default of the Contractor, thereby ensuring more timely continuity of work by a replacement contractor.

##### 2.7 Subcontractors/manufacturers

Subcontractors/manufacturers for the following additional major items of supply or services (‘Specialist Subcontractors’) must meet the following minimum criteria, herein listed for that item:

<<Notes for the Employer>>

The minimum criteria should be established only for major items of supply or services, not for general items. Specifically, for subcontractors, the minimum criteria should apply only to subcontractors performing a specific type of work, rather than to all subcontractors.

| Item No. | Description of Item | Minimum Criteria to be met |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| … |  |  |

Failure to comply with this requirement will result in the rejection of the Subcontractor. Should a manufacturer or subcontractor be determined to be unacceptable, the Bid will not be rejected, but the Bidder will be required to propose, without changing its bid price, an acceptable substitute manufacturer or subcontractor meeting the minimum criteria in accordance with ITB 35.4.

In the case of a Bidder who offers to supply and install major items of supply under the Contract that the Bidder did not manufacture or otherwise produce, the Bidder shall provide the manufacturer’s authorization, using the form provided in Section IV (Bidding Forms), showing that the Bidder has been duly authorized by the manufacturer or producer of the related plant and equipment or component to supply and/or install that item in the Employer’s country. Failure to submit the Manufacturer’s authorization at the first instance is considered a minor, nonmaterial omission and shall be subject to clarification. However, failure of the Bidder to submit the omitted authorization shall lead to rejection of the Subcontractor or Manufacturer of the item under evaluation in accordance with ITB 37.4 (for Two-envelope; substitute ITB 35.4).

Section IV. Bidding Forms
(Following Prequalification)

This section contains the forms to be completed by the Bidder and submitted as part of its Bid.

Table of Forms

Letter of Bid (Single-Stage One-Envelope Bidding Procedure)	110

Letter of Technical Bid (Single-Stage Two-Envelope Bidding Procedure)	113

Letter of Price Bid (Single-Stage Two-Envelope Bidding Procedure)	115

Price Schedules	117

Schedule No. 1: Plant and Mandatory Spare Parts Supplied from Abroad	119

Schedule No. 2:  Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country	120

Schedule No. 3:  Design Services	121

Schedule No. 4:  Installation and Other Services	122

Schedule No. 5:  Grand Summary	123

Schedule No. 6:  Recommended Spare Parts	124

Tables of Adjustment Data	125

Form of Bid Security (Bank Guarantee)	126

Form of Bid Security (Bid Bond)	128

Form of Bid-Securing Declaration	130

Technical Proposal	132

Site Organization	133

Method Statement	134

Mobilization Schedule	135

Construction Schedule	136

Plant		137

Safety Plan	138

Personnel	139

Contractor’s Equipment	141

Proposed Subcontractors and/or Manufacturers for Major Items of Plant and

Installation Services	142

Manufacturer's Authorization	143

Time Schedule	144

Functional Guarantee of the Proposed Facilities	145

Updating of Bidders Qualification	146

Form ELI – 1: Bidder’s Information Sheet	147

Form ELI – 2: Party to JVA Information Sheet	148

Form CON – 1: Historical Contract Non-Performance and Pending Litigation	149

Form FIN – 1: Financial Situation and Performance	151

Form FIN – 2: Average Annual Turnover	153

Form FIN - 3: Availability of Financial Resources	154

Form FIN - 4: Financial Requirements for Current Contract Commitments	155

Form FIN – 5: Self-Assessment Tool for Bidder’s Compliance to Financial

Resources(Criterion 2.2 of Section III)	156

Declaration of Participation in Economic Development Cooperation Fund (EDCF) Financed Projects	157

Letter of Bid

(Single-Stage One-Envelope Bidding Procedure)

Date:

CB No.:

Invitation for Bid No.:

To: [insert full name of Employer],

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB) 8.

- We, including any Subcontractors/manufacturers, for any part of the Contract, meet the eligibility requirements in accordance with ITB 4 and ITB 5.

- We, including any Subcontractors/manufacturers, for any part of the Contract, have no conflict of interests in accordance with ITB 4.

- We offer to [insert the services that apply, i.e., design, manufacture, test, deliver, install, precommission and commission], in conformity with the Bidding Documents, the following Plant and Installation Services: [insert a brief description of the Plant and Installation Services]

[Amount of foreign currency in words], [amount in figures], and [amount of local currency in words], [amount in figures]

The total bid price from the Grand Summary (Schedule No. 5) should be entered by the Bidder inside this box. Absence of the total bid price in the Letter of Bid may result in the rejection of the bid.

The total price of our Bid, excluding any discounts offered in item (f) below is the sum of

- The discounts offered and the methodology for their application are as follows: [insert discounts and methodology for their application if any]

- Our Bid shall be valid for a period of [insert bid validity period as specified in ITB 20.1 of the BDS] days from the date fixed for the bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period.

- If our Bid is accepted, we commit to obtain a performance security in accordance with the Bidding Documents.

- We are not participating, as a Bidder, either individually or as partner in a JVA, in more than one Bid in this bidding process in accordance with ITB 4.3(e), other than alternative offers submitted in accordance with ITB 13.

- We are not subject to, or not controlled by any entity or individual that is subject to, a sanction imposed by the Bank or any sanction in accordance with ‘Act on Contracts to which the State is a Party’ and ‘Regulation on Contracts to which the Public enterprise is a Party’ of the Republic of Korea or a cross debarment imposed by Multilateral Development Banks (MDBs).

- [select the appropriate option and delete the other] [We are not a government-owned enterprise] / [We are a government-owned enterprise but meet the requirements of ITB 4.5]

- We have not been suspended nor declared ineligible by the Employer based on execution of a Bid-Securing Declaration in the Employer’s Country in accordance with ITB 4.6.

- We understand that this Bid, together with your written acceptance thereof included in your notification of award, shall constitute a binding contract between us, until a formal contract is prepared and executed.

- We understand that you are not bound to accept the lowest evaluated Bid or any other Bid that you may receive.

- We agree to permit the Bank or its representative to inspect our accounts and records and other documents relating to the bid submission and to have them audited by auditors appointed by the Bank.

- If our Bid is accepted, we commit to mobilizing key equipment and personnel in accordance with the requirements set forth in Section VI (Employer’s Requirements) and our technical proposal, or as otherwise agreed with the Employer.

- We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf will engage in any type of fraud and corruption.

Name of the Bidder*: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder**: [insert complete name of the person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above: [insert signature of person whose name and capacity are shown above]

Date signed [insert date of signing] day of [insert month], [insert year]

* In the case of the Bid submitted by JVA specify the name of the JVA as Bidder.

** Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid.

Letter of Technical Bid

(Single-Stage Two-Envelope Bidding Procedure)

Date:

CB No.:

Invitation for Bid No.:

To: [insert full name of Employer],

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB) 8.

- We, including any Subcontractors/manufacturers, for any part of the Contract, meet the eligibility requirements in accordance with ITB 4 and ITB 5.

- We, including any Subcontractors/manufacturers, for any part of the Contract, have no conflict of interests in accordance with ITB 4.

- We offer to [insert the services that apply, i.e., design, manufacture, test, deliver, install, precommission and commission], in conformity with the Bidding Documents, the following Plant and Installation Services: [insert a brief description of the Plant and Installation Services]

- Our Bid consisting of the Technical Bid and the Price Bid shall be valid for a period of [insert bid validity period as specified in ITB 20.1 of the BDS] days from the date fixed for the bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period.

- We are not participating, as a Bidder, either individually or as partner in a JVA, in more than one Bid in this bidding process in accordance with ITB 4.3(e), other than alternative offers submitted in accordance with ITB 13.

- We are not subject to, or not controlled by any entity or individual that is subject to, a sanction imposed by the Bank or any sanction in accordance with ‘Act on Contracts to which the State is a Party’ and ‘Regulation on Contracts to which the Public enterprise is a Party’ of the Republic of Korea or a cross debarment imposed by Multilateral Development Banks (MDBs).

- [select the appropriate option and delete the other] [We are not a government-owned enterprise] / [We are a government-owned enterprise but meet the requirements of ITB 4.5]

- We have not been suspended nor declared ineligible by the Employer based on execution of a Bid-Securing Declaration in the Employer’s Country in accordance with ITB 4.6.

- We agree to permit the Bank or its representative to inspect our accounts and records and other documents relating to the bid submission and to have them audited by auditors appointed by the Bank.

- If our Bid is accepted, we commit to mobilizing key equipment and personnel in accordance with the requirements set forth in Section VI (Employer’s Requirements) and our technical proposal, or as otherwise agreed with the Employer.

- We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf will engage in any type of fraud and corruption.

Name of the Bidder*: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder**: [insert complete name of the person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above: [insert signature of person whose name and capacity are shown above]

Date signed [insert date of signing] day of [insert month], [insert year]

* In the case of the Bid submitted by JVA specify the name of the JVA as Bidder.

** Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid.

Letter of Price Bid

(Single-Stage Two-Envelope Bidding Procedure)

Date:

CB No.:

Invitation for Bid No.:

To: [insert full name of Employer],

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB) 8.

- We, including any Subcontractors/manufacturers, for any part of the Contract, meet the eligibility requirements in accordance with ITB 4 and ITB 5.

- We, including any Subcontractors/manufacturers, for any part of the Contract, have no conflict of interests in accordance with ITB 4.

- We offer to [insert the services that apply, i.e., design, manufacture, test, deliver, install, precommission and commission], in conformity with the Bidding Documents, the following Plant and Installation Services: [insert a brief description of the Plant and Installation Services]

[Amount of foreign currency in words], [amount in figures], and [amount of local currency in words], [amount in figures]

The total bid price from the Grand Summary (Schedule No. 5) should be entered by the Bidder inside this box. Absence of the total bid price in the Letter of Bid may result in the rejection of the bid.

The total price of our Bid, excluding any discounts offered in item (f) below is the sum of

- The discounts offered and the methodology for their application are as follows: [insert discounts and methodology for their application if any]

- Our Bid consisting of the Technical Bid and the Price Bid shall be valid for a period of [insert bid validity period as specified in ITB 20.1 of the BDS] days from the date fixed for the bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period.

- If our Bid is accepted, we commit to obtain a performance security in accordance with the Bidding Documents.

- We understand that this Bid, together with your written acceptance thereof included in your notification of award, shall constitute a binding contract between us, until a formal contract is prepared and executed.

- We understand that you are not bound to accept the lowest evaluated Bid or any other Bid that you may receive.

- We agree to permit the Bank or its representative to inspect our accounts and records and other documents relating to the bid submission and to have them audited by auditors appointed by the Bank.

Name of the Bidder*: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder**: [insert complete name of the person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above: [insert signature of person whose name and capacity are shown above]

Date signed [insert date of signing] day of [insert month], [insert year]

* In the case of the Bid submitted by JVA specify the name of the JVA as Bidder.

** Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid.

Price Schedules

PREAMBLE

General

1.	The Price Schedules are divided into separate Schedules as follows:

Schedule No. 1:	Plant and Mandatory Spare Parts Supplied from Abroad

Schedule No. 2:	Plant and Mandatory Spare Parts Supplied from within the Employer’s Country

Schedule No. 3:	Design Services

Schedule No. 4:	Installation and Other Services

Schedule No. 5:	Grand Summary

Schedule No. 6:	Recommended Spare Parts

2.	The Schedules do not generally give a full description of the Plant to be supplied and the Installation Services to be performed under each item. Bidders shall be deemed to have read the Employer’s Requirements and other sections of the Bidding Document and reviewed the Drawings to ascertain the full scope of the requirements included in each item prior to filling in the rates and prices. The entered rates and prices shall be deemed to cover the full scope as aforesaid, including overheads and profit.

3.	If Bidders are unclear or uncertain as to the scope of any item, they shall seek clarification in accordance with ITB 7 prior to submitting their bid.

Pricing

4.	The units and rates in figures entered into the Price Schedules should be typewritten or if written by hand, must be in print form. Price Schedules not presented accordingly may be considered nonresponsive. Any alterations necessary due to errors, etc., shall be initialed by the Bidder.

As specified in the Bid Data Sheet and Particular Conditions of Contract, prices shall be fixed and firm for the duration of the Contract, or prices shall be subject to adjustment in accordance with the corresponding Appendix (Price Adjustment) to the Contract Agreement.

5.	Bid prices shall be quoted in the manner indicated and in the currencies specified in the Instructions to Bidders in the Bidding Document.

For each item, Bidders shall complete each appropriate column in the respective Schedules, giving the price breakdown as indicated in the Schedules.

Prices given in the Schedules against each item shall be for the scope covered by that item as detailed in Section VI (Employer’s Requirements) or elsewhere in the Bidding Document.

6.	Payments will be made to the Contractor in the currency or currencies indicated under each respective item.

7.	When requested by the Employer for the purposes of making payments or partial payments, valuing variations or evaluating claims, or for such other purposes as the Employer may reasonably require, the Contractor shall provide the Employer with a breakdown of any composite or lump sum items included in the Schedules.

Schedules of Rates and Prices

##### Schedule No. 1: Plant and Mandatory Spare Parts Supplied from Abroad

| Item | Description | Country of Origin | Quantity | Unit Pricea |  | Total Pricea | Taxes and Duties |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Foreign Currency | CIP | Foreign Currency | Local Currency |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 = 4 x 6 | 8 |
| TOTAL Column 7 to be carried forward to Schedule No. 5: Grand Summary |  |  |  |  |  |  |  |
| Name of Bidder |  |  |  |  |  |  |  |
| Signature of Bidder |  |  |  |  |  |  |  |

a 	Specify currencies in accordance with ITB 19.1 of the BDS. Create additional columns for foreign currencies if so required.

Country of Origin Declaration Form

| Item | Description | Country |
| --- | --- | --- |

##### Schedule No. 2:  Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country

| Item | Description | Quantity | Unit Pricea |  | Total EXW Pricea | Sales and other taxes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Local Currency | EXW Priceb |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 = 3 x 5 | 7 |
| TOTAL Column 6 to be carried forward to Schedule No. 5: Grand Summary |  |  |  |  |  |  |
| Name of Bidder |  |  |  |  |  |  |
| Signature of Bidder |  |  |  |  |  |  |

a    Specify currency in accordance with ITB 19.1 of the BDS.

b     Column 5  EXW Price shall include all customs duties and sales and other taxes already paid or payable on the components and raw materials used in the manufacture or assembly of the item or the customs duties and sales and other taxes already paid on previously imported items.

##### Schedule No. 3:  Design Services

| Item | Description | Quantity | Unit Pricea |  | Total Pricea |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Local Currency Portion | Foreign Currency Portion | Local Currency Portion | Foreign Currency Portion |
| 1 | 2 | 3 | 4 | 5 | 6 = 3 x 4 | 7 = 3 x 5 |
| TOTAL Columns 6 and 7 to be carried forward to Schedule No. 5: Grand Summary |  |  |  |  |  |  |
| Name of Bidder |  |  |  |  |  |  |
| Signature of Bidder |  |  |  |  |  |  |

a 	Specify currency in accordance with ITB 19.1 of the BDS.

##### Schedule No. 4:  Installation and Other Services

| Item | Description | Quantity | Unit Pricea |  | Total Pricea |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Local Currency Portion | Foreign Currency Portion | Local Currency Portion | Foreign Currency Portion |
| 1 | 2 | 3 | 4 | 5 | 6 = 3 x 4 | 7 = 3 x 5 |
| TOTAL Columns 6 and 7 to be carried forward to Schedule No. 5: Grand Summary |  |  |  |  |  |  |
| Name of Bidder |  |  |  |  |  |  |
| Signature of Bidder |  |  |  |  |  |  |

a 	Specify currency in accordance with ITB 19.1 of the BDS.

##### Schedule No. 5:  Grand Summary

| Schedule No. | Title | Total Pricea |  |
| --- | --- | --- | --- |
|  |  | Foreign | Local |
| 1 | Plant and Mandatory Spare Parts Supplied from Abroad b |  |  |
| 2 | Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country b |  |  |
| 3 | Design Services |  |  |
| 4 | Installation and Other Services |  |  |
| Grand Total to be carried forward to Letter of Bid |  |  |  |
| Name of Bidder |  |  |  |
| Signature of Bidder |  |  |  |

a 		Specify currency in accordance with ITB 19.1 of the BDS. Create additional columns for  foreign currencies if so required.

b   	Taxes and/or duties from Schedules 1 and 2 may be added to the contract price in accordance with GC 14 (Taxes and Duties) but excluded from bid evaluation in accordance with ITB 36.4 (for Two-envelope; substitute ITB 38.2).

##### Schedule No. 6:  Recommended Spare Parts

| Item | Description | Quantity | Unit Pricea |  | Total Pricea |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | EXW Local Parts Local Currency | CIP Imported Parts Foreign Currency | Local Currency Portion | Foreign Currency Portion |
| 1 | 2 | 3 | 4 | 5 | 6 = 3 x 4 | 7 = 3 x 5 |
| TOTAL |  |  |  |  |  |  |
| Name of Bidder |  |  |  |  |  |  |
| Signature of Bidder |  |  |  |  |  |  |

a 	Specify currency in accordance with ITB 19.1 of the BDS.

Tables of Adjustment Data

Table A - Local Currency

| Index Code |  |  | Index Description |  |  | Source of Index |  |  | Base Value and Date |  | Bidder’s Local Currency Amount |  | Bidder’s Proposed Weighting |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Nonadjustable |  |  | --- |  |  | --- |  | --- |  | a: b: c: d: e: _________ |  |
|  |  |  |  |  |  |  | Total |  |  |  |  | 1.00 |  |  |

Table B - Foreign Currency

Name of Currency: _____________________________________________________________________.

[Insert name of currency. If the Bidder wishes to quote in more than one foreign currency, this table should be repeated for each foreign currency.]

| Index Code |  |  | Index Description |  | Source of Index |  |  |  | Base Value and Date |  |  | Bidder’s Currency in Type/Amount |  |  | Equivalent in FC1 |  |  | Bidder’s Proposed Weighting |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Nonadjustable |  |  | --- |  |  | --- |  |  | --- |  |  |  | a: b: c: d: e: _________ |  |
|  |  |  |  |  |  |  |  |  |  |  | Total |  |  |  |  | 1.00 |  |  |  |

<<Note>>

The base date shall be the date 28 days prior to the deadline for submission of the bid.

Tables of Adjustment Data shall only be included if prices are to be quoted as adjustable prices in accordance with ITB 18.6.

Form of Bid Security

(Bank Guarantee)

__________________________  [Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:  __________________________ [Name and Address of Employer]

Date:  __________________________

Bid Security No.: __________________________

We have been informed that __________________________ [name of the Bidder] (hereinafter called "the Bidder") has submitted to you its bid dated  ___________ (hereinafter called "the Bid") for the execution of ________________ [name of contract]  under Invitation for Bids No. ___________ (“the IFB”).

Furthermore, we understand that, according to your conditions, bids must be supported by a bid guarantee.

At the request of the Bidder, we ____________________ [name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of ___________ [amount in figures]  (____________) [amount in words]  upon receipt by us of your first demand in writing accompanied by a written statement stating that the Bidder is in breach of its obligation(s) under the bid conditions, because the Bidder:

(a) 	has withdrawn its Bid prior to the Bid validity expiry date set forth in the Applicant’s Letters of Technical and Price Bid (for One-envelope; substitute the Letter of Bid), or any extended date provided by the Applicant; or

(b) 	having been notified of the acceptance of its Bid by the Beneficiary prior to the expiry date of the Bid validity or any extension thereto provided by the Applicant, (i) has failed to execute the Contract Agreement, or (ii) has failed to furnish the Performance Security, in accordance with the Instructions to Bidders (“ITB”) of the Beneficiary’s bidding document.

This guarantee will expire: (a) if the Bidder is the successful Bidder, upon our receipt of copies of the Contract Agreement signed by the Bidder and the Performance Security issued to you upon the instruction of the Bidder; or (b) if the Bidder is not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification to the Bidder of the name of the successful Bidder, or (ii) twenty-eight (28) days after the expiration of the Bidder’s bid.

Consequently, any demand for payment under this guarantee must be received by us at the office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 revision, ICC Publication No. 758.

___________________________________

[Banker’s seal and authorized signature(s)]

Note: All italicized text is for use in preparing this form and shall be deleted from the final product.

Form of Bid Security

(Bid Bond)

BOND NO. ______________________

BY THIS BOND [insert name of Bidder] as Principal (hereinafter called “the Principal”), and [insert name, legal title, and address of surety], authorized to transact business in [insert name of country of Employer], as Surety (hereinafter called “the Surety”), are held and firmly bound unto [insert name of Employer] as Obligee (hereinafter called “the Employer”) in the sum of [insert amount of Bond in words and figures], for the payment of which sum, well and truly to be made, we, the said Principal and Surety, bind ourselves, our successors and assigns, jointly and severally, firmly by these presents.

WHEREAS the Principal has submitted a written Bid to the Employer dated the day of ______, 20__, for the construction of [insert name of Contract] (hereinafter called the “Bid”).

NOW, THEREFORE, THE CONDITION OF THIS OBLIGATION is such that if the Principal:

- withdraws its Bid prior to the bid validity expiry date set forth in the Principal’s Letters of Technical and Price Bid (for One-envelope; substitute the Letter of Bid), or any extended date provided by the Principal; or

- having been notified of the acceptance of its Bid by the Employer prior to the expiry date of the Bid validity or any extension thereto provided by the Principal,; (i) fails or refuses to execute the Contract Form, if required; or (ii) fails or refuses to furnish the Performance Security in accordance with the Instructions to Bidders,

then the Surety undertakes to immediately pay to the Employer up to the above amount upon receipt of the Employer’s first written demand, without the Employer having to substantiate its demand, provided that in its demand the Employer shall state that the demand arises from the occurrence of any of the above events, specifying which event(s) has occurred.

The Surety hereby agrees that its obligation will remain in full force and effect up to and including the date 28 days after the date of expiration of the Bid validity set forth in the Principal’s Letters of Technical and Price Bid (for One-envelope; substitute the Letter of Bid) or any extension thereto provided by the Principal.

IN TESTIMONY WHEREOF, the Principal and the Surety have caused these presents to be executed in their respective names this ____ day of ____________ 20__.

Principal: _______________________	Surety: _____________________________
	Corporate Seal (where appropriate)

_______________________________	____________________________________
(Signature)	(Signature)

(Printed name and title)	                        (Printed name and title)

Form of Bid-Securing Declaration

Date: [insert date (as day, month and year)]

Bid No.: [insert number of bidding process]

Alternative No.: [insert identification No if this is a bid for an alternative]

To: [insert complete name of the Employer]

We, the undersigned, declare that:

We understand that, according to your conditions, Bids must be supported by a Bid-Securing Declaration.

We accept that we will automatically be suspended from being eligible for bidding in any contract with the Borrower for the period of time of [insert number of years as indicated in ITB 21.1 of the BDS] starting on the date that we receive a notification from the Employer, if we are in breach of our obligation(s) under the bid conditions, because we

- have withdrawn our Bid prior to the expiry date of the Bid validity specified in the Letters of Technical and Price Bid (for One-envelope; substitute the Letter of Bid) or any extended date provided by us; or

- having been notified of the acceptance of our Bid by the Employer prior to the expiry date of the Bid validity in the Letter of Bid or any extended date provided by us, (i) fail or refuse to execute the Contract, if required, or (ii) fail or refuse to furnish the Performance Security, in accordance with the ITB.

We understand that this Bid-Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of your notification to us of the name of the successful Bidder; or (ii) twenty-eight (28) days after the expiration of our Bid.

Name of the Bidder*

Name of the person duly authorized to sign the Bid on behalf of the Bidder**___________

Title of the person signing the Bid______________________________________________

Signature of the person named above____________________________________________

Date signed ________________________________ day of ___________________, ______

Corporate Seal (where appropriate)

`

*: In the case of the Bid submitted by joint venture specify the name of the Joint Venture as Bidder

**: Person signing the Bid shall have the power of attorney given by the Bidder attached to the Bid

[Note: In case of a Joint Venture, the Bid-Securing Declaration must be in the name of all members to the Joint Venture that submits the Bid.]

Technical Proposal

- Site Organization

- Method Statement

- Mobilization Schedule

- Construction Schedule

- Plant

- Safety Plan

- Personnel

- Contractor’s Equipment

- Proposed Subcontractors/Manufacturers for Major Items of Plant and Installation Services

- Manufacturer’s Authorization

- Time Schedule

- Functional Guarantee of the Proposed Facilities

##### Site Organization

##### Method Statement

##### Mobilization Schedule

##### Construction Schedule

##### Plant

##### Safety Plan

##### Personnel

Form PER – 1: Proposed Personnel

Bidders should provide the names of suitably qualified personnel to meet the specified requirements stated in Section III (Evaluation and Qualification Criteria). The data on their experience should be supplied using the Form below for each candidate.

| 1. | Title of position |
| --- | --- |
|  | Name |
| 2. | Title of position |
|  | Name |
| 3. | Title of position |
|  | Name |
| 4. | Title of position |
|  | Name |

[Note: All titles of positions will be as listed in Section VI (Employer’s Requirements).]

Form PER – 2:  Resume of Proposed Personnel

The Bidder shall provide all the information requested below. Use one form for each position.

| Position |  |  |
| --- | --- | --- |
| Personnel information | Name | Date of birth |
|  | Professional qualifications |  |
| Present employment | Name of employer |  |
|  | Address of employer |  |
|  | Telephone | Contact (manager/personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present employer |

Summarize professional experience over the last twenty (20) years, in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

| ### From | ### To | ### Company/Project/Position/Relevant Technical and Management Experience |
| --- | --- | --- |

##### Contractor’s Equipment

Form EQU:  Equipment

The Bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key equipment listed in Section III (Evaluation and Qualification Criteria). A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the Bidder.

| Item of equipment |  |  |
| --- | --- | --- |
| Equipment information | Name of manufacturer | Model and power rating |
|  | Capacity | Year of manufacture |
| Current status | Current location |  |
|  | Details of current commitments |  |
| Source | Indicate source of the equipment o Owned o Rented o Leased o Specially manufactured |  |

Omit the following information for equipment owned by the Bidder.

| Owner | Name of owner |  |
| --- | --- | --- |
|  | Address of owner |  |
|  | Telephone | Contact name and title |
|  | Fax | Telex |
| Agreements | Details of rental / lease / manufacture agreements specific to the project |  |

##### Proposed Subcontractors and/or Manufacturers for Major Items of Plant and Installation Services

A list of major items of Plant and Installation Services is provided below.

The following Subcontractors and/or Manufacturers are proposed for carrying out the item of the facilities. Bidders are free to propose more than one for each item.

| Major Items of Plant and Installation Services | Proposed Subcontractors or Manufacturers | Nationality |
| --- | --- | --- |

##### Manufacturer's Authorization

Date: [insert date (as day, month and year) of bid submission]

IFB No.: [insert number of bidding process]

To:  [insert complete name of the Employer]

WHEREAS

We [insert complete name of the manufacturer or manufacturer’s authorized agent], who are official manufacturers or agent authorized by the Manufacturer of [insert type of goods manufactured], having factories at [insert full address of manufacturer’s factories], do hereby authorize [insert complete name of the Bidder] to submit a bid the purpose of which is to provide the following goods, manufactured by us [insert name and/or brief description of the goods], and to subsequently negotiate and sign the Contract.

We hereby extend our full guarantee and warranty in accordance with Clause 27 of the General Conditions of Contract, with respect to the goods offered by the above firm.

Signed: [insert signature(s) of authorized representative(s) of the manufacturer]

Name: [insert complete name(s) of authorized representative(s) of the manufacturer]

Title: [insert title]

Duly authorized to sign this Authorization on behalf of: [insert complete name of the manufacturer]

Dated on ____________ day of __________________, _______ [insert date of signing]

[Note: The bidder shall require the manufacturer to fill out this form in accordance with the instructions indicated. This letter of authorization should be signed by a person with the proper authority to sign documents that are binding on the manufacturer. The bidder shall include it in its bid, if so indicated in the BDS.]

##### Time Schedule

To be used by Bidder when alternative Time for Completion is invited in ITB 13.2.

##### Functional Guarantee of the Proposed Facilities

Form FUNC

The Bidder shall copy on the left column of the table below, the identification of each functional guarantee required in the Specification and stated by the Employer in EQC 1.3.4 of Section III, Evaluation and Qualification Criteria, and on the right column, provide the corresponding value for each functional guarantee of the proposed plant and equipment.

| Functional Guarantee [as required by the Employer in Section III] | Value of Functional Guarantee of the Proposed Plant and Equipment |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| … |  |

Updating of Bidders Qualification

The Bidder shall update the information given during the corresponding Prequalification exercise to demonstrate that he continues to meet the criteria used at the time of Prequalification regarding:

(a)	Eligibility

(b)	Historical Contract Non-Performance and Pending Litigation

(c)	Financial Situation and Performance

For this purpose, the Bidder shall use the relevant forms included in this Section.

##### Form ELI – 1: Bidder’s Information Sheet

Date: ______________________

IFB No.: ___________________

Page ________ of _______ pages

1. Bidder’s Legal Name:

2. In case of JVA, legal name of each party:

3. Bidder’s Country of Constitution:

4. Bidder’s Year of Constitution:

5. Bidder’s Legal Address in Country of Constitution:

6. Bidder’s Authorized Representative Information Name: Address: Telephone/Fax numbers: Email Address:

7. Attached are copies of original documents of  Articles of Incorporation (or equivalent documents of constitution or association), and/or documents of registration of the legal entity named above, in accordance with ITB 4.1 and ITB 4.2.  Authorization to represent the firm or JVA named above, in accordance with ITB 22.2.  In case of JVA, letter of intent to form JVA or JVA agreement, in accordance with ITB 4.1  In case of state-owned enterprise or institution, in accordance with ITB 4.5, documents establishing: - Legal and financial autonomy - Operation under commercial law - Establishing that the Bidder is not under the supervision of the Employer 8. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.

##### Form ELI – 2: Party to JVA Information Sheet

Date: ______________________

IFB No.: ___________________

Page ________ of _______ pages

[Each party of the Joint Venture must fill out this form separately. Subcontractors must fill out this form]

1. Bidder’s Legal Name:

2. Joint Venture Partner’s or Subcontractor’s legal name:

3. Joint Venture Partner’s or Subcontractor’s country of constitution:

4. Joint Venture Partner’s or Subcontractor’s year of constitution:

5. Joint Venture Partner’s or Subcontractor’s legal address in country of constitution:

6. Joint Venture Partner’s or Subcontractor’s authorized representative information Name: Address: Telephone/Fax numbers: Email Address:

7. Attached are copies of original documents of  Articles of Incorporation (or equivalent documents of constitution or association), and/or registration documents of the legal entity named above, in accordance with ITB 4.1 and ITB 4.2.  Authorization to represent the firm named above, in accordance with ITB 22.2.  In case of a state-owned enterprise, documents establishing legal and financial autonomy, operation in accordance with commercial law, and that they are not under the supervision of the Employer, in accordance with ITB 4.5. 8. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.

Subcontractors are those listed in Technical Proposal – Proposed Subcontractors and/or Manufacturers for Major Items of Plant and Services.

##### Form CON – 1: Historical Contract Non-Performance and Pending Litigation

[The following table shall be filled in for the Bidder and for each member of a JV.]

Date: ______________________

Bidder’s Legal Name: _______________

Joint Venture Party Legal Name: _______________

IFB No.: _______________

Page ________ of _______ pages

Each Bidder must fill out this form in accordance with Criteria 2.2.2 of Section III (Evaluation and Qualification Criteria) to describe pending litigation formally commenced against it.

| ##### Table 1: History of Nonperforming Contracts |  |  |  |
| --- | --- | --- | --- |
| ##### Choose one of the following: - No nonperforming contracts. - Below is a description of nonperforming contracts involving the Bidder (or each Joint Venture member if Bidder is a Joint Venture). |  |  |  |
| Year | Description | Amount of Nonperformed Portion of Contract (US$ equivalent) | Total Contract Amount (US$ equivalent) |
| [insert year] | Contract Identification: [indicate complete contract name/ number, and any other identification] Name of Employer: [insert full name] Address of Employer: [insert street/city/country] Reason(s) for nonperformance: [indicate main reason(s)] | [insert amount] | [insert amount] |
| Table 2: Pending Litigation |  |  |  |
| ##### Choose one of the following: - No pending litigation - Below is a description of all pending litigation against the Bidder (or each Joint Venture member if Bidder is a Joint Venture). |  |  |  |
| Year | Matter in Dispute | Value of Pending Claim in $ Equivalent | Value of Pending Claim as a Percentage of Net Worth |
| [insert year] | Contract Identification: [indicate complete contract name/ number, and any other identification] Name of Employer: [insert full name] Address of Employer: [insert street/city/country] Matter of Dispute: [indicate full description of dispute] Party who initiated the dispute: [indicate “Employer” or “Contractor”] Status: [indicate status of dispute] | [insert amount] | [insert amount] |

[Note: Table 2 of this form shall only be included if Criterion 2.2.2 of Section III (Evaluation and Qualification Criteria) is applicable.]

##### Form FIN – 1: Financial Situation and Performance

Each Bidder must fill out this form.

In case of a Joint Venture, each Joint Venture Partner must fill out this form separately and provide the Joint Venture Partner’s name:

Joint Venture Partner: ___________________

1. Financial data

| Type of Financial information in (currency) | Historic information for previous _________years, (amount, currency, exchange rate, US$ equivalent) |  |  |
| --- | --- | --- | --- |
|  | Year 1: | Year 2: | Year 3: |
| Statement of Financial Position (Information from Balance Sheet) |  |  |  |
| Total Assets (TA) |  |  |  |
| Total Liabilities (TL) |  |  |  |
| Net Worth (NW) = TA - TL |  |  |  |
| Current Assets (CA) |  |  |  |
| Current Liabilities (CL) |  |  |  |
| Working Capital = CA - CL |  |  |  |
| Most Recent Working Capital |  | To be obtained for most recent year and carried forward to FIN - 3 Line 1; in case of Joint Ventures, to the corresponding Joint Venture Partner’s FIN – 3. |  |
| Information from Income Statement |  |  |  |
| Total Revenue (TR) |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |
| Profits After Taxes (PAT) |  |  |  |

2. Financial documents

The Bidder and its parties shall provide copies of the financial statements for [number of years] years pursuant to the Prequalification Cirteria. The financial statements shall:

- reflect the financial situation of the Bidder or in case of JVA member, of each member, and not an affiliated entity (such as parent company or group member).

- be independently audited or certified in accordance with local legislation.

- be complete, including all notes to the financial statements.

- correspond to accounting periods already completed and audited (no statements for partial periods shall be requested or accepted).

- Attached are copies of financial statements for the [number of years] years required above; and complying with the requirements.

##### Form FIN – 2: Average Annual Turnover

Each Bidder must fill out this form.

The information supplied should be the Annual Turnover of the Bidder or each member of a Joint Venture in terms of the amounts billed to clients for each year for work in progress or completed, converted to US dollars at the rate of exchange at the end of the period reported.

In case of a Joint Venture, each Joint Venture Partner must fill out this form separately and provide the Joint Venture Partner’s name:

Joint Venture Partner: ___________________

| Annual Turnover Data for the Last _____ Years |  |  |  |
| --- | --- | --- | --- |
| Year | Amount Currency | Exchange rate | US$ equivalent |
| [indicate year] | [insert amount and indicate currency] |  |  |
| Average Annual Turnover |  |  |  |

##### Form FIN - 3: Availability of Financial Resources

Bidders must demonstrate sufficient financial resources, usually comprising of Working Capital supplemented by credit line statements or overdraft facilities and others to meet the Bidder’s financial requirements for:

- its current contract commitments; and

- the subject contract.

In case of a Joint Venture, each Joint Venture Partner must fill out this form separately and provide the Joint Venture Partner’s name:

Joint Venture Partner: ___________________

| No. | Source of financing | Amount (US$ equivalent) |
| --- | --- | --- |
| 1 | Working Capital (to be taken from FIN - 1) |  |
| 2 | Credit Linea |  |
| 3 | Other Financial Resources |  |
| Total Available Financial Resources |  |  |

- To be substantiated by a letter from the bank issuing the line of credit.

##### Form FIN - 4: Financial Requirements for Current Contract Commitments

Bidders (or each Joint Venture partner) should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

In case of a Joint Venture, each Joint Venture Partner must fill out this form separately and provide the Joint Venture Partner’s name:

Joint Venture Partner: ___________________

##### Current Contract Commitments

| No. | Name of Contract | Employer’s Contact (Address, Tel, Fax) | Contract Completion Date | Outstanding Contract Value (X) a | Remaining Contract Period in months (Y) b | Monthly Financial Resources Requirement (X / Y) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |
| Total Monthly Financial Requirement for Current Contract Commitments |  |  |  |  |  | US$ . . . . . . . . . . . . . . . . . |

- Remaining outstanding contract values to be calculated from 28 days prior to the bid submission deadline (US$ equivalent based on the foreign exchange rate as of the same date).

- Remaining contract period to be calculated from 28 days prior to bid submission deadline.

##### Form FIN – 5: Self-Assessment Tool for Bidder’s Compliance to Financial Resources (Criterion 2.2 of Section III)

This form requires the same information submitted in Forms FIN - 3 and FIN - 4. All conditions of “Available Financial Resources Net of CCC ≥ Requirement for the Subject Contract” must be satisfied to qualify.

Form FIN - 5A: For Single Entities

| For Single Entities: (A) | Total Available Financial Resources from FIN – 3 (B) | Total Monthly Financial Requirement for Current Contract Commitments (CCC) from FIN – 4 (C) | Available Financial Resources Net of CCC D = (B - C) | Requirement for the Subject Contract (E) | Results: Yes or No [D must be greater than or equal to E] (F) |
| --- | --- | --- | --- | --- | --- |
| _________ (Name of Bidder) |  |  |  | . . . . . . . . . . ._ |  |

Form FIN - 5B: For Joint Ventures

| For Joint Ventures: (A) | Total Available Financial Resources from FIN – 3 (B) | Total Monthly Financial Requirement for Current Contract Commitments (CCC) from FIN – 4 (C) | Available Financial Resources Net of CCC D = (B - C) | Requirement for the Subject Contract (E) | Results: Yes or No [D must be greater than or equal to E] (F) |
| --- | --- | --- | --- | --- | --- |
| One Partner: |  |  |  |  |  |
| ____________ (Name of Partner) |  |  |  | . . . . . . . . . . . |  |
| Each Partner: |  |  |  |  |  |
| _____________ (Name of Partner 1) |  |  |  | . . . . . . . . . . . |  |
| _____________ (Name of Partner 2) |  |  |  | . . . . . . . . . . . |  |
| _____________ (Name of Partner 3) |  |  |  | . . . . . . . . . . . |  |
| All partners combined | ∑ D = Sum of available financial resources net of current contract commitments for all partners |  | ∑ D = _______ | . . . . . . . . . . . |  |

[Note: Form FIN – 5 is made available for use by the bidder as a self-assessment tool, and by the Employer as an evaluation work sheet, to determine compliance with the financial resources requirement as stated in 2.2. Failure to submit Form FIN - 5 by the Bidder shall not lead to bid rejection.]

Declaration of Participation in Economic Development Cooperation Fund (EDCF) Financed Projects

경협기금 지원사업 참여관련 확약서

Declaration of participation in Economic Development Cooperation Fund (EDCF) financed projects

한국수출입은행 귀중

To The Export-Import Bank of Korea (the “Bank”)

사 업 명:

Name of the Project (the “Project”):

당사는 표제의 대외경제협력기금(EDCF)(이하 “기금”이라 한다) 지원사업 참여와 관련하여, 다음 사항을 확인하고 준수할 것을 확약합니다.

We, the undersigned company, hereby declare that we will comply with the following with regard to our participation in the above-stated Project financed by the Economic Development Cooperation Fund (EDCF):

- - 다 음 -

Ⅰ. 부정당행위 제재 관련

I. Declaration on Anti-Corruption and Anti-Malpractice

1. 당사는「국제상거래에 있어서 외국공무원에 대한 뇌물방지법」의 내용을 충분히 숙지하고 이를 정히 준수하며, 표제 사업과 관련하여 동 법에 규정된 외국공무원 등에 대한 뇌물제공 등 부패행위와 사실왜곡 등 부정당행위에 관여한 사실이 없으며, 앞으로도 이러한 행위에 관련되지 않겠음.

1. We undertake to fully understand and comply with the Act on Combating Bribery of Foreign Public Officials in International Business Transactions, and we declare that neither we nor any other party acting on our behalf with regard to the Project has engaged or will engage in corrupt practices such as bribery and malpractices such as false statement.

2. 당사는 대한민국의 ‘국가를 당사자로 하는 계약에 관한 법률’, ‘지방자치단체를 당사자로 하는 계약에 관한 법률’ 및 ‘공공기관의 운영에 관한 법률’에 의거 입찰 참가자격이 제한되는 제재 처분을 받고 있지 않으며, 다자개발은행으로부터 부패행위와 사실왜곡 등 부정당행위로 인하여 상호제재 처분을 받고 있지 않으며, 동 제재의 유무 판단기준일은 입찰서류 접수 마감일로 하는 것에 동의함. 또한, 제재 처분을 받고 처분기간 중에 있는 경우 표제 사업의 계약 입찰에 참가하거나, 계약을 수주 또는 체결하지 않을 것을 확약함.* 단, 다자개발은행으로부터 상호제재 처분에 따른 기금지원사업의 계약 입찰 참가, 계약 수주 또는 체결 금지기간은 해당 상호제재 부과일로부터 2년 이내로 함.

2. We confirm that our company is not under any sanction in accordance with the Act on Contracts to Which the State is a Party, the Act on Contracts to Which a Local Government is a Party, and the Act on the Management of Public Institutions of the Republic of Korea, nor is under cross debarment imposed by Multilateral Development Banks (MDBs) as a result of engaging in corruption and malpractices such as false statement. Also, we agree that the base date of determination on our sanction status is the date of the deadline for submission of bids. Nevertheless, in case our company is under any aforementioned sanction or cross debarment, we will not participate in the bid for, to be awarded, and to enter into the contract of the Project, unless two (2) years have passed since such sanction or cross debarment is imposed.

3. 당사는 공정한 입찰 진행을 위해 민원을 제기하는 경우 민원내용의 출처를 명확히 밝히고 기술평가 및 가격평가 결과 등 낙찰자 선정과 관련하여 입찰서류에 명시된 민원제기절차를 철저히 준수할 것을 확약함.

3. We confirm that in case we file a complaint, our company will clarify the sources of the complaint for a fair bidding process. We will thoroughly abide by the complaint procedures, with regard to the successful bidder selection process including technical evaluation and price evaluation, specified in the bidding documents.

4. 당사는 컨설턴트 고용계약 또는 구매계약을 신의에 따라 성실하게 이행하며, 정당한 사유 없는 계약 미이행, 대금 부당청구 등의 불성실한 계약 이행을 하지 않을 것임을 확약함.

4. We will faithfully perform consultant and procurement contracts, avoiding negligent performance, including nonfulfillment of contractual obligations without justifiable reasons or unfair payment claims.

5. 당사는 귀 행이 ‘당사가 (1) 각 목에 해당하는 부정당행위를 유발하거나 (2) 확약서에 기재된 내용이 거짓이거나 (3) 확약한 내용을 준수하지 아니하였다’고 판단하는 경우 귀행이 2년 이내의 기금지원사업 참여 제한, 부정당행위를 유발한 당해 사업 참여 제한(기간 한정 없음) 표제사업 및 입찰절차 진행 중인 사업의 차주와 사업실시기관에게 제재 사실 통보, 기업 개요ㆍ제재 사유ㆍ제재기간을 한국수출입은행 홈페이지에 공개하는 등의 조치를 취하더라도 어떠한 이의를 제기하지 않겠음.

가. 계약과 관련된 서류의 위․변조 또는 허위기재

나. 과실에 의한 하자 또는 보수 발생

다. 부정하도급 또는 하도급 대금 부당 미지급·지연

라. 조사설계 및 타당성조사용역 부실

마. 계약위반

바. 공중 손해 사고

사. 업무 관계자 사고

아. 뇌물공여

자. 담 합(컨설턴트-입찰자 간 담합 포함)

차. 입찰 및 계약체결 등 방해

카. 부정 또는 불성실한 행위

5. In the event that the Bank determines (a) our company has engaged in any activity falling under the malpractice category set out below, (b) any part of this Declaration is found to be false, or (c) we fail to abide by this Declaration, we will not raise any objections against the Bank’s measures, including the prohibition of our participation in any projects financed by EDCF loans for up to two years, the prohibition of our participation in this Project without limit of time, the Bank’s notification of the sanction to the Borrowers (including the Project Executing Agency) of the Project and other projects in bidding process, and disclosure of our company overview, grounds for sanction, and a sanction period on the Bank’s website.

a. False Statements

b. Negligent Operations

c. Improper Subcontracting or Unfair Nonpayment/Payment Delay to Subcontractor

d. Poor Survey and Design Services, Feasibility Studies

e. Breach of Contract

f. Damage or Injury to the Public

g. Damage or Injury to a Person Involved in the Operation

h. Bribery

i. Bid Rigging, including any Bid Rigging between a Consultant and a Bidder

j. Interference in Bidding and Contract Conclusion

k. Wrongful or Dishonest Acts

6. 당사는 대한민국의 ‘국가를 당사자로 하는 계약에 관한 법률’, ‘지방자치단체를 당사자로 하는 계약에 관한 법률’ 및 ‘공공기관의 운영에 관한 법률’에 의거 입찰 참가자격이 제한되는 제재 처분을 받거나, 다자개발은행(MDB)으로부터 부패행위와 사실왜곡 등 부정당행위로 인하여 상호제재(cross debarment) 처분을 받은 경우 귀행이 그 처분기간 동안 기금지원사업 참여 제한 등 조치를 취하더라도 어떠한 이의를 제기하지 않겠음.

* 단, 다자개발은행으로부터 상호제재 처분에 따른 기금지원사업의 계약 입찰 참가, 계약 수주 또는 체결 금지기간은 해당 상호제재 부과일로부터 2년 이내로 함.

6. In the event that our company is under any sanction in accordance with the Act on Contracts to Which the State is a Party, the Act on Contracts to Which a Local Government is a Party, and the Act on the Management of Public Institutions of the Republic of Korea, or is under cross debarment imposed by MDBs as a result of engaging in corruption or malpractices such as false statement, we will not raise any objections against the Bank’s measures, including the prohibition of our participation in any projects financed by EDCF loans for the sanction period decided by the Korean government and public institutions and the debarment period decided by MDBs, unless two (2) years have passed since such sanction or cross debarment is imposed.

Ⅱ. 법적 권리 및 청구권 관련

Ⅱ. Declaration on Legal Rights and Claims

1. 당사는 입찰서류 또는 계약서가 당사와 차주(사업실시기관 포함. 이하 같다)의 권리의무관계를 규율하는 바, 당사는 동 입찰서 또는 계약서를 근거로 귀 행에 대한 어떠한 법적 권리 또는 청구권을 갖지 않음을 확인함.

1. We acknowledge that the bidding documents and the contract stipulate the rights and obligations of the Supplier and the Borrower(including the Project Executing Agency), and thus we do not have any legal rights nor claims whatsoever against the Bank, which is not a party to the contract, with regard to the bidding documents or the contract.

2. 당사는 차관공여계약서의 당사자는 귀 행과 차주이며, 제3자인 당사는 동 차관계약서를 근거로 귀 행을 상대로 어떠한 권리나 청구권도 갖지 않음을 확인함.

2. We also acknowledge that Loan Agreement governs the relationship between the Borrower and the Bank, and that our company, as a third party, do not have any legal rights nor claims whatsoever derived therefrom.

3. 이에 따라, 당사는 당사가 입찰에 탈락하거나 입찰서류 및 계약서의 하자 또는 불이행 등으로 손실을 입는 경우에도 귀 행을 상대로 법적 소송을 포함하여 어떠한 형태의 이의도 제기하지 않을 것을 확약함.

3. Therefore, we hereby declare not to raise any objections against the Bank including lawsuits, in the event of tender failure or losses due to defects or nonfulfillment of the contract.

Ⅲ. 인권 및 환경보호 ․건강, 안전 기준 준수 관련

Ⅲ. Declaration on Human Rights ․Environment Protection ․Health and Safety

1. 당사는 사업을 수행함에 있어서 적용되는 노동법 및 국제노동기구(ILO)의 핵심노동기준(Core labor standard)을 준수할 것임을 확약함.

1. We undertake to comply with relevant labor laws and the Core Labor Standards of the International Labour Organization (ILO) in the process of contract execution.

2. 당사는 사업을 수행함에 있어서 적용되는 환경보호, 건강 및 안전에 관한 국제 또는 현지국 기준을 준수할 것을 확약함.

2. We undertake to comply with relevant international/local standards with regard to environment protection, health and safety in the process of contract execution.

Ⅳ. 사회적 가치 구현 관련

Ⅳ. Declaration on Upholding Social Value

1. 당사는 사업을 수행함에 있어서 일자리 창출, 균등한 기회 및 사회통합, 상생협력, 성비위 예방, 반부패·청렴 및 윤리경영 등 다양한 사회적 가치를 존중하고 이를 구현하기 위해 노력할 것을 확약함.

1. We declare to uphold social values including job creation, equal opportunity with social integration, cooperation for co-prosperity, prevention of sexual exploitation, abuse and harassment and ethical management, and to endeavor to realize those values in the process of contract execution.

년   월   일

Year Month Date

회사명:

Name of Company:

대표자:                            (인)

Name of Authorized Signatory                                               Signature

Section IV. Bidding Forms 
(Without Prequalification)

Table of Forms

Letter of Bid (Single-Stage One-Envelope Bidding Procedure)	167

Letter of Technical Bid (Single-Stage Two-Envelope Bidding Procedure)	170

Letter of Price Bid (Single-Stage Two-Envelope Bidding Procedure)	172

Price Schedules	174

Schedule No. 1: Plant and Mandatory Spare Parts Supplied from Abroad	176

Schedule No. 2:  Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country	177

Schedule No. 3:  Design Services	178

Schedule No. 4:  Installation and Other Services	179

Schedule No. 5:  Grand Summary	180

Schedule No. 6:  Recommended Spare Parts	181

Tables of Adjustment Data	182

Form of Bid Security(Bank Guarantee)	183

Form of Bid Security (Bid Bond)	185

Form of Bid-Securing Declaration	187

Technical Proposal	189

Site Organization	190

Method Statement	191

Mobilization Schedule	192

Construction Schedule	193

Plant		194

Safety Plan	195

Personnel	196

Contractor’s Equipment	198

Proposed Subcontractors and/or Manufacturers for Major Items of Plant and

Installation Services	199

Manufacturer's Authorization	200

Time Schedule	201

Functional Guarantee of the Proposed Facilities	202

Bidders Qualification without Prequalification	203

Form ELI – 1: Bidder’s Information Sheet	204

Form ELI – 2: Party to JVA Information Sheet	205

Form CON – 1: Historical Contract Non-Performance and Pending Litigation	206

Form FIN – 1: Financial Situation and Performance	208

Form FIN – 2: Average Annual Turnover	210

Form FIN – 3: Availability of Financial Resources	211

Form FIN – 4: Financial Requirements for Current Contract Commitments	212

Form FIN – 5: Self-Assessment Tool for Bidder’s Compliance to Financial

Resources (Criterion 2.3.3 of Section III)	213

Form EXP-1: General Experience	214

Form EXP – 2(a): Specific Experience	215

Form EXP – 2(b): Experience in Key Activities	216

Form EXP - 3: Subcontractors	217

Declaration of Participation in Economic Development Cooperation Fund (EDCF) Financed Projects	218

Letter of Bid

(Single-Stage One-Envelope Bidding Procedure)

Date:

CB No.:

Invitation for Bid No.:

To: [insert full name of Employer],

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB) 8.

- We, including any Subcontractors/manufacturers, for any part of the Contract, meet the eligibility requirements in accordance with ITB 4 and ITB 5.

- We, including any Subcontractors/manufacturers, for any part of the Contract, have no conflict of interests in accordance with ITB 4.

- We offer to [insert the services that apply, i.e., design, manufacture, test, deliver, install, precommission and commission], in conformity with the Bidding Documents, the following Plant and Installation Services: [insert a brief description of the Plant and Installation Services]

[Amount of foreign currency in words], [amount in figures], and [amount of local currency in words], [amount in figures]

The total bid price from the Grand Summary (Schedule No. 5) should be entered by the Bidder inside this box. Absence of the total bid price in the Letter of Bid may result in the rejection of the bid.

The total price of our Bid, excluding any discounts offered in item (f) below is the sum of

- The discounts offered and the methodology for their application are as follows: [insert discounts and methodology for their application if any]

- Our Bid shall be valid for a period of [insert bid validity period as specified in ITB 20.1 of the BDS] days from the date fixed for the bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period.

- If our Bid is accepted, we commit to obtain a performance security in accordance with the Bidding Documents.

- We are not participating, as a Bidder, either individually or as partner in a JVA, in more than one Bid in this bidding process in accordance with ITB 4.3(e), other than alternative offers submitted in accordance with ITB 13.

- We are not subject to, or not controlled by any entity or individual that is subject to, a sanction imposed by the Bank or any sanction in accordance with ‘Act on Contracts to which the State is a Party’ and ‘Regulation on Contracts to which the Public enterprise is a Party’ of the Republic of Korea or a cross debarment imposed by Multilateral Development Banks (MDBs).

- [select the appropriate option and delete the other] [We are not a government-owned enterprise] / [We are a government-owned enterprise but meet the requirements of ITB 4.5]

- We have not been suspended nor declared ineligible by the Employer based on execution of a Bid-Securing Declaration in the Employer’s Country in accordance with ITB 4.6.

- We understand that this Bid, together with your written acceptance thereof included in your notification of award, shall constitute a binding contract between us, until a formal contract is prepared and executed.

- We understand that you are not bound to accept the lowest evaluated Bid or any other Bid that you may receive.

- We agree to permit the Bank or its representative to inspect our accounts and records and other documents relating to the bid submission and to have them audited by auditors appointed by the Bank.

- If our Bid is accepted, we commit to mobilizing key equipment and personnel in accordance with the requirements set forth in Section VI (Employer’s Requirements) and our technical proposal, or as otherwise agreed with the Employer.

- We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf will engage in any type of fraud and corruption.

Name of the Bidder*: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder**: [insert complete name of the person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above: [insert signature of person whose name and capacity are shown above]

Date signed [insert date of signing] day of [insert month], [insert year]

* In the case of the Bid submitted by JVA specify the name of the JVA as Bidder.

** Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid.

Letter of Technical Bid

(Single-Stage Two-Envelope Bidding Procedure)

Date:

CB No.:

Invitation for Bid No.:

To: [insert full name of Employer],

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB) 8.

- We, including any Subcontractors/manufacturers, for any part of the Contract, meet the eligibility requirements in accordance with ITB 4 and ITB 5.

- We, including any Subcontractors/manufacturers, for any part of the Contract, have no conflict of interests in accordance with ITB 4.

- We offer to [insert the services that apply, i.e., design, manufacture, test, deliver, install, precommission and commission], in conformity with the Bidding Documents, the following Plant and Installation Services: [insert a brief description of the Plant and Installation Services]

- Our Bid consisting of the Technical Bid and the Price Bid shall be valid for a period of [insert bid validity period as specified in ITB 20.1 of the BDS] days from the date fixed for the bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period.

- We are not participating, as a Bidder, either individually or as partner in a JVA, in more than one Bid in this bidding process in accordance with ITB 4.3(e), other than alternative offers submitted in accordance with ITB 13.

- We are not subject to, or not controlled by any entity or individual that is subject to, a sanction imposed by the Bank or any sanction in accordance with ‘Act on Contracts to which the State is a Party’ and ‘Regulation on Contracts to which the Public enterprise is a Party’ of the Republic of Korea or a cross debarment imposed by Multilateral Development Banks (MDBs).

- [select the appropriate option and delete the other] [We are not a government-owned enterprise] / [We are a government-owned enterprise but meet the requirements of ITB 4.5]

- We have not been suspended nor declared ineligible by the Employer based on execution of a Bid-Securing Declaration in the Employer’s Country in accordance with ITB 4.6.

- We agree to permit the Bank or its representative to inspect our accounts and records and other documents relating to the bid submission and to have them audited by auditors appointed by the Bank.

- If our Bid is accepted, we commit to mobilizing key equipment and personnel in accordance with the requirements set forth in Section VI (Employer’s Requirements) and our technical proposal, or as otherwise agreed with the Employer.

- We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf will engage in any type of fraud and corruption.

Name of the Bidder*: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder**: [insert complete name of the person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above: [insert signature of person whose name and capacity are shown above]

Date signed [insert date of signing] day of [insert month], [insert year]

* In the case of the Bid submitted by JVA specify the name of the JVA as Bidder.

** Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid.

Letter of Price Bid

(Single-Stage Two-Envelope Bidding Procedure)

Date:

CB No.:

Invitation for Bid No.:

To: [insert full name of Employer],

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB) 8.

- We, including any Subcontractors/manufacturers, for any part of the Contract, meet the eligibility requirements in accordance with ITB 4 and ITB 5.

- We, including any Subcontractors/manufacturers, for any part of the Contract, have no conflict of interests in accordance with ITB 4.

- We offer to [insert the services that apply, i.e., design, manufacture, test, deliver, install, precommission and commission], in conformity with the Bidding Documents, the following Plant and Installation Services: [insert a brief description of the Plant and Installation Services]

[Amount of foreign currency in words], [amount in figures], and [amount of local currency in words], [amount in figures]

The total bid price from the Grand Summary (Schedule No. 5) should be entered by the Bidder inside this box. Absence of the total bid price in the Letter of Bid may result in the rejection of the bid.

The total price of our Bid, excluding any discounts offered in item (f) below is the sum of

- The discounts offered and the methodology for their application are as follows: [insert discounts and methodology for their application if any]

- Our Bid consisting of the Technical Bid and the Price Bid shall be valid for a period of [insert bid validity period as specified in ITB 20.1 of the BDS] days from the date fixed for the bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period.

- If our Bid is accepted, we commit to obtain a performance security in accordance with the Bidding Documents.

- We understand that this Bid, together with your written acceptance thereof included in your notification of award, shall constitute a binding contract between us, until a formal contract is prepared and executed.

- We understand that you are not bound to accept the lowest evaluated Bid or any other Bid that you may receive.

- We agree to permit the Bank or its representative to inspect our accounts and records and other documents relating to the bid submission and to have them audited by auditors appointed by the Bank.

Name of the Bidder*: [insert complete name of the Bidder]

Name of the person duly authorized to sign the Bid on behalf of the Bidder**: [insert complete name of the person duly authorized to sign the Bid]

Title of the person signing the Bid: [insert complete title of the person signing the Bid]

Signature of the person named above: [insert signature of person whose name and capacity are shown above]

Date signed [insert date of signing] day of [insert month], [insert year]

* In the case of the Bid submitted by JVA specify the name of the JVA as Bidder.

** Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid.

Price Schedules

PREAMBLE

General

1.	The Price Schedules are divided into separate Schedules as follows:

Schedule No. 1:	Plant and Mandatory Spare Parts Supplied from Abroad

Schedule No. 2:	Plant and Mandatory Spare Parts Supplied from within the Employer’s Country

Schedule No. 3:	Design Services

Schedule No. 4:	Installation and Other Services

Schedule No. 5:	Grand Summary

Schedule No. 6:	Recommended Spare Parts

2.	The Schedules do not generally give a full description of the Plant to be supplied and the Installation Services to be performed under each item. Bidders shall be deemed to have read the Employer’s Requirements and other sections of the Bidding Document and reviewed the Drawings to ascertain the full scope of the requirements included in each item prior to filling in the rates and prices. The entered rates and prices shall be deemed to cover the full scope as aforesaid, including overheads and profit.

3.	If Bidders are unclear or uncertain as to the scope of any item, they shall seek clarification in accordance with ITB 7 prior to submitting their bid.

Pricing

4.	The units and rates in figures entered into the Price Schedules should be typewritten or if written by hand, must be in print form. Price Schedules not presented accordingly may be considered nonresponsive. Any alterations necessary due to errors, etc., shall be initialed by the Bidder.

As specified in the Bid Data Sheet and Particular Conditions of Contract, prices shall be fixed and firm for the duration of the Contract, or prices shall be subject to adjustment in accordance with the corresponding Appendix (Price Adjustment) to the Contract Agreement.

5.	Bid prices shall be quoted in the manner indicated and in the currencies specified in the Instructions to Bidders in the Bidding Document.

For each item, Bidders shall complete each appropriate column in the respective Schedules, giving the price breakdown as indicated in the Schedules.

Prices given in the Schedules against each item shall be for the scope covered by that item as detailed in Section VI (Employer’s Requirements) or elsewhere in the Bidding Document.

6.	Payments will be made to the Contractor in the currency or currencies indicated under each respective item.

7.	When requested by the Employer for the purposes of making payments or partial payments, valuing variations or evaluating claims, or for such other purposes as the Employer may reasonably require, the Contractor shall provide the Employer with a breakdown of any composite or lump sum items included in the Schedules.

Schedules of Rates and Prices

##### Schedule No. 1: Plant and Mandatory Spare Parts Supplied from Abroad

| Item | Description | Country of Origin | Quantity | Unit Pricea |  | Total Pricea | Taxes and Duties |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Foreign Currency | CIP | Foreign Currency | Local Currency |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 = 4 x 6 | 8 |
| TOTAL Column 7 to be carried forward to Schedule No. 5: Grand Summary |  |  |  |  |  |  |  |
| Name of Bidder |  |  |  |  |  |  |  |
| Signature of Bidder |  |  |  |  |  |  |  |

a 	Specify currencies in accordance with ITB 19.1 of the BDS. Create additional columns for foreign currencies if so required.

Country of Origin Declaration Form

| Item | Description | Country |
| --- | --- | --- |

##### Schedule No. 2:  Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country

| Item | Description | Quantity | Unit Pricea |  | Total EXW Pricea | Sales and other taxes |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Local Currency | EXW Priceb |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 = 3 x 5 | 7 |
| TOTAL Column 6 to be carried forward to Schedule No. 5: Grand Summary |  |  |  |  |  |  |
| Name of Bidder |  |  |  |  |  |  |
| Signature of Bidder |  |  |  |  |  |  |

a    Specify currency in accordance with ITB 19.1 of the BDS.

b     Column 5  EXW Price shall include all customs duties and sales and other taxes already paid or payable on the components and raw materials used in the manufacture or assembly of the item or the customs duties and sales and other taxes already paid on previously imported items.

##### Schedule No. 3:  Design Services

| Item | Description | Country of Origin |  | Quantity | Unit Pricea |  | Total Pricea |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Local Currency Portion | Foreign Currency Portion | Local Currency Portion | Foreign Currency Portion |
| 1 | 2-1 | 2-2 |  | 3 | 4 | 5 | 6 = 3 x 4 | 7 = 3 x 5 |
| TOTAL Columns 6 and 7 to be carried forward to Schedule No. 5: Grand Summary |  |  |  |  |  |  |  |  |
| Name of Bidder |  |  |  |  |  |  |  |  |
| Signature of Bidder |  |  |  |  |  |  |  |  |

a 	Specify currency in accordance with ITB 19.1 of the BDS.

##### Schedule No. 4:  Installation and Other Services

| Item | Description | Country of Origin | Quantity | Unit Pricea |  | Total Pricea |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Local Currency Portion | Foreign Currency Portion | Local Currency Portion | Foreign Currency Portion |
| 1 | 2-1 | 2-2 | 3 | 4 | 5 | 6 = 3 x 4 | 7 = 3 x 5 |
| TOTAL Columns 6 and 7 to be carried forward to Schedule No. 5: Grand Summary |  |  |  |  |  |  |  |
| Name of Bidder |  |  |  |  |  |  |  |
| Signature of Bidder |  |  |  |  |  |  |  |

a 	Specify currency in accordance with ITB 19.1 of the BDS.

##### Schedule No. 5:  Grand Summary

| Schedule No. | Title | Total Pricea |  |  |
| --- | --- | --- | --- | --- |
|  |  | Foreign |  | Local |
|  |  | KOR | 3rd |  |
| 1 | Plant and Mandatory Spare Parts Supplied from Abroad b |  |  |  |
| 2 | Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country b |  |  |  |
| 3 | Design Services |  |  |  |
| 4 | Installation and Other Services |  |  |  |
| Grand Total to be carried forward to Letter of Bid |  |  |  |  |
| Name of Bidder |  |  |  |  |
| Signature of Bidder |  |  |  |  |

a 		Specify currency in accordance with ITB 19.1 of the BDS. Create additional columns for foreign currencies if so required.

b   	Taxes and/or duties from Schedules 1 and 2 may be added to the contract price in accordance with GC 14 (Taxes and Duties) but excluded from bid evaluation in accordance with ITB 36.4 (for Two-envelope; substitute ITB 38.2).

##### Schedule No. 6:  Recommended Spare Parts

| Item | Description | Country of Origin | Quantity | Unit Pricea |  | Total Pricea |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | EXW Local Parts Local Currency | CIP Imported Parts Foreign Currency | Local Currency Portion | Foreign Currency Portion |
| 1 | 2-1 | 2-2 | 3 | 4 | 5 | 6 = 3 x 4 | 7 = 3 x 5 |
| TOTAL |  |  |  |  |  |  |  |
| Name of Bidder |  |  |  |  |  |  |  |
| Signature of Bidder |  |  |  |  |  |  |  |

a 	Specify currency in accordance with ITB 19.1 of the BDS.

Tables of Adjustment Data

Table A - Local Currency

| Index Code |  |  | Index Description |  |  | Source of Index |  |  | Base Value and Date |  | Bidder’s Local Currency Amount |  | Bidder’s Proposed Weighting |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Nonadjustable |  |  | --- |  |  | --- |  | --- |  | a: b: c: d: e: _________ |  |
|  |  |  |  |  |  |  | Total |  |  |  |  | 1.00 |  |  |

Table B - Foreign Currency

Name of Currency: _____________________________________________________________________.

[Insert name of currency. If the Bidder wishes to quote in more than one foreign currency, this table should be repeated for each foreign currency.]

| Index Code |  |  | Index Description |  | Source of Index |  |  |  | Base Value and Date |  |  | Bidder’s Currency in Type/Amount |  |  | Equivalent in FC1 |  |  | Bidder’s Proposed Weighting |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Nonadjustable |  |  | --- |  |  | --- |  |  | --- |  |  |  | a: b: c: d: e: _________ |  |
|  |  |  |  |  |  |  |  |  |  |  | Total |  |  |  |  | 1.00 |  |  |  |

<<Note>>

The base date shall be the date 28 days prior to the deadline for submission of the bid.

Tables of Adjustment Data shall only be included if prices are to be quoted as adjustable prices in accordance with ITB 18.6.

Form of Bid Security

(Bank Guarantee)

__________________________ [Bank’s Name, and Address of Issuing Branch or Office]

Beneficiary:  __________________________ [Name and Address of Employer]

Date:  __________________________

Bid Security No.: __________________________

We have been informed that __________________________ [name of the Bidder] (hereinafter called "the Bidder") has submitted to you its bid dated ___________ (hereinafter called "the Bid") for the execution of ________________ [name of contract] under Invitation for Bids No. ___________ (“the IFB”).

Furthermore, we understand that, according to your conditions, bids must be supported by a bid guarantee.

At the request of the Bidder, we ____________________ [name of Bank] hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of ___________ [amount in figures] (____________) [amount in words] upon receipt by us of your first demand in writing accompanied by a written statement stating that the Bidder is in breach of its obligation(s) under the bid conditions, because the Bidder:

(a) 	has withdrawn its Bid prior to the Bid validity expiry date set forth in the Applicant’s Letters of Technical and Price Bid (for One-envelope; substitute the Letter of Bid), or any extended date provided by the Applicant; or

(b) 	having been notified of the acceptance of its Bid by the Beneficiary prior to the expiry date of the Bid validity or any extension thereto provided by the Applicant, (i) has failed to execute the Contract Agreement, or (ii) has failed to furnish the Performance Security, in accordance with the Instructions to Bidders (“ITB”) of the Beneficiary’s bidding document.

This guarantee will expire: (a) if the Bidder is the successful Bidder, upon our receipt of copies of the Contract Agreement signed by the Bidder and the Performance Security issued to you upon the instruction of the Bidder; or (b) if the Bidder is not the successful Bidder, upon the earlier of (i) our receipt of a copy of your notification to the Bidder of the name of the successful Bidder, or (ii) twenty-eight (28) days after the expiration of the Bidder’s bid.

Consequently, any demand for payment under this guarantee must be received by us at the office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 revision, ICC Publication No. 758.

___________________________________

[Banker’s seal and authorized signature(s)]

Note: All italicized text is for use in preparing this form and shall be deleted from the final product.

Form of Bid Security

(Bid Bond)

BOND NO. ______________________

BY THIS BOND [insert name of Bidder] as Principal (hereinafter called “the Principal”), and [insert name, legal title, and address of surety], authorized to transact business in [insert name of country of Employer], as Surety (hereinafter called “the Surety”), are held and firmly bound unto [insert name of Employer] as Obligee (hereinafter called “the Employer”) in the sum of [insert amount of Bond in words and figures], for the payment of which sum, well and truly to be made, we, the said Principal and Surety, bind ourselves, our successors and assigns, jointly and severally, firmly by these presents.

WHEREAS the Principal has submitted a written Bid to the Employer dated the day of ______, 20__, for the construction of [insert name of Contract] (hereinafter called the “Bid”).

NOW, THEREFORE, THE CONDITION OF THIS OBLIGATION is such that if the Principal:

- withdraws its Bid prior to the bid validity expiry date set forth in the Principal’s Letters of Technical and Price Bid (for One-envelope; substitute the Letter of Bid), or any extended date provided by the Principal; or

- having been notified of the acceptance of its Bid by the Employer prior to the expiry date of the Bid validity or any extension thereto provided by the Principal,; (i) fails or refuses to execute the Contract Form, if required; or (ii) fails or refuses to furnish the Performance Security in accordance with the Instructions to Bidders,

then the Surety undertakes to immediately pay to the Employer up to the above amount upon receipt of the Employer’s first written demand, without the Employer having to substantiate its demand, provided that in its demand the Employer shall state that the demand arises from the occurrence of any of the above events, specifying which event(s) has occurred.

The Surety hereby agrees that its obligation will remain in full force and effect up to and including the date 28 days after the date of expiration of the Bid validity set forth in the Principal’s Letters of Technical and Price Bid (for One-envelope; substitute the Letter of Bid) or any extension thereto provided by the Principal.

IN TESTIMONY WHEREOF, the Principal and the Surety have caused these presents to be executed in their respective names this ____ day of ____________ 20__.

Principal: _______________________	Surety: _____________________________
	Corporate Seal (where appropriate)

_______________________________	____________________________________
(Signature)	(Signature)

(Printed name and title)	                        (Printed name and title)

Form of Bid-Securing Declaration

Date: [insert date (as day, month and year)]

Bid No.: [insert number of bidding process]

Alternative No.: [insert identification No if this is a bid for an alternative]

To: [insert complete name of the Employer]

We, the undersigned, declare that:

We understand that, according to your conditions, Bids must be supported by a Bid-Securing Declaration.

We accept that we will automatically be suspended from being eligible for bidding in any contract with the Borrower for the period of time of [insert number of years as indicated in ITB 21.1 of the BDS] starting on the date that we receive a notification from the Employer, if we are in breach of our obligation(s) under the bid conditions, because we

- have withdrawn our Bid prior to the expiry date of the Bid validity specified in the Letters of Technical and Price Bid (for One-envelope; substitute the Letter of Bid) or any extended date provided by us; or

- having been notified of the acceptance of our Bid by the Employer prior to the expiry date of the Bid validity in the Letter of Bid or any extended date provided by us, (i) fail or refuse to execute the Contract, if required, or (ii) fail or refuse to furnish the Performance Security, in accordance with the ITB.

We understand that this Bid-Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of your notification to us of the name of the successful Bidder; or (ii) twenty-eight (28) days after the expiration of our Bid.

Name of the Bidder*

Name of the person duly authorized to sign the Bid on behalf of the Bidder**___________

Title of the person signing the Bid______________________________________________

Signature of the person named above____________________________________________

Date signed ________________________________ day of ___________________, ______

Corporate Seal (where appropriate)

`

*: In the case of the Bid submitted by JVA specify the name of the JVA as Bidder

**: Person signing the Bid shall have the power of attorney given by the Bidder attached to the Bid

[Note: In case of a JVA, the Bid-Securing Declaration must be in the name of all members to the JVA that submits the Bid.]

Technical Proposal

- Site Organization

- Method Statement

- Mobilization Schedule

- Construction Schedule

- Plant

- Safety Plan

- Personnel

- Contractor’s Equipment

- Proposed Subcontractors/Manufacturers for Major Items of Plant and Installation Services

- Manufacturer’s Authorization

- Time Schedule

- Functional Guarantee of the Proposed Facilities

##### Site Organization

##### Method Statement

##### Mobilization Schedule

##### Construction Schedule

##### Plant

##### Safety Plan

##### Personnel

Form PER – 1: Proposed Personnel

Bidders should provide the names of suitably qualified personnel to meet the specified requirements stated in Section III (Evaluation and Qualification Criteria). The data on their experience should be supplied using the Form below for each candidate.

| 1. | Title of position |
| --- | --- |
|  | Name |
| 2. | Title of position |
|  | Name |
| 3. | Title of position |
|  | Name |
| 4. | Title of position |
|  | Name |

[Note: All titles of positions will be as listed in Section VI (Employer’s Requirements).]

Form PER – 2:  Resume of Proposed Personnel

The Bidder shall provide all the information requested below. Use one form for each position.

| Position |  |  |
| --- | --- | --- |
| Personnel information | Name | Date of birth |
|  | Professional qualifications |  |
| Present employment | Name of employer |  |
|  | Address of employer |  |
|  | Telephone | Contact (manager/personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present employer |

Summarize professional experience over the last twenty (20) years, in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

| ### From | ### To | ### Company/Project/Position/Relevant Technical and Management Experience |
| --- | --- | --- |

##### Contractor’s Equipment

Form EQU:  Equipment

The Bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key equipment listed in Section III (Evaluation and Qualification Criteria). A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the Bidder.

| Item of equipment |  |  |
| --- | --- | --- |
| Equipment information | Name of manufacturer | Model and power rating |
|  | Capacity | Year of manufacture |
| Current status | Current location |  |
|  | Details of current commitments |  |
| Source | Indicate source of the equipment o Owned o Rented o Leased o Specially manufactured |  |

Omit the following information for equipment owned by the Bidder.

| Owner | Name of owner |  |
| --- | --- | --- |
|  | Address of owner |  |
|  | Telephone | Contact name and title |
|  | Fax | Telex |
| Agreements | Details of rental / lease / manufacture agreements specific to the project |  |

##### Proposed Subcontractors and/or Manufacturers for Major Items of Plant and Installation Services

A list of major items of Plant and Installation Services is provided below.

The following Subcontractors and/or Manufacturers are proposed for carrying out the item of the facilities. Bidders are free to propose more than one for each item.

| Major Items of Plant and Installation Services | Proposed Subcontractors or Manufacturers | Nationality |
| --- | --- | --- |

##### Manufacturer's Authorization

Date: [insert date (as day, month and year) of bid submission]

IFB No.: [insert number of bidding process]

To:  [insert complete name of the Employer]

WHEREAS

We [insert complete name of the manufacturer or manufacturer’s authorized agent], who are official manufacturers or agent authorized by the Manufacturer of [insert type of goods manufactured], having factories at [insert full address of manufacturer’s factories], do hereby authorize [insert complete name of the Bidder] to submit a bid the purpose of which is to provide the following goods, manufactured by us [insert name and/or brief description of the goods], and to subsequently negotiate and sign the Contract.

We hereby extend our full guarantee and warranty in accordance with Clause 27 of the General Conditions of Contract, with respect to the goods offered by the above firm.

Signed: [insert signature(s) of authorized representative(s) of the manufacturer]

Name: [insert complete name(s) of authorized representative(s) of the manufacturer]

Title: [insert title]

Duly authorized to sign this Authorization on behalf of: [insert complete name of the manufacturer]

Dated on ____________ day of __________________, _______ [insert date of signing]

[Note: The bidder shall require the manufacturer to fill out this form in accordance with the instructions indicated. This letter of authorization should be signed by a person with the proper authority to sign documents that are binding on the manufacturer. The bidder shall include it in its bid, if so indicated in the BDS.]

##### Time Schedule

To be used by Bidder when alternative Time for Completion is invited in ITB 13.2.

##### Functional Guarantee of the Proposed Facilities

Form FUNC

The Bidder shall copy on the left column of the table below, the identification of each functional guarantee required in the Specification and stated by the Employer in EQC 1.3.4 of Section III, Evaluation and Qualification Criteria, and on the right column, provide the corresponding value for each functional guarantee of the proposed plant and equipment.

| Functional Guarantee [as required by the Employer in Section III] | Value of Functional Guarantee of the Proposed Plant and Equipment |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| … |  |

Bidders Qualification without Prequalification

To establish its qualifications to perform the contract in accordance with Section III, Evaluation and Qualification Criteria the Bidder shall provide the information requested in the corresponding Information Sheets included hereunder.

##### Form ELI – 1: Bidder’s Information Sheet

Date: ______________________

IFB No.: ___________________

Page ________ of _______ pages

1. Bidder’s Legal Name:

2. In case of JVA, legal name of each party:

3. Bidder’s Country of Constitution:

4. Bidder’s Year of Constitution:

5. Bidder’s Legal Address in Country of Constitution:

6. Bidder’s Authorized Representative Information Name: Address: Telephone/Fax numbers: Email Address:

7. Attached are copies of original documents of  Articles of Incorporation (or equivalent documents of constitution or association), and/or documents of registration of the legal entity named above, in accordance with ITB 4.1 and ITB 4.2.  Authorization to represent the firm or JVA named above, in accordance with ITB 22.2.  In case of JVA, letter of intent to form JVA or JVA agreement, in accordance with ITB 4.1  In case of state-owned enterprise or institution, in accordance with ITB 4.5, documents establishing: - Legal and financial autonomy - Operation under commercial law - Establishing that the Bidder is not under the supervision of the Employer 8. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.

##### Form ELI – 2: Party to JVA Information Sheet

Date: ______________________

IFB No.: ___________________

Page ________ of _______ pages

[Each party of the JVA must fill out this form separately. Subcontractors must fill out this form]

1. Bidder’s Legal Name:

2. JVA Partner’s or Subcontractor’s legal name:

3. JVA Partner’s or Subcontractor’s country of constitution:

4. JVA Partner’s or Subcontractor’s year of constitution:

5. JVA Partner’s or Subcontractor’s legal address in country of constitution:

6. JVA Partner’s or Subcontractor’s authorized representative information Name: Address: Telephone/Fax numbers: Email Address:

7. Attached are copies of original documents of  Articles of Incorporation (or equivalent documents of constitution or association), and/or registration documents of the legal entity named above, in accordance with ITB 4.1 and ITB 4.2.  Authorization to represent the firm named above, in accordance with ITB 22.2.  In case of a state-owned enterprise, documents establishing legal and financial autonomy, operation in accordance with commercial law, and that they are not under the supervision of the Employer, in accordance with ITB 4.5. 8. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.

Subcontractors are those listed in Technical Proposal – Proposed Subcontractors and/or Manufacturers for Major Items of Plant and Services.

##### Form CON – 1: Historical Contract Non-Performance and Pending Litigation

Each Bidder must fill out this form in accordance with Criteria 2.2.2 of Section III (Evaluation and Qualification Criteria) to describe pending litigation or arbitration formally commenced against it.

In case of a JVA, each JVA Partner must fill out this form separately and provide the JVA Partner’s name:

JVA Partner: ___________________

| ##### Table 1: History of Nonperforming Contracts |  |  |  |
| --- | --- | --- | --- |
| ##### Choose one of the following: - No nonperforming contracts. - Below is a description of nonperforming contracts involving the Bidder (or each JVA member if Bidder is a JVA). |  |  |  |
| Year | Description | Amount of Nonperformed Portion of Contract (US$ equivalent) | Total Contract Amount (US$ equivalent) |
| [insert year] | Contract Identification: [indicate complete contract name/ number, and any other identification] Name of Employer: [insert full name] Address of Employer: [insert street/city/country] Reason(s) for nonperformance: [indicate main reason(s)] | [insert amount] | [insert amount] |
| Table 2: Pending Litigation |  |  |  |
| ##### Choose one of the following: - No pending litigation. - Below is a description of all pending litigation against the Bidder (or each JVA member if Bidder is a JVA). |  |  |  |
| Year | Matter in Dispute | Value of Pending Claim in US$ Equivalent | Value of Pending Claim as a Percentage of Net Worth |
| [insert year] | Contract Identification: [indicate complete contract name/ number, and any other identification] Name of Employer: [insert full name] Address of Employer: [insert street/city/country] Matter of Dispute: [indicate full description of dispute] Party who initiated the dispute: [indicate “Employer” or “Contractor”] Status: [indicate status of dispute] | [insert amount] | [insert amount] |

[Note: Table 2 of this form shall only be included if Criterion 2.2.2 of Section III (Evaluation and Qualification Criteria) is applicable.]

##### Form FIN – 1: Financial Situation and Performance

Each Bidder must fill out this form.

In case of a JVA, each JVA Partner must fill out this form separately and provide the JVA Partner’s name:

JVA Partner: ___________________

1. Financial data

| Type of Financial information in (currency) | Historic information for previous _________years, (amount, currency, exchange rate, US$ equivalent) |  |  |
| --- | --- | --- | --- |
|  | Year 1: | Year 2: | Year 3: |
| Statement of Financial Position (Information from Balance Sheet) |  |  |  |
| Total Assets (TA) |  |  |  |
| Total Liabilities (TL) |  |  |  |
| Net Worth (NW) = TA - TL |  |  |  |
| Current Assets (CA) |  |  |  |
| Current Liabilities (CL) |  |  |  |
| Working Capital = CA - CL |  |  |  |
| Most Recent Working Capital |  | To be obtained for most recent year and carried forward to FIN - 3 Line 1; in case of JVAs, to the corresponding JVA Partner’s FIN – 3. |  |
| Information from Income Statement |  |  |  |
| Total Revenue (TR) |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |
| Profits After Taxes (PAT) |  |  |  |

2. Financial documents

The Bidder and its parties shall provide copies of the financial statements for [number of years] years pursuant to Section III (Evaluation and Qualification Criteria), Sub-factor 2.3.1. The financial statements shall:

- reflect the financial situation of the Bidder or in case of JVA member, of each member, and not an affiliated entity (such as parent company or group member).

- be independently audited or certified in accordance with local legislation.

- be complete, including all notes to the financial statements.

- correspond to accounting periods already completed and audited (no statements for partial periods shall be requested or accepted).

- Attached are copies of financial statements for the [number of years] years required above; and complying with the requirements.

##### Form FIN – 2: Average Annual Turnover

Each Bidder must fill out this form.

The information supplied should be the Annual Turnover of the Bidder or each member of a JVA in terms of the amounts billed to clients for each year for work in progress or completed, converted to US dollars at the rate of exchange at the end of the period reported.

In case of a JVA, each JVA Partner must fill out this form separately and provide the JVA Partner’s name:

JVA Partner: ___________________

| Annual Turnover Data for the Last _____ Years |  |  |  |
| --- | --- | --- | --- |
| Year | Amount Currency | Exchange rate | US$ equivalent |
| [indicate year] | [insert amount and indicate currency] |  |  |
| Average Annual Turnover |  |  |  |

##### Form FIN – 3: Availability of Financial Resources

Bidders must demonstrate sufficient financial resources, usually comprising of Working Capital supplemented by credit line statements or overdraft facilities and others to meet the Bidder’s financial requirements for:

- its current contract commitments; and

- the subject contract.

In case of a JVA, each JVA Partner must fill out this form separately and provide the JVA Partner’s name:

JVA Partner: ___________________

| No. | Source of financing | Amount (US$ equivalent) |
| --- | --- | --- |
| 1 | Working Capital (to be taken from FIN - 1) |  |
| 2 | Credit Linea |  |
| 3 | Other Financial Resources |  |
| Total Available Financial Resources |  |  |

- To be substantiated by a letter from the bank issuing the line of credit.

##### Form FIN – 4: Financial Requirements for Current Contract Commitments

Bidders (or each JVA partner) should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

In case of a JVA, each JVA Partner must fill out this form separately and provide the JVA Partner’s name:

JVA Partner: ___________________

##### Current Contract Commitments

| No. | Name of Contract | Employer’s Contact (Address, Tel, Fax) | Contract Completion Date | Outstanding Contract Value (X) a | Remaining Contract Period in months (Y) b | Monthly Financial Resources Requirement (X / Y) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |
| Total Monthly Financial Requirement for Current Contract Commitments |  |  |  |  |  | US$ . . . . . . . . . . . . . . . . . |

- Remaining outstanding contract values to be calculated from twenty-eight (28) days prior to the bid submission deadline (US$ equivalent based on the foreign exchange rate as of the same date).

- Remaining contract period to be calculated from twenty-eight (28) days prior to bid submission deadline.

##### Form FIN – 5: Self-Assessment Tool for Bidder’s Compliance to Financial Resources (Criterion 2.3.3 of Section III)

This form requires the same information submitted in Forms FIN - 3 and FIN - 4. All conditions of “Available Financial Resources Net of CCC ≥ Requirement for the Subject Contract” must be satisfied to qualify.

Form FIN - 5A: For Single Entities

| For Single Entities: (A) | Total Available Financial Resources from FIN – 3 (B) | Total Monthly Financial Requirement for Current Contract Commitments (CCC) from FIN – 4 (C) | Available Financial Resources Net of CCC D = (B - C) | Requirement for the Subject Contract (E) | Results: Yes or No [D must be greater than or equal to E] (F) |
| --- | --- | --- | --- | --- | --- |
| _________ (Name of Bidder) |  |  |  | . . . . . . . . . . ._ |  |

Form FIN - 5B: For JVAs

| For JVAs: (A) | Total Available Financial Resources from FIN – 3 (B) | Total Monthly Financial Requirement for Current Contract Commitments (CCC) from FIN – 4 (C) | Available Financial Resources Net of CCC D = (B - C) | Requirement for the Subject Contract (E) | Results: Yes or No [D must be greater than or equal to E] (F) |
| --- | --- | --- | --- | --- | --- |
| One Partner: |  |  |  |  |  |
| ____________ (Name of Partner) |  |  |  | . . . . . . . . . . . |  |
| Each Partner: |  |  |  |  |  |
| _____________ (Name of Partner 1) |  |  |  | . . . . . . . . . . . |  |
| _____________ (Name of Partner 2) |  |  |  | . . . . . . . . . . . |  |
| _____________ (Name of Partner 3) |  |  |  | . . . . . . . . . . . |  |
| All partners combined | ∑ D = Sum of available financial resources net of current contract commitments for all partners |  | ∑ D = _______ | . . . . . . . . . . . |  |

[Note: Form FIN – 5 is made available for use by the bidder as a self-assessment tool, and by the Employer as an evaluation work sheet, to determine compliance with the financial resources requirement as stated in 2.3.3. Failure to submit Form FIN - 5 by the Bidder shall not lead to bid rejection.]

##### Form EXP-1: General Experience

[The following table shall be filled in for the Bidder and for each member of a JVA.]

Date: ______________________

Bidder’s Legal Name: _______________

JVA Party Legal Name: _______________

IFB No.: _______________

Page ________ of _______ pages

[Identify Contracts that demonstrate continuous work over the past [number] years pursuant to Section III (Evaluation and Qualification Criteria), 2.4.1. List Contract chronologically, according to their commencement (starting) dates.]

| Starting Month / Year | Ending Month / Year | Years* | Contract Identification | Role of Bidder |
| --- | --- | --- | --- | --- |
| [indicate year] | [indicate year] |  | - Contract name: [insert full name] - Brief Description of the Contract performed by the Bidder: [describe works performed briefly] - Amount of Contract: [insert amount, currency, exchange rate and US$ equivalent] - Name of Employer: [indicate full name] - Address: [indicate street/number/town or city/country] | [insert “Prime Contractor”(Single entity or JVA member) or “Subcontractor” or “Management Contractor”] |

* List calendar year for years with contracts with at least nine (9) months activity per year starting with the earliest year

##### Form EXP – 2(a): Specific Experience

Fill out one (1) form per contract.

The exchange rate to be used to calculate the value of the contract for conversion to a specific currency shall be the selling rate of the Borrower’s national bank on the date of the contract.

| ##### Contract of Similar Size and Nature |  |  |  |
| --- | --- | --- | --- |
| Contract No . . . . . . of . . . . . | Contract Identification |  |  |
| Award Date |  | Completion Date |  |
| Role in Contract | - Contractor | - Management Contractor | - Subcontractor |
| Total Contract Amount | US$ |  |  |
| If partner in a JVA or Subcontractor, specify participation of total contract amount | Percent of Total | Amount |  |
| Employer’s name Address Telephone number Fax number E-mail |  |  |  |
| ##### Description of the Similarity in Accordance with Criterion 2.4.2(a) of Section III (Evaluation and Qualification Criteria) |  |  |  |

##### Form EXP – 2(b): Experience in Key Activities

Fill out one (1) form per contract.

Each Bidder must fill out this form.

If complied by Specialist Subcontractor, each Specialist Subcontractor must fill out this form and provide the Specialist Subcontractor’s name:

Specialist Subcontractor: ___________________

| ##### Contract with Similar Key Activities |  |  |  |
| --- | --- | --- | --- |
| Contract No . . . . . . of . . . . . | Contract Identification |  |  |
| Award Date |  | Completion Date |  |
| Role in Contract | - Contractor | - Management Contractor | - Subcontractor |
| Total Contract Amount | $ |  |  |
| If partner in a JVA or Subcontractor, specify participation of total contract amount | Percent of Total | Amount |  |
| Employer’s name Address Telephone number Fax number E-mail |  |  |  |
| ##### Description of the Key Activities in Accordance with Criterion 2.4.2(b) of Section III (Evaluation and Qualification Criteria) |  |  |  |

##### Form EXP - 3: Subcontractors

Fill out one (1) form per contract.

| ##### Contract for the Major Items |  |  |  |
| --- | --- | --- | --- |
| Contract No . . . . . . of . . . . . . | Contract Identification |  |  |
| Award Date |  | Completion Date |  |
| Role in Contract | - Contractor | - Management Contractor | - Subcontractor |
| Total Contract Amount | US$ |  |  |
| If partner in a JVA or Subcontractor, specify participation of total contract amount | Percent of Total | Amount |  |
| Employerʼs name Address Telephone number Fax number E-mail |  |  |  |
| ##### Description of the Major Items in Accordance with Criterion 2.7 of Section III (Evaluation and Qualification Criteria) |  |  |  |

Declaration of Participation in Economic Development Cooperation Fund (EDCF) Financed Projects

경협기금 지원사업 참여관련 확약서

Declaration of participation in Economic Development Cooperation Fund (EDCF) financed projects

한국수출입은행 귀중

To The Export-Import Bank of Korea (the “Bank”)

사 업 명:

Name of the Project (the “Project”):

당사는 표제의 대외경제협력기금(EDCF)(이하 “기금”이라 한다) 지원사업 참여와 관련하여, 다음 사항을 확인하고 준수할 것을 확약합니다.

We, the undersigned company, hereby declare that we will comply with the following with regard to our participation in the above-stated Project financed by the Economic Development Cooperation Fund (EDCF):

- - 다 음 -

Ⅰ. 부정당행위 제재 관련

I. Declaration on Anti-Corruption and Anti-Malpractice

1. 당사는「국제상거래에 있어서 외국공무원에 대한 뇌물방지법」의 내용을 충분히 숙지하고 이를 정히 준수하며, 표제 사업과 관련하여 동 법에 규정된 외국공무원 등에 대한 뇌물제공 등 부패행위와 사실왜곡 등 부정당행위에 관여한 사실이 없으며, 앞으로도 이러한 행위에 관련되지 않겠음.

1. We undertake to fully understand and comply with the Act on Combating Bribery of Foreign Public Officials in International Business Transactions, and we declare that neither we nor any other party acting on our behalf with regard to the Project has engaged or will engage in corrupt practices such as bribery and malpractices such as false statement.

2. 당사는 대한민국의 ‘국가를 당사자로 하는 계약에 관한 법률’, ‘지방자치단체를 당사자로 하는 계약에 관한 법률’ 및 ‘공공기관의 운영에 관한 법률’에 의거 입찰 참가자격이 제한되는 제재 처분을 받고 있지 않으며, 다자개발은행으로부터 부패행위와 사실왜곡 등 부정당행위로 인하여 상호제재 처분을 받고 있지 않으며, 동 제재의 유무 판단기준일은 입찰서류 접수 마감일로 하는 것에 동의함. 또한, 제재 처분을 받고 처분기간 중에 있는 경우 표제 사업의 계약 입찰에 참가하거나, 계약을 수주 또는 체결하지 않을 것을 확약함.

* 단, 다자개발은행으로부터 상호제재 처분에 따른 기금지원사업의 계약 입찰 참가, 계약 수주 또는 체결 금지기간은 해당 상호제재 부과일로부터 2년 이내로 함.

2. We confirm that our company is not under any sanction in accordance with the Act on Contracts to Which the State is a Party, the Act on Contracts to Which a Local Government is a Party, and the Act on the Management of Public Institutions of the Republic of Korea, nor is under cross debarment imposed by Multilateral Development Banks (MDBs) as a result of engaging in corruption and malpractices such as false statement. Also, we agree that the base date of determination on our sanction status is the date of the deadline for submission of bids. Nevertheless, in case our company is under any aforementioned sanction or cross debarment, we will not participate in the bid for, to be awarded, and to enter into the contract of the Project, unless two (2) years have passed since such sanction or cross debarment is imposed.

3. 당사는 공정한 입찰 진행을 위해 민원을 제기하는 경우 민원내용의 출처를 명확히 밝히고 기술평가 및 가격평가 결과 등 낙찰자 선정과 관련하여 입찰서류에 명시된 민원제기절차를 철저히 준수할 것을 확약함.

3. We confirm that in case we file a complaint, our company will clarify the sources of the complaint for a fair bidding process. We will thoroughly abide by the complaint procedures, with regard to the successful bidder selection process including technical evaluation and price evaluation, specified in the bidding documents.

4. 당사는 컨설턴트 고용계약 또는 구매계약을 신의에 따라 성실하게 이행하며, 정당한 사유 없는 계약 미이행, 대금 부당청구 등의 불성실한 계약 이행을 하지 않을 것임을 확약함.

4. We will faithfully perform consultant and procurement contracts, avoiding negligent performance, including nonfulfillment of contractual obligations without justifiable reasons or unfair payment claims.

5. 당사는 귀 행이 ‘당사가 (1) 각 목에 해당하는 부정당행위를 유발하거나 (2) 확약서에 기재된 내용이 거짓이거나 (3) 확약한 내용을 준수하지 아니하였다’고 판단하는 경우 귀행이 2년 이내의 기금지원사업 참여 제한, 부정당행위를 유발한 당해 사업 참여 제한(기간 한정 없음) 표제사업 및 입찰절차 진행 중인 사업의 차주와 사업실시기관에게 제재 사실 통보, 기업 개요ㆍ제재 사유ㆍ제재기간을 한국수출입은행 홈페이지에 공개하는 등의 조치를 취하더라도 어떠한 이의를 제기하지 않겠음.

가. 계약과 관련된 서류의 위․변조 또는 허위기재

나. 과실에 의한 하자 또는 보수 발생

다. 부정하도급 또는 하도급 대금 부당 미지급·지연

라. 조사설계 및 타당성조사용역 부실

마. 계약위반

바. 공중 손해 사고

사. 업무 관계자 사고

아. 뇌물공여

자. 담 합(컨설턴트-입찰자 간 담합 포함)

차. 입찰 및 계약체결 등 방해

카. 부정 또는 불성실한 행위

5. In the event that the Bank determines (a) our company has engaged in any activity falling under the malpractice category set out below, (b) any part of this Declaration is found to be false, or (c) we fail to abide by this Declaration, we will not raise any objections against the Bank’s measures, including the prohibition of our participation in any projects financed by EDCF loans for up to two years, the prohibition of our participation in this Project without limit of time, the Bank’s notification of the sanction to the Borrowers (including the Project Executing Agency) of the Project and other projects in bidding process, and disclosure of our company overview, grounds for sanction, and a sanction period on the Bank’s website.

a. False Statements

b. Negligent Operations

c. Improper Subcontracting or Unfair Nonpayment/Payment Delay to Subcontractor

d. Poor Survey and Design Services, Feasibility Studies

e. Breach of Contract

f. Damage or Injury to the Public

g. Damage or Injury to a Person Involved in the Operation

h. Bribery

i. Bid Rigging, including any Bid Rigging between a Consultant and a Bidder

j. Interference in Bidding and Contract Conclusion

k. Wrongful or Dishonest Acts

6. 당사는 대한민국의 ‘국가를 당사자로 하는 계약에 관한 법률’, ‘지방자치단체를 당사자로 하는 계약에 관한 법률’ 및 ‘공공기관의 운영에 관한 법률’에 의거 입찰 참가자격이 제한되는 제재 처분을 받거나, 다자개발은행(MDB)으로부터 부패행위와 사실왜곡 등 부정당행위로 인하여 상호제재(cross debarment) 처분을 받은 경우 귀행이 그 처분기간 동안 기금지원사업 참여 제한 등 조치를 취하더라도 어떠한 이의를 제기하지 않겠음.

* 단, 다자개발은행으로부터 상호제재 처분에 따른 기금지원사업의 계약 입찰 참가, 계약 수주 또는 체결 금지기간은 해당 상호제재 부과일로부터 2년 이내로 함.

6. In the event that our company is under any sanction in accordance with the Act on Contracts to Which the State is a Party, the Act on Contracts to Which a Local Government is a Party, and the Act on the Management of Public Institutions of the Republic of Korea, or is under cross debarment imposed by MDBs as a result of engaging in corruption or malpractices such as false statement, we will not raise any objections against the Bank’s measures, including the prohibition of our participation in any projects financed by EDCF loans for the sanction period decided by the Korean government and public institutions and the debarment period decided by MDBs, unless two (2) years have passed since such sanction or cross debarment is imposed.

Ⅱ. 법적 권리 및 청구권 관련

Ⅱ. Declaration on Legal Rights and Claims

1. 당사는 입찰서류 또는 계약서가 당사와 차주(사업실시기관 포함. 이하 같다)의 권리의무관계를 규율하는 바, 당사는 동 입찰서 또는 계약서를 근거로 귀 행에 대한 어떠한 법적 권리 또는 청구권을 갖지 않음을 확인함.

1. We acknowledge that the bidding documents and the contract stipulate the rights and obligations of the Supplier and the Borrower(including the Project Executing Agency), and thus we do not have any legal rights nor claims whatsoever against the Bank, which is not a party to the contract, with regard to the bidding documents or the contract.

2. 당사는 차관공여계약서의 당사자는 귀 행과 차주이며, 제3자인 당사는 동 차관계약서를 근거로 귀 행을 상대로 어떠한 권리나 청구권도 갖지 않음을 확인함.

2. We also acknowledge that Loan Agreement governs the relationship between the Borrower and the Bank, and that our company, as a third party, do not have any legal rights nor claims whatsoever derived therefrom.

3. 이에 따라, 당사는 당사가 입찰에 탈락하거나 입찰서류 및 계약서의 하자 또는 불이행 등으로 손실을 입는 경우에도 귀 행을 상대로 법적 소송을 포함하여 어떠한 형태의 이의도 제기하지 않을 것을 확약함.

3. Therefore, we hereby declare not to raise any objections against the Bank including lawsuits, in the event of tender failure or losses due to defects or nonfulfillment of the contract.

Ⅲ. 인권 및 환경보호 ․건강, 안전 기준 준수 관련

Ⅲ. Declaration on Human Rights ․Environment Protection ․Health and Safety

1. 당사는 사업을 수행함에 있어서 적용되는 노동법 및 국제노동기구(ILO)의 핵심노동기준(Core labor standard)을 준수할 것임을 확약함.

1. We undertake to comply with relevant labor laws and the Core Labor Standards of the International Labour Organization (ILO) in the process of contract execution.

2. 당사는 사업을 수행함에 있어서 적용되는 환경보호, 건강 및 안전에 관한 국제 또는 현지국 기준을 준수할 것을 확약함.

2. We undertake to comply with relevant international/local standards with regard to environment protection, health and safety in the process of contract execution.

Ⅳ. 사회적 가치 구현 관련

Ⅳ. Declaration on Upholding Social Value

1. 당사는 사업을 수행함에 있어서 일자리 창출, 균등한 기회 및 사회통합, 상생협력, 성비위 예방, 반부패·청렴 및 윤리경영 등 다양한 사회적 가치를 존중하고 이를 구현하기 위해 노력할 것을 확약함.

1. We declare to uphold social values including job creation, equal opportunity with social integration, cooperation for co-prosperity, prevention of sexual exploitation, abuse and harassment and ethical management, and to endeavor to realize those values in the process of contract execution.

년   월   일

Year Month Date

회사명:

Name of Company:

대표자:                            (인)

Name of Authorized Signatory                                               Signature

Section V. Eligible Countries

This section contains eligible countries as follows:

- In accordance with the Loan Agreement, a Bidder, and all parties constituting the Bidder, shall have the nationality of [insert the name of countries in accordance with the restrictions regarding nationality of Eligible Bidder indicated in the Loan Agreement of the Project]; and

- All Plant and Installation Services to be supplied under the Contract and financed by the Bank shall have their origin in the Loan Agreement. Any bid that does not meet the following requirements shall be rejected by the Employer as non-responseive:

- Foreign Currency Portion shall be procured from the Republic of Korea and shall be [insert the relative percentage requirement as specified in the Loan Agreement] percent ([●]%) or more of the total cost of Plant and Installation Services to be financed out of the loan proceeds;

- Local Currency Portion shall be procured from [Insert the name of countries]; and

- All Plant and Installation Services to be financed out of the proceeds of the Loan shall be procured from the Eligible Source Countries, provided that a part of Plant and Installation Services may be procured from the countries other than the Eligible Source Countries up to [insert the relative percentage requirement as specified in the Loan Agreement] percent(%) of the total cost of Plant and Installation Services to be financed out of the loan proceeds.

PART 2 – Employer’s Requirements

Section VI. Employer’s Requirements

1. Scope of Supply of Plant and Installation Services	229

2. Specifications	230

3. Drawings	231

4. Supplementary Information	232

5. Certificates	233

5.1 Form of Completion Certificate	234

5.2  Form of Operational Acceptance Certificate	235

6. Change Orders	236

6.1. 	Change Order Procedure	237

6.1.1 General	237

6.1.2 Change Order Log	237

6.1.3 References for Changes	237

6.2 	Change Order Forms	238

6.2.1  Request for Change Proposal Form	238

6.2.2   Estimate for Change Proposal Form	240

6.2.3  Acceptance of Estimate Form	242

6.2.4  Change Proposal Form	243

6.2.5  Change Order Form	246

6.2.6  Pending Agreement Change Order Form	247

6.2.7  Application for Change Proposal Form	249

7. Personnel Requirements	251

8. Equipment Requirements	252

1. Scope of Supply of Plant and Installation Services

2. Specifications

<< Note >>

- For Bank financed design, supply and install contract to be procured through international competition, the Employer’s Requirements must be drawn up to permit the widest, possible competition and, at the same time, present a clear statement of the required standards of workmanship, materials and performance of the Facilities. Only if this is done will the objectives of economy, efficiency, fairness and transparency in procurement be realized, responsiveness of bids be ensured and the subsequent task of Bid evaluation facilitated.

- In a design, supply and install approach, the design is to be done by the Contractor. No detailed technical specification as is normal practice is developed at the pre-Bid stage. However, the Employer does and must know what it wants and must communicate its needs to the Bidders. Hence, this section on Employer’s Requirements replaces the usual Technical Specifications of a more traditional approach.

- While this section of the bidding document should endeavor to define the Employer’s Requirements as precisely as possible, care must be taken to avoid over specifying details to the extent that the flexibility and potential benefits associated with a design, supply and install contract are seriously eroded or threatened.

- Care must be taken when drafting the Employer’s Requirements to ensure that the requirements are not restrictive. Recognized international standards should be used as much as possible for the description of goods, materials and workmanship. Where other particular standards are specified, whether national standards of the Borrower’s Country or other standards, it should be stated that goods, materials and workmanship meeting other authoritative standards and which promise to ensure equal or higher quality than the standards specified, will also be acceptable. Where a brand name of a product is specified it should always be qualified with the terms “or equivalent.”

- For a design, supply and install contract no detail drawings would generally be available at the pre-Bidding process stage. It would, however, be useful to include such conceptual drawings as are appropriate to supplement or help explain the general concept of the Employer’s needs.

- The Employer should specify any Environmental, Social, health, and safety requirements as appropriate.

- Where Bidders are invited to submit alternative technical solutions for specified parts of the Facilities, such parts shall be described in this Specification.

3. Drawings

<<Note>>

- It is customary to bind the drawings in a separate volume, which is often larger than other volumes of the Contract documents. The size will be dictated by the scale of the drawings, which must not be reduced to the extent that details are rendered illegible.

- A simplified map showing the location of the Site in relation to the local geography, including major roads, ports, airports, and railroads, is helpful.

- The construction drawings, even if not fully developed, must show sufficient details to enable bidders to understand the type and complexity of the work involved.

4. Supplementary Information

5. Certificates

##### 5.1 Form of Completion Certificate

Contract: [insert name of contract and contract identification details]

Date:

Certificate No.:

To:  [insert name and address of contractor]

Dear Ladies and/or Gentlemen,

Pursuant to GC Clause 24 (Completion of the Facilities) of the General Conditions entered into between yourselves and the Employer dated [insert date ], relating to the [brief description of the Facilities], we hereby notify you that the following part(s) of the Facilities was (were) complete on the date specified below, and that, in accordance with the terms of the Contract, the Employer hereby takes over the said part(s) of the Facilities, together with the responsibility for care and custody and the risk of loss thereof on the date mentioned below.

1.	Description of the Facilities or part thereof:  [insert description]

2.	Date of Completion:  [insert date]

However, you are required to complete the outstanding items listed in the attachment hereto as soon as practicable.

This letter does not relieve you of your obligation to complete the execution of the Facilities in accordance with the Contract nor of your obligations during the Defect Liability Period.

Very truly yours,

Title

(Project Manager)

##### 5.2 Form of Operational Acceptance Certificate

Contract: [insert name of contract and contract identification details]

Date:

Certificate No.:

To:  [insert name and address of contractor]

Pursuant to GC Sub-Clause 25.3 (Operational Acceptance) of the General Conditions entered into between yourselves and the Employer dated [insert date], relating to the [brief description of the facilities], we hereby notify you that the Functional Guarantees of the following part(s) of the Facilities were satisfactorily attained on the date specified below.

1.	Description of the Facilities or part thereof:  [insert description.]

2.	Date of Operational Acceptance:  [insert date]

This letter does not relieve you of your obligation to complete the execution of the Facilities in accordance with the Contract nor of your obligations during the Defect Liability Period.

Very truly yours,

Title

(Project Manager)

6. Change Orders

6.1	Change Order Procedure

6.1.1	General

6.1.2	Change Order Log

6.1.3	References for Changes

6.2.	Change Order Forms

6.2.1	Request for Change Proposal

6.2.2	Estimate for Change Proposal

6.2.3	Acceptance of Estimate

6.2.4	Change Proposal

6.2.5	Change Order

6.2.6	Pending Agreement Change Order

6.2.7	Application for Change Proposal

##### 6.1. 	Change Order Procedure

6.1.1 General

This section provides samples of procedures and forms for implementing changes in the Facilities during the performance of the Contract in accordance with GC Clause 39 (Change in the Facilities) of the General Conditions.

6.1.2 Change Order Log

The Contractor shall keep an up-to-date Change Order Log to show the current status of Requests for Change and Changes authorized or pending. Entries of the Changes in the Change Order Log shall be made to ensure that the log is up-to-date. The Contractor shall attach a copy of the current Change Order Log in the monthly progress report to be submitted to the Employer.

6.1.3 References for Changes

(1)	Request for Change as referred to in GCC Clause 39 shall be serially numbered CR-X-nnn.

(2)	Estimate for Change Proposal as referred to in GCC Clause 39 shall be serially numbered CN-X-nnn.

(3)	Acceptance of Estimate as referred to in GCC Clause 39 shall be serially numbered CA-X-nnn.

(4)	Change Proposal as referred to in GCC Clause 39 shall be serially numbered CP-X-nnn.

(5)	Change Order as referred to in GCC Clause 39 shall be serially numbered CO-X-nnn.

Note: (a)	Requests for Change issued from the Employer’s Home Office and the Site representatives of the Employer shall have the following respective references:

Home Office	CR-H-nnn

Site		CR-S-nnn

(b)	The above number “nnn” is the same for Request for Change, Estimate for Change Proposal, Acceptance of Estimate, Change Proposal and Change Order.

##### 6.2 	Change Order Forms

6.2.1  Request for Change Proposal Form

[Employer’s letterhead]

To:  [insert Contractor’s name and address]	Date:

Attention:  [insert name and title]

Contract Name:  [insert Contract name]

Contract Number:  [insert Contract number]

Dear Ladies and/or Gentlemen:

With reference to the captioned Contract, you are requested to prepare and submit a Change Proposal for the Change noted below in accordance with the following instructions within [insert number of days] days of the date of this letter [or on or before (date)].

1.	Title of Change:  [insert title]

2.	Change Request No./Rev.:  [insert number]

3.	Originator of Change:

Employer:  [insert name of Employer]

Contractor (by Application for Change Proposal No. [Number Refer to Annex 6.2.7])

4.	Brief Description of Change:  [insert description]

5.	Facilities and/or Item No. of equipment related to the requested Change:  [insert description]

6.	Reference drawings and/or technical documents for the request of Change:

Drawing No./Document No.		Description

7.	Detailed conditions or special requirements on the requested Change:  [insert description]

8.	General Terms and Conditions:

(a)	Please submit your estimate showing what effect the requested Change will have on the Contract Price.

(b)	Your estimate shall include your claim for the additional time, if any, for completing the requested Change.

(c)	If you have any opinion that is critical to the adoption of the requested Change in connection with the conformability to the other provisions of the Contract or the safety of the Plant or Facilities, please inform us in your proposal of revised provisions.

(d)	Any increase or decrease in the work of the Contractor relating to the services of its personnel shall be calculated.

(e)	You shall not proceed with the execution of the work for the requested Change until we have accepted and confirmed the amount and nature in writing.

(Employer’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

6.2.2   Estimate for Change Proposal Form

[Contractor’s letterhead]

To:  [insert Employer's name and address]	Date:

Attention:  [insert name and title]

Contract Name:  [insert Contract name]

Contract Number:  [insert Contract number]

Dear Ladies and/or Gentlemen:

With reference to your Request for Change Proposal, we are pleased to notify you of the approximate cost to prepare the below-referenced Change Proposal in accordance with GC Sub-Clause 39.2.1 of the General Conditions. We acknowledge that your agreement to the cost of preparing the Change Proposal, in accordance with GC Sub-Clause 39.2.2, is required before estimating the cost for change work.

1.	Title of Change:  [insert title]

2.	Change Request No./Rev.:  [insert number]

3.	Brief Description of Change:  [insert description]

4.	Scheduled Impact of Change:  [insert description]

5.	Cost for Preparation of Change Proposal:  [insert costs, which shall be in the currencies of the contract]

(a)	Engineering                                                             (Amount)

(i)	Engineer		 hrs x 	 rate/hr =

(ii)	Draftsperson		 hrs x 	 rate/hr =

Sub-total		 hrs

Total Engineering Cost

(b)	Other Cost

Total Cost (a) + (b)

(Contractor’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

6.2.3  Acceptance of Estimate Form

[Employer’s letterhead]

To:  [insert Contractor’s name and address]	Date:

Attention:  [insert name and title]

Contract Name:  [insert Contract name]

Contract Number:  [insert Contract number]

Dear Ladies and/or Gentlemen:

We hereby accept your Estimate for Change Proposal and agree that you should proceed with the preparation of the Change Proposal.

1.	Title of Change:  [insert Title]

2.	Change Request No./Rev.:  [insert Request number/revision]

3.	Estimate for Change Proposal No./Rev.:  [insert Proposal number/revision]

4.	Acceptance of Estimate No./Rev.:  [insert Estimate number/revision]

5.	Brief Description of Change:  [insert description]

6.	Other Terms and Conditions: In the event that we decide not to order the Change accepted, you shall be entitled to compensation for the cost of preparing the Change Proposal described in your Estimate for Change Proposal mentioned in para. 3 above in accordance with GC Clause 39 of the General Conditions.

(Employer’s Name)

(Signature)

(Name of Title of signatory)

6.2.4  Change Proposal Form

[Contractor’s letterhead]

To:  [insert Employer's name and address]	Date:

Attention:  [insert name and title]

Contract Name:  [insert Contract name]

Contract Number:  [insert Contract number]

Dear Ladies and/or Gentlemen:

In response to your Request for Change Proposal No. [insert number], we hereby submit our proposal as follows:

1.	Title of Change:  [insert title]

2.	Change Proposal No./Rev.:  [insert Proposal number / revision ]

3.	Originator of Change:  Employer:  [insert name of Employer]

Contractor:  [insert name of Contractor]

4.	Brief Description of Change:  [insert description]

5.	Reasons for Change:  [insert reason]

6.	Facilities and/or Item No. of Equipment related to the requested Change:  [insert description]

7.	Reference drawings and/or technical documents for the requested Change:

Drawing No./Document No.		Description

8.	Estimate of increase/decrease to the Contract Price resulting from the Change Proposal:

Amount

[insert amounts in the currencies of the Contract]

(a)	Direct material

(b)	Major construction equipment

(c)	Direct field labor (Total 	 hrs)

(d)	Subcontracts

(e)	Indirect material and labor

(f)	Site supervision

(g)	Head office technical staff salaries

Process engineer			 hrs @ 	 rate/hr

Project engineer			 hrs @ 	 rate/hr

Equipment engineer		 hrs @ 	 rate/hr

Procurement			 hrs @ 	 rate/hr

Draftsperson			 hrs @ 	  rate/hr

Total			hrs

(h)	Extraordinary costs (computer, travel, etc.)

(i)	Fee for general administration, 	% of Items

(j)	Taxes and customs duties

Total lump sum cost of Change Proposal

[Sum of items (a) to (j)]

Cost to prepare Estimate for Change Proposal

[Amount payable if Change is not accepted]

9.	Additional time for Completion required due to Change Proposal

10.	Effect on the Functional Guarantees

11.	Effect on the other terms and conditions of the Contract

12.	Validity of this Proposal:  within [Number] days after receipt of this Proposal by the Employer

13.	Other terms and conditions of this Change Proposal:

(a)	You are requested to notify us of your acceptance, comments or rejection of this detailed Change Proposal within [Number] days from your receipt of this Proposal.

(b)	The amount of any increase and/or decrease shall be taken into account in the adjustment of the Contract Price.

(c)	Contractor’s cost for preparation of this Change Proposal: [insert amount. This cost shall be reimbursed by the employer in case of employer’s withdrawal or rejection of this Change Proposal without default of the contractor in accordance with GCC Clause 39 of the General Conditions]

(Contractor’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

6.2.5  Change Order Form

[Employer’s letterhead]

To:  [insert Contractor’s name and address]	Date:

Attention:  [insert name and title]

Contract Name:  [insert Contract name]

Contract Number:  [insert Contract number]

Dear Ladies and/or Gentlemen:

We approve the Change Order for the work specified in the Change Proposal (No. [number]), and agree to adjust the Contract Price, Time for Completion, and/or other conditions of the Contract in accordance with GC Clause 39 of the General Conditions.

1.	Title of Change:  [insert title]

2.	Change Request No./Rev.:  [insert Request number / revision]

3.	Change Order No./Rev.:  [insert Order number / revision]

4.	Originator of Change:	Employer:  [insert name of Employer]

Contractor:  [insert name of Contractor]

5.	Authorized Price:

Ref. No.:  [insert number]	Date:  [insert date]

Foreign currency portion [insert amount] plus Local currency portion [insert amount]

6.	Adjustment of Time for Completion

None		Increase [insert number] days		Decrease [insert number] days

7.	Other effects, if any

Authorized by:  		Date:

(Employer)

Accepted by:  		Date:

(Contractor)

6.2.6  Pending Agreement Change Order Form

[Employer’s letterhead]

To:  [insert Contractor’s name and address]	Date:

Attention:  [insert name and title]

Contract Name:  [insert Contract name]

Contract Number:  [insert Contract number]

Dear Ladies and/or Gentlemen:

We instruct you to carry out the work in the Change Order detailed below in accordance with GC Clause 39 of the General Conditions.

1.	Title of Change:  [insert title]

2.	Employer’s Request for Change Proposal No./Rev.:  [insert number/revision]	dated:  [insert date]

3.	Contractor’s Change Proposal No./Rev.:  [insert number / revision]	dated:  [insert  date]

4.	Brief Description of Change:  [insert description]

5.	Facilities and/or Item No. of equipment related to the requested Change:  [insert description]

6.	Reference Drawings and/or technical documents for the requested Change:

Drawing No./Document No.		Description

7.	Adjustment of Time for Completion:

8.	Other change in the Contract terms:

9.	Other terms and conditions:

(Employer’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

6.2.7  Application for Change Proposal Form

[Contractor’s letterhead]

To:  [insert Employer's name and address]	Date:

Attention:  [insert name and title]

Contract Name:  [insert Contract name]

Contract Number:  [insert Contract number]

Dear Ladies and/or Gentlemen:

We hereby propose that the work mentioned below be treated as a Change in the Facilities.

1.	Title of Change:  [insert title]

2.	Application for Change Proposal No./Rev.:  [insert Number / revision]	dated:  [insert date]

3.	Brief Description of Change:  [insert description]

4.	Reasons for Change:

5.	Order of Magnitude Estimation (amount in the currencies of the Contract): [insert amount]

6.	Scheduled Impact of Change:

7.	Effect on Functional Guarantees, if any:

8.	Appendix:

(Employer’s Name)

(Signature)

(Name of signatory)

(Title of signatory)

7. Personnel Requirements

Using Form PER - 1 and PER - 2 in Section IV (Bidding Forms), the Bidder must demonstrate that it has personnel who meet the following requirements:

| No. | Position | Total Work Experience [years] | Experience In Similar Work [years] |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |

8. Equipment Requirements

Using Form EQU in Section IV (Bidding Forms), the Bidder must demonstrate that it has the key equipment listed below:

| No. | Equipment Type and Characteristics | Minimum Number Required |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |

PART 3 – Conditions of Contract and Contract Forms

Section VII. General Conditions

These General Conditions (GC) are based on the Model Form of International Contract for Process Plant Construction published by the Engineering Advancement Association of Japan (ENNA). The GC contain general clauses to be applied on all contracts. The GC in this section, read in conjunction with the Particular Conditions in Section VIII and other documents listed therein, should be a complete document expressing all the rights and obligations of the contracting parties. The General Conditions herein shall not be altered.

Table of Clauses

A.  Contract and Interpretation	256

1.	Definitions	256

2.	Contract Documents	259

3.	Interpretation	260

4. 	Communications	261

5.	Law and Language	262

6.	Fraud and Corruption	262

B.  Subject Matter of Contract	263

7.	Scope of Facilities	263

8.	Time for Commencement and Completion	264

9.	Contractor’s Responsibilities	264

10.	Employer’s Responsibilities	266

C.  Payment	268

11.	Contract Price	268

12.	Terms of Payment	268

13.	Securities	268

14.	Taxes and Duties	270

D.  Intellectual Property	271

15.	License/Use of Technical Information	271

16.	Confidential Information	271

E.   Execution of the Facilities	272

17.	Representatives	272

18.	Work Program	274

19. 	Subcontracting	276

20.	Design and Engineering	276

21.	Procurement	279

22.	Installation	280

23.	Test and Inspection	288

24.	Completion of the Facilities	290

25. Commissioning and Operational Acceptance	292

F.  Guarantees and Liabilities	295

26.	Completion Time Guarantee	295

27.	Defect Liability	296

28.	Functional Guarantees	299

29.	Patent Indemnity	300

30.	Limitation of Liability	301

G.  Risk Distribution	301

31.	Transfer of Ownership	301

32.	Care of Facilities	302

33.	Loss of or Damage to Property; Accident or Injury to Workers; Indemnification	303

34.	Insurance	304

35.	Unforeseen Conditions	307

36.	Change in Laws and Regulations	308

37.	Force Majeure	309

38.	War Risks	310

H.  Change in Contract Elements	312

39.	Change in the Facilities	312

40.	Extension of Time for Completion	315

41.	Suspension	317

42.	Termination	318

43.	Assignment	325

I.  Claims, Disputes, and Arbitration	325

44.	Contractor’s Claims	325

45. 	Disputes and Arbitration	327

#### A.  Contract and Interpretation

| ##### 1. Definitions |  | ##### 1.1 The following words and expressions shall have the meanings hereby assigned them: - “Commissioning” means operation of the Facilities or any part thereof by the Contractor following Completion, which operation is to be carried out by the Contractor as provided in GC Sub-Clause 25.1 (Commissioning) hereof, for the purpose of carrying out Guarantee Test(s). - “Completion” means that the Facilities (or a specific part thereof where specific parts are specified in the Contract) have been completed operationally and structurally and put in a tight and clean condition, that all work in respect of Pre-commissioning of the Facilities or such specific part thereof has been completed, and that the Facilities or specific part thereof are ready for Commissioning as provided in GC Clause 24 (Completion) hereof. - “Construction Manager” means the person appointed by the Contractor’s Representative in the manner provided in GC Sub-Clause 17.2.4. - “Contract” means the Contract Agreement entered into between the Employer and the Contractor, together with the Contract Documents referred to therein; they shall constitute the Contract, and the term “the Contract” shall in all such documents be construed accordingly. - “Contract Documents” means the documents listed in Article 1.1 (Contract Documents) of the Contract Agreement (including any amendments thereto). - “Contract Price” means the sum specified in Article 2.1 (Contract Price) of the Contract Agreement, subject to such additions and adjustments thereto or deductions therefrom, as may be made pursuant to the Contract. - “Contractor” means the person(s) named as Contractor in the Contract Agreement, and includes the legal successors or permitted assigns of the Contractor. - “Contractor’s Equipment” means all facilities, equipment, machinery, tools, apparatus, appliances, or things of every kind required in or for installation, completion and maintenance of Facilities that are to be provided by the Contractor, but does not include Plant, or other things intended to form or forming part of the Facilities. - “Contractor’s Personnel” means all personnel whom the Contractor utilizes in the execution of the Contract, including the staff, labor and other employees of the Contractor and each Subcontractor; and any other personnel assisting the Contractor in the execution of the Contract. - “Contractor’s Representative” means any person nominated by the Contractor and approved by the Employer in the manner provided in GC Sub-Clause 17.2 (Contractor’s Representative and Construction Manager) hereof to perform the duties delegated by the Contractor. - “Country of Origin” means the countries and territories eligible under the rules of the Bank as further elaborated in the PC. - “day” means calendar day. - “Defect Liability Period” means the period of validity of the warranties given by the Contractor commencing at Completion of the Facilities or a part thereof, during which the Contractor is responsible for defects with respect to the Facilities (or the relevant part thereof) as provided in GC Clause 27 (Defect Liability) hereof. - “Dispute Board” (DB) means the person or persons named as such in the PC appointed by agreement between the Employer and the Contractor to make a decision on or to settle any dispute or difference between the Employer and the Contractor referred to him or her by the Parties pursuant to GC Sub-Clause 45.1 (Dispute Board) hereof. - “Effective Date” means the date of fulfillment of all conditions stated in Article 3 (Effective Date) of the Contract Agreement, from which the period until the Time for Completion shall be counted. - “Employer” means the person named as such in the PC and includes the legal successors or permitted assigns of the Employer. - “Employer’s Personnel” means all staff, labor and other employees of the Project Manager and of the Employer engaged in fulfilling the Employer’s obligations under the Contract; and any other personnel identified as Employer’s Personnel, by a notice from the Employer to the Contractor. - “Employer’s Requirements” means the document entitled employer’s requirements, as included in the Contract, and any additions and modifications to such document in accordance with the Contract. Such document includes Drawings, Specifications, and any other documents specifying the purpose, scope, and/or design and/or other technical criteria, for the Facilities. - “Facilities” means the Plant to be supplied and installed, as well as all the Installation Services to be carried out by the Contractor under the Contract. - “GC” means the General Conditions. - “Guarantee Test(s)” means the test(s) specified in the Employer’s Requirements to be carried out to ascertain whether the Facilities or a specified part thereof is able to attain the Functional Guarantees specified in the Appendix (Functional Guarantees) to the Contract Agreement in accordance with the provisions of GC Sub-Clause 25.2 (Guarantee Test) hereof. - “Installation Services” means all those services ancillary to the supply of the Plant for the Facilities, to be provided by the Contractor under the Contract, such as transportation and provision of marine or other similar insurance, inspection, expediting, site preparation works (including the provision and use of Contractor’s Equipment and the supply of all construction materials required), installation, testing, pre-commissioning, commissioning, operations, maintenance, the provision of operations and maintenance manuals, training, etc. as the case may require. - “Letter of Acceptance” means the letter of formal acceptance, signed by the Employer, of the Letter of Bid, including any annexed memoranda comprising agreements between and signed by both Parties. If there is no such letter of acceptance, the expression “Letter of Acceptance” means the Contract Agreement and the date of issuing or receiving the Letter of Acceptance means the date of signing the Contract Agreement. - “month” means calendar month. - “Operational Acceptance” means the acceptance by the Employer of the Facilities (or any part of the Facilities where the Contract provides for acceptance of the Facilities in parts), which certifies the Contractor’s fulfillment of the Contract in respect of Functional Guarantees of the Facilities (or the relevant part thereof) in accordance with the provisions of GC Clause 28 (Functional Guarantees) hereof and shall include deemed acceptance in accordance with GC Clause 25 (Commissioning and Operational Acceptance) hereof. - “Party” means the Employer or the Contractor, as the context requires, and “Parties” means both of them. - “PC” means the Particular Conditions. - “Performance Security” means the security (or securities, if any) under GC Sub-Clause 13.3 (Performance Security). - “Plant” means permanent plant, equipment, machinery, apparatus, articles and things of all kinds to be provided and incorporated in the Facilities by the Contractor under the Contract (including the spare parts to be supplied by the Contractor under GC Sub-Clause 7.3 hereof), but does not include Contractor’s Equipment. - “Pre-commissioning” means the testing, checking and other requirements specified in the Employer’s Requirements that are to be carried out by the Contractor in preparation for Commissioning as provided in GC Clause 24 (Completion) hereof. - “Project Manager” means the person appointed by the Employer in the manner provided in GC Sub-Clause 17.1 (Project Manager) hereof and named as such in the PC to perform the duties delegated by the Employer. - “Site” means the land and other places upon which the Facilities are to be installed, and such other land or places as may be specified in the Contract as forming part of the Site. - “Subcontractor,” including manufacturers, means any person to whom execution of any part of the Facilities, including preparation of any design or supply of any Plant, is sub-contracted directly or indirectly by the Contractor, and includes its legal successors or permitted assigns. - “The Bank” means the financing institution named in the PC. - “Time for Completion” means the time within which Completion of the Facilities as a whole (or of a part of the Facilities where a separate Time for Completion of such part has been prescribed) is to be attained, as referred to in GC Clause 8 and in accordance with the relevant provisions of the Contract. - “year” means 365 days. |  |
| --- | --- | --- | --- |
| 2. Contract Documents |  | 2.1 Subject to Article 1.2 (Order of Precedence) of the Contract Agreement, all documents forming part of the Contract (and all parts thereof) are intended to be correlative, complementary and mutually explanatory. The Contract shall be read as a whole. |  |
| 3. Interpretation |  | 3.1 In the Contract, except where the context requires otherwise: - words indicating one gender include all genders; - words indicating the singular also include the plural and words indicating the plural also include the singular; - provisions including the word “agree,” “agreed,” or “agreement” require the agreement to be record in writing; - the word “tender” is synonymous with “bid,” “tenderer” with “Bidder,” and “tender documents” with “Bidding Documents;” and - “written” or “in writing” means hand-written, type-written, printed or electronically made, and resulting in a permanent record. The marginal words and other headings shall not be taken into consideration in the interpretation of these Conditions. 3.2 Incoterms Unless inconsistent with any provision of the Contract, the meaning of any trade term and the rights and obligations of Parties thereunder shall be as prescribed by Incoterms. “Incoterms” means international rules for interpreting trade terms published by the International Chamber of Commerce (latest edition), 38 Cours Albert 1er, 75008 Paris, France. 3.3 Entire Agreement Subject to GC Sub-Clause 16.4 hereof, the Contract constitutes the entire agreement between the Employer and Contractor with respect to the subject matter of Contract and supersedes all communications, negotiations, and agreements (whether written or oral) of Parties with respect thereto made prior to the date of Contract. 3.4 Amendment No amendment or other variation of the Contract shall be effective unless it is in writing, is dated, expressly refers to the Contract, and is signed by a duly authorized representative of each Party hereto. 3.5 Independent Contractor The Contractor shall be an independent contractor performing the Contract. The Contract does not create any agency, partnership, joint venture, or other joint relationship between the Parties hereto. Subject to the provisions of the Contract, the Contractor shall be solely responsible for the manner in which the Contract is performed. All employees, representatives, or Subcontractors engaged by the Contractor in connection with the performance of the Contract shall be under the complete control of the Contractor and shall not be deemed to be employees of the Employer, and nothing contained in the Contract or in any subcontract awarded by the Contractor shall be construed to create any contractual relationship between any such employees, representatives, or Subcontractors and the Employer. 3.6 Non-Waiver 3.6.1 Subject to GC Sub-Clause 3.6.2 below, no relaxation, forbearance, delay, or indulgence by either Party in enforcing any of the terms and conditions of the Contract or the granting of time by either Party to the other shall prejudice, affect, or restrict the rights of that Party under the Contract, nor shall any waiver by either Party of any breach of Contract operate as waiver of any subsequent or continuing breach of Contract. 3.6.2 Any waiver of a Party’s rights, powers, or remedies under the Contract must be in writing, must be dated, and signed by an authorized representative of the Party granting such waiver, and must specify the right and the extent to which it is being waived. 3.7 Severability If any provision or condition of the Contract is prohibited or rendered invalid or unenforceable, such prohibition, invalidity, or unenforceability shall not affect the validity or enforceability of any other provisions and conditions of the Contract. 3.8 Country of Origin “Origin” means the place where the plant and component parts thereof are mined, grown, produced, or manufactured, and from which the services are provided. Plant components are produced when, through manufacturing, processing, or substantial or major assembling of components, a commercially recognized product results that is substantially in its basic characteristics or in purpose or utility from its components. |  |
| 4. Communications |  | 4.1 Wherever these Conditions provide for the giving or issuing of approvals, certificates, consents, determinations, notices, requests, and discharges, these communications shall be: - in writing and delivered against receipt; and - delivered, sent, or transmitted to the address for the recipient’s communications as stated in the Contract Agreement. When a certificate is issued to a Party, the certifier shall send a copy to the other Party. When a notice is issued to a Party, by the other Party or the Project Manager, a copy shall be sent to the Project Manager or the other Party, as the case may be. |  |
| 5. Law and Language |  | 5.1 The Contract shall be governed by and interpreted in accordance with laws of the country specified in the PC. 5.2 The ruling language of the Contract shall be that stated in the PC. 5.3 The language for communications shall be the ruling language unless otherwise stated in the PC. |  |
| 6. Fraud and Corruption |  | 6.1 If the Employer determines, based on reasonable evidence, that the Contractor has engaged in corrupt, fraudulent practices, in competing for or in executing the Contract, then the Employer may, after giving fourteen (14) days’ notice to the Contractor, terminate the Contractor’s employment under the Contract and expel him from the Site, and the provisions of Clause 42 shall apply as if such expulsion had been made under Sub-Clause 42.2.1 (c). For the purpose of this provision, the terms are defined as follows: - “corrupt practice” means the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence the action of a public official in the procurement process or in contract execution; and - “fraudulent practice” means a misrepresentation or omission of facts in order to influence a procurement process or the execution of a contract. |  |
|  |  | 6.2 All Bidders, consultants, contractors, suppliers, and other third parties engaged or involved in Bank-related activities have a duty to cooperate fully in any screening or investigation when requested by the Bank to do so. Such cooperation includes, but is not limited to, the following: - being available to be interviewed and replying fully and truthfully to all questions asked; - providing the Bank with any items requested that are within the Party’s control including, but not limited to, documents and other physical objects; - upon written request by the Bank, authorizing other related entities to release directly to the Bank such information that is specifically and materially related, directly or indirectly, to the said entities or issues which are the subject of the investigation; - cooperating with all reasonable requests to search or physically inspect their person and/or work areas, including files, electronic databases, and personal property used on Bank activities, or that utilizes Bank’s Information and Communications Technology (ICT) resources or systems (including mobile phones, personal electronic devices, and electronic storage devices such as external disk drives); - cooperating in any testing requested by the Bank, including but not limited to, fingerprint identification, handwriting analysis, and physical examination and analysis; and - preserving and protecting confidentiality of all information discussed with, and as required by, the Bank. 6.3 All Bidders, consultants, contractors and suppliers shall ensure that, in its contract with its sub-consultants, subcontractors, and other third parties engaged or involved in Bank-related activities, such sub-consultants, subcontractors, and other third parties similarly undertake the foregoing duty to cooperate fully in any screening or investigation when requested by the Bank to do so. |  |

#### B.  Subject Matter of Contract

| 7. Scope of Facilities | 7.1 Unless otherwise expressly limited in the Employer’s Requirements, the Contractor’s obligations cover the provision of all Plant and the performance of all Installation Services required for the design, the manufacture (including procurement, quality assurance, construction, installation, associated civil works, pre-commissioning and delivery) of the Plant and the installation, completion, and commissioning of the Facilities in accordance with the plans, procedures, specifications, drawings, codes, and any other documents as specified in the section Employer’s Requirements. Such specifications include, but are not limited to, the provision of supervision and engineering services; the supply of labor, materials, equipment, spare parts (as specified in GC Sub-Clause 7.3 below) and accessories; Contractor’s Equipment; construction utilities and supplies; temporary materials, structures, and facilities; transportation (including, without limitation, unloading and hauling to, from and at the Site); and storage, except for those supplies, works, and services that will be provided or performed by the Employer, as set forth in the Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement. 7.2 The Contractor shall, unless specifically excluded in the Contract, perform all such work and/or supply all such items and materials not specifically mentioned in the Contract but that can be reasonably inferred from the Contract as being required for attaining Completion of the Facilities as if such work and/or items and materials were expressly mentioned in the Contract. 7.3 In addition to the supply of Mandatory Spare Parts included in the Contract, the Contractor agrees to supply spare parts required for the operation and maintenance of the Facilities for the period specified in the PC and the provisions, if any, specified in the PC. However, the identity, specifications, and quantities of such spare parts and the terms and conditions relating to the supply thereof are to be agreed between the Employer and the Contractor, and the price of such spare parts shall be that given in Price Schedule, which shall be added to the Contract Price. The price of such spare parts shall include the purchase price therefore and other costs and expenses (including the Contractor’s fees) relating to the supply of spare parts. |
| --- | --- |
| 8. Time for Commencement and Completion | 8.1 The Contractor shall commence work on the Facilities within the period specified in the PC and without prejudice to GC Sub-Clause 26.2 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified in the Appendix 4 (Time Schedule) to the Contract Agreement. 8.2 The Contractor shall attain Completion of the Facilities or of a part where a separate time for Completion of such part is specified in the Contract, within the time stated in the PC or within such extended time to which the Contractor shall be entitled under GC Clause 40 hereof. |
| 9. Contractor’s Responsibilities | 9.1 The Contractor shall design, manufacture, including associated purchases and/or subcontracting, install, and complete the Facilities in accordance with the Contract. When completed, the Facilities should be fit for the purposes for which they are intended as defined in the Contract. 9.2 The Contractor confirms that it has entered into this Contract on the basis of a proper examination of the data relating to the Facilities, including any data as to boring tests provided by the Employer, and on the basis of information that the Contractor could have obtained from a visual inspection of the Site if access thereto was available and of other data readily available to it relating to the Facilities as of the date twenty-eight (28) days prior to bid submission. The Contractor acknowledges that any failure to acquaint itself with all such data and information shall not relieve its responsibility for properly estimating the difficulty or cost of successfully performing the Facilities. 9.3 The Contractor shall acquire and pay for all permits, approvals, and/or licenses from all local, state, or national government authorities or public service undertakings in the country where the Site is located, which such authorities or undertakings require the Contractor to obtain in its name and which are necessary for the performance of the Contract, including, without limitation, visas for the Contractor’s and Subcontractor’s personnel and entry permits for all imported Contractor’s Equipment. The Contractor shall acquire all other permits, approvals, and/or licenses that are not the responsibility of the Employer under GC Sub-Clause 10.3 hereof and that are necessary for the performance of the Contract. 9.4 The Contractor shall comply with all laws in force in the country where the Facilities are to be implemented. The laws will include all local, state, national, or other laws that affect the performance of the Contract and bind upon the Contractor. The Contractor shall indemnify and hold harmless the Employer from and against any and all liabilities, damages, claims, fines, penalties, and expenses of whatever nature arising or resulting from the violation of such laws by the Contractor or its personnel, including the Subcontractors and their personnel, but without prejudice to GC Sub-Clause 10.1 hereof. 9.5 Any Plant and Installation Services that will be incorporated in or be required for the Facilities and other supplies shall have their origin as specified under GC Clause 1 (Country of Origin). Any Subcontractors retained by the Contractor shall be from a country as specified in GC Clause 1 (Country of Origin). - The Contractor shall permit the Bank to inspect the Contractor’s accounts and records relating to the performance of the Contractor and to have them audited by auditors appointed by the Bank, if so required by the Bank. - If the Contractor is a joint venture or consortium of two or more persons, all such persons shall be jointly and severally bound to the Employer for the fulfillment of the provisions of the Contract and shall designate one of such persons to act as a leader with authority to bind the joint venture or consortium. The composition or the constitution of the joint venture or consortium shall not be altered without the prior consent of the Employer. - Protection of the Environment - The Contractor shall take all reasonable steps to protect the environment (both on and off the Site) and to limit damage and nuisance to people and property resulting from pollution, noise, and other results of his operations. - The Contractor shall ensure that emissions, surface discharges, and effluent from the Contractor’s activities shall not exceed the values stated in the Specification or prescribed by applicable Laws. |
| 10. Employer’s Responsibilities | 10.1 All information and/or data to be supplied by the Employer as described in the Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement shall be deemed to be accurate, except when the Employer expressly states otherwise, and the Contractor shall not be liable for the consequences of any discrepancies, errors, omissions or inaccuracies in such information and/or data. 10.2 The Employer shall be responsible for acquiring and providing legal and physical possession of the Site and access thereto, and for providing possession of and access to all other areas reasonably required for the proper execution of the Contract, including all requisite rights of way, as specified in the Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement. The Employer shall give full possession of and accord all rights of access thereto on or before the date(s) specified in that Appendix. 10.3 The Employer shall acquire and pay for all permits, approvals, and/or licenses from all local, state, or national government authorities, or public service undertakings in the country where the Site is located which (a) such authorities or undertakings require the Employer to obtain in the Employer’s name, (b) are necessary for the execution of the Contract, including those required for the performance by both the Contractor and the Employer of their respective obligations under the Contract, and (c) are specified in the Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement. 10.4 If requested by the Contractor, the Employer shall use its best endeavors to assist the Contractor in obtaining in a timely and expeditious manner all permits, approvals, and/or licenses necessary for the execution of the Contract from all local, state, or national government authorities, or public service undertakings that such authorities or undertakings require the Contractor or Subcontractors or the personnel of the Contractor or Subcontractors, as the case may be, to obtain. 10.5 Unless otherwise specified in the Contract or agreed upon by the Employer and the Contractor, the Employer shall provide sufficient, properly qualified operating and maintenance personnel; shall supply and make available all raw materials, utilities, lubricants, chemicals, catalysts, other materials and facilities; and shall perform all work and services of whatsoever nature, including those required by the Contractor to properly carry out Pre-commissioning, Commissioning, and Guarantee Tests, all in accordance with the provisions of the Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement at or before the time specified in the program furnished by the Contractor under GC Sub-Clause 18.2 hereof and in the manner thereupon specified or as otherwise agreed upon by the Employer and the Contractor. 10.6 The Employer shall be responsible for the continued operation of the Facilities after Completion, in accordance with GC Sub-Clause 24.8, and shall be responsible for facilitating the Guarantee Test(s) for the Facilities, in accordance with GC Sub-Clause 25.2. - All costs and expenses involved in the performance of the obligations under this GC Clause 10 shall be the responsibility of the Employer, except those incurred by the Contractor with respect to the performance of Guarantee Tests, in accordance with GC Sub-Clause 25.2. - In the event that the Employer shall be in breach of any of his obligations under this Clause, the additional cost incurred by the Contractor in consequence thereof shall be determined by the Project Manager and added to the Contract Price. |

#### C.  Payment

| 11. Contract Price | 11.1 The Contract Price shall be as specified in Article 2 (Contract Price and Terms of Payment) of the Contract Agreement. 11.2 Unless an adjustment clause is provided for in the PC, the Contract Price shall be a firm lump sum not subject to any alteration, except in the event of a Change in the Facilities or as otherwise provided in the Contract. 11.3 Subject to GC Sub-Clauses 9.2, 10.1, and 35 hereof, the Contractor shall be deemed to have satisfied itself as to the correctness and sufficiency of the Contract Price, which shall, except as otherwise provided for in the Contract, cover all its obligations under the Contract. |
| --- | --- |
| 12. Terms of Payment | 12.1 The Contract Price shall be paid as specified in Article 2 (Contract Price and Terms of Payment) of the Contract Agreement and in the Appendix (Terms and Procedures of Payment) to the Contract Agreement, which also outlines the procedures to be followed in making application for and processing payments. 12.2 No payment made by the Employer herein shall be deemed to constitute acceptance by the Employer of the Facilities or any part(s) thereof. 12.3 In the event that the Employer fails to make any payment by its respective due date or within the period set forth in the Contract, the Employer shall pay to the Contractor interest on the amount of such delayed payment at the rate(s) shown in the Appendix (Terms and Procedures of Payment) to the Contract Agreement for the period of delay until payment has been made in full, whether before or after judgment or arbitrage award. 12.4 The currency or currencies in which payments are made to the Contractor under this Contract shall be specified in the Appendix (Terms and Procedures of Payment) to the Contract Agreement, subject to the general principle that payments will be made in the currency or currencies in which the Contract Price has been stated in the Contractor’s bid. |
| 13. Securities | 13.1 Issuance of Securities The Contractor shall provide the securities specified below in favor of the Employer at the times, and in the amount, manner, and form specified below. 13.2 Advance Payment Security 13.2.1 The Contractor shall, within twenty-eight (28) days of the notification of contract award, provide a security in an amount equal to the advance payment calculated in accordance with the Appendix (Terms and Procedures of Payment) to the Contract Agreement, and in the same currency or currencies. 13.2.2 The security shall be in the form provided in the Bidding Documents or in another form acceptable to the Employer. The amount of the security shall be reduced in proportion to the value of the Facilities executed by and paid to the Contractor from time to time, and shall automatically become null and void when the full amount of the advance payment has been recovered by the Employer. The security shall be returned to the Contractor immediately after its expiration. 13.3 Performance Security 13.3.1 The Contractor shall, within twenty-eight (28) days of the notification of contract award, provide a security for the due performance of the Contract in the amount specified in the PC. 13.3.2 The performance security shall be denominated in the currency or currencies of the Contract, or in a freely convertible currency acceptable to the Employer, and shall be in one of the forms of bank guarantees provided in the Bidding Documents, as stipulated by the Employer in the PC, or in another form acceptable to the Employer. - Unless otherwise specified in the PC, the security shall be reduced by half on the date of the Operational Acceptance. The Security shall become null and void, or shall be reduced pro rata to the Contract Price of a part of the Facilities for which a separate Time for Completion is provided, five hundred and forty (540) days after Completion of the Facilities or three hundred and sixty five (365) days after Operational Acceptance of the Facilities, whichever occurs first; provided, however, that if the Defects Liability Period has been extended on any part of the Facilities pursuant to GC Sub-Clause 27.8 hereof, the Contractor shall issue an additional security in an amount proportionate to the Contract Price of that part. The security shall be returned to the Contractor immediately after its expiration, provided, however, that if the Contractor, pursuant to GC Sub-Clause 27.10, is liable for an extended defect liability obligation, the performance security shall be extended for the period and up to the amount specified in the PC. - The Employer shall not make a claim under the Performance Security, except for amounts to which the Employer is entitled under the Contract. The Employer shall indemnify and hold the Contractor harmless against and from all damages, losses and expenses (including legal fees and expenses) resulting from a claim under the Performance Security to the extent to which the Employer was not entitled to make the claim. |
| 14. Taxes and Duties | 14.1 Except as otherwise specifically provided in the Contract, the Contractor shall bear and pay all taxes, duties, levies, and charges assessed on the Contractor, its Subcontractors, or their employees by all municipal, state, or national government authorities in connection with the Facilities in and outside of the country where the Site is located. 14.2 Notwithstanding GC Sub-Clause 14.1 above, the Employer shall bear and promptly pay: - all customs and import duties for the Plant specified in the Price Schedule No.1; and - other domestic taxes such as sales tax and value added tax (VAT) on the Plant specified in Price Schedules No.1 and No.2 and that is to be incorporated into the Facilities, and on the finished goods, imposed by the law of the country where the Site is located. 14.3 If any tax exemptions, reductions, allowances, or privileges may be available to the Contractor in the country where the Site is located, the Employer shall use its best endeavors to enable the Contractor to benefit from any such tax savings to the maximum allowable extent. 14.4 For the purpose of the Contract, it is agreed that the Contract Price specified in Article 2 (Contract Price and Terms of Payment) of the Contract Agreement is based on the taxes, duties, levies, and charges prevailing at the date twenty-eight (28) days prior to the date of bid submission in the country where the Site is located (hereinafter called “Tax” in this GC Sub-Clause 14.4). If any rates of Tax are increased or decreased, a new Tax is introduced, an existing Tax is abolished, or any change in interpretation or application of any Tax occurs in the course of the performance of Contract, which was or will be assessed on the Contractor, Subcontractors, or their employees in connection with performance of the Contract, an equitable adjustment of the Contract Price shall be made to fully take into account any such change by addition to the Contract Price or deduction therefrom, as the case may be, in accordance with GC Clause 36 hereof. |

#### D.  Intellectual Property

| 15. License/Use of Technical Information | 15.1 For the operation and maintenance of the Plant, the Contractor hereby grants a non-exclusive and nontransferable license (without the right to sublicense) to the Employer under the patents, utility models, or other industrial property rights owned by the Contractor or by a third Party from whom the Contractor has received the right to grant licenses thereunder, and shall also grant to the Employer a nonexclusive and nontransferable right (without the right to sublicense) to use the know-how and other technical information disclosed to the Employer under the Contract. Nothing contained herein shall be construed as transferring ownership of any patent, utility model, trademark, design, copyright, know-how, or other intellectual property right from the Contractor or any third Party to the Employer. 15.2 The copyright in all drawings, documents, and other materials containing data and information furnished to the Employer by the Contractor herein shall remain vested in the Contractor or, if they are furnished to the Employer directly or through the Contractor by any third Party, including suppliers of materials, the copyright in such materials shall remain vested in such third Party. |
| --- | --- |
| 16. Confidential Information | 16.1 The Employer and the Contractor shall keep confidential and shall not, without the written consent of the other Party hereto, divulge to any third Party any documents, data or other information furnished directly or indirectly by the other Party hereto in connection with the Contract, whether such information has been furnished prior to, during, or following termination of the Contract. Notwithstanding the above, the Contractor may furnish to its Subcontractor(s) such documents, data, and other information it receives from the Employer to the extent required for the Subcontractor(s) to perform its work under the Contract, in which event the Contractor shall obtain from such Subcontractor(s) an undertaking of confidentiality similar to that imposed on the Contractor under this GC Clause 16. 16.2 The Employer shall not use such documents, data, and other information received from the Contractor for any purpose other than the operation and maintenance of the Facilities. Similarly, the Contractor shall not use such documents, data, and other information received from the Employer for any purpose other than the design, procurement of Plant, construction, or such other work and services as are required for the performance of the Contract. 16.3 The obligation of a Party under GC Sub-Clauses 16.1 and 16.2 above, however, shall not apply to that information, which: - now or hereafter enters the public domain through no fault of that Party; - can be proven to have been possessed by that Party at the time of disclosure and which was not previously obtained, directly or indirectly, from the other Party hereto; - otherwise lawfully becomes available to that Party from a third Party that has no obligation of confidentiality; and - is being provided to the Bank. 16.4 The above provisions of this GC Clause 16 shall not in any way modify any undertaking of confidentiality given by either of the Parties hereto prior to the date of the Contract in respect of the Facilities or any part thereof. 16.5 The provisions of this GC Clause 16 shall survive termination, for whatever reason, of the Contract. |

#### E.  Execution of the Facilities

| 17. Representatives | 17.1 Project Manager If the Project Manager is not named in the Contract, then within fourteen (14) days of the Effective Date, the Employer shall appoint and notify the Contractor in writing of the name of the Project Manager. The Employer may from time to time appoint some other person as the Project Manager in place of the person previously so appointed, and shall give notice of the name of such other person to the Contractor without delay. No such appointment shall be made at such a time or in such a manner as to impede the progress of work on the Facilities. Such appointment shall only take effect upon receipt of such notice by the Contractor. The Project Manager shall represent and act for the Employer at all times during the performance of the Contract. All notices, instructions, orders, certificates, approvals, and all other communications under the Contract shall be given by the Project Manager, except as herein otherwise provided. All notices, instructions, information, and other communications given by the Contractor to the Employer under the Contract shall be given to the Project Manager, except as herein otherwise provided. 17.2 Contractor’s Representative and Construction Manager 17.2.1 If the Contractor’s Representative is not named in the Contract, then within fourteen (14) days of the Effective Date, the Contractor shall appoint the Contractor’s Representative and shall request the Employer in writing to approve the person so appointed. If the Employer makes no objection to the appointment within fourteen (14) days, the Contractor’s Representative shall be deemed to have been approved. If the Employer objects to the appointment within fourteen (14) days giving the reason therefor, then the Contractor shall appoint a replacement within fourteen (14) days of such objection, and the foregoing provisions of this GC Sub-Clause 17.2.1 shall apply thereto. 17.2.2 The Contractor’s Representative shall represent and act for the Contractor at all times during the performance of the Contract and shall give to the Project Manager all the Contractor’s notices, instructions, information, and all other communications under the Contract. All notices, instructions, information, and all other communications given by the Employer or the Project Manager to the Contractor under the Contract shall be given to the Contractor’s Representative or, in its absence, its deputy, except as herein otherwise provided. The Contractor shall not revoke the appointment of the Contractor’s Representative without the Employer’s prior written consent, which shall not be unreasonably withheld. If the Employer consents thereto, the Contractor shall appoint some other person as the Contractor’s Representative, pursuant to the procedure set out in GC Sub-Clause 17.2.1. 17.2.3 The Contractor’s Representative may, subject to the approval of the Employer which shall not be unreasonably withheld, at any time delegate to any person any of the powers, functions and authorities vested in him or her. Any such delegation may be revoked at any time. Any such delegation or revocation shall be subject to a prior notice signed by the Contractor’s Representative, and shall specify the powers, functions, and authorities thereby delegated or revoked. No such delegation or revocation shall take effect unless and until a copy thereof has been delivered to the Employer and the Project Manager. Any act or exercise by any person of powers, functions and authorities so delegated to him or her in accordance with this GC Sub-Clause 17.2.3 shall be deemed to be an act or exercise by the Contractor’s Representative. 17.2.4 From the commencement of installation of the Facilities at the Site until Completion, the Contractor’s Representative shall appoint a suitable person as the Construction Manager. The Construction Manager shall supervise all work done at the Site by the Contractor and shall be present at the Site throughout normal working hours except when on leave, sick, or absent for reasons connected with the proper performance of the Contract. Whenever the Construction Manager is absent from the Site, the Contractor’s Representative or the Construction Manager shall appoint a suitable person to act as the Construction Manager’s deputy. 17.2.5 The Employer may by notice to the Contractor object to any representative or person employed by the Contractor in the execution of the Contract who, in the reasonable opinion of the Employer, may behave inappropriately, may be incompetent or negligent, or may commit a serious breach of the Site regulations provided under GC Sub-Clause 22.4. The Employer shall provide evidence of the same, whereupon the Contractor shall remove such person from the Facilities. 17.2.6 If any representative or person employed by the Contractor is removed in accordance with GC Sub-Clause 17.2.5, the Contractor shall, where required, promptly appoint a suitable replacement with equivalent skills and experience. |
| --- | --- |
| 18. Work Program | 18.1 Contractor’s Organization The Contractor shall supply to the Employer and the Project Manager a chart showing the proposed organization to be established by the Contractor for carrying out work on the Facilities within twenty-one (21) days of the Effective Date. The chart shall include the identities of the key personnel, and the curricula vitae of such key personnel to be employed shall be supplied together with the chart. The Contractor shall promptly inform the Employer and the Project Manager in writing of any revision or alteration of such an organization chart. 18.2 Program of Performance Within twenty-eight (28) days after the Effective Date, the Contractor shall submit to the Project Manager a detailed program of performance of the Contract, made in a form acceptable to the Project Manager and showing the sequence in which it proposes to design, manufacture, transport, assemble, install, and pre-commission the Facilities, as well as the date by which the Contractor reasonably requires that the Employer shall have fulfilled its obligations under the Contract so as to enable the Contractor to execute the Contract in accordance with the program and to achieve Completion, Commissioning, and Acceptance of the Facilities in accordance with the Contract. The program so submitted by the Contractor shall accord with the Time Schedule included in the Appendix (Time Schedule) to the Contract Agreement and any other dates and periods specified in the Contract. The Contractor shall update and revise the program as and when appropriate or when required by the Project Manager, but without modification in the Times for Completion specified in the PC and any extension granted in accordance with GC Clause 40, and shall submit all such revisions to the Project Manager. 18.3 Progress Report The Contractor shall monitor progress of all the activities specified in the program referred to in GC Sub-Clause 18.2 above, and supply a progress report to the Project Manager every month. The progress report shall be in a form acceptable to the Project Manager and shall indicate: (a) percentage completion achieved compared with the planned percentage completion for each activity; and (b) where any activity is behind the program, giving comments and likely consequences and stating the corrective action being taken. 18.4 Progress of Performance If at any time the Contractor’s actual progress falls behind the program referred to in GC Sub-Clause 18.2, or it becomes apparent that it will so fall behind, the Contractor shall, at the request of the Employer or the Project Manager, prepare and submit to the Project Manager a revised program, taking into account the prevailing circumstances, and shall notify the Project Manager of the steps being taken to expedite progress so as to attain Completion of the Facilities within the Time for Completion under GC Sub-Clause 8.2, any extension thereof entitled under GC Sub-Clause 40.1, or any extended period as may otherwise be agreed upon between the Employer and the Contractor. 18.5 Procedures The Contract shall be executed in accordance with the Contract Documents including the procedures given in the Forms and Procedures of the Employer’s Requirements. The Contractor may execute the Contract in accordance with its own standard project execution plans and procedures to the extent that they do not conflict with the provisions contained in the Contract. |
| 19. Subcontracting | 19.1 The Appendix 5 (List of Major Items of Plant and Installation Services and List of Approved Subcontractors) to the Contract Agreement specifies major items of Plant and Installation Services and a list of approved Subcontractors against each item, including manufacturers. Insofar as no Subcontractors are listed against any such item, the Contractor shall prepare a list of Subcontractors for such item for inclusion in such list. The Contractor may from time to time propose any addition to or deletion from any such list. The Contractor shall submit any such list or any modification thereto to the Employer for its approval in sufficient time so as not to impede the progress of work on the Facilities. Such approval by the Employer for any of the Subcontractors shall not relieve the Contractor from any of its obligations, duties, or responsibilities under the Contract. 19.2 The Contractor shall select and employ its Subcontractors for such major items from those listed in the lists referred to in GC Sub-Clause 19.1. - For items or parts of the Facilities not specified in the Appendix (List of Major Items of Plant and Installation Services and List of Approved Subcontractors for Major Items) to the Contract Agreement, the Contractor may employ such Subcontractors as it may select, at its discretion. - Each subcontract shall include provisions which would entitle the Employer to require the sub-contract to be assigned to the Employer under GC 19.5 (if and when applicable), or in event of termination by the Employer under GC 42.2. - If a Sub-contractor's obligations extend beyond the expiry date of the relevant Defects Liability Period and the Project Manager, prior to that date, instructs the Contractor to assign the benefits of such obligations to the Employer, then the Contractor shall do so. |
| 20. Design and Engineering | 20.1 Specifications and Drawings 20.1.1 The Contractor shall execute the basic and detailed design and the engineering work in compliance with the provisions of the Contract, or where not so specified, in accordance with good engineering practice. The Contractor shall be responsible for any discrepancies, errors, or omissions in the specifications, drawings, and other technical documents that it has prepared, whether such specifications, drawings, and other documents have been approved by the Project Manager or not, provided that such discrepancies, errors, or omissions are not because of inaccurate information furnished in writing to the Contractor by or on behalf of the Employer. 20.1.2 The Contractor shall be entitled to disclaim responsibility for any design, data, drawing, specification, or other document, or any modification thereof provided or designated by or on behalf of the Employer, by giving a notice of such disclaimer to the Project Manager. 20.2 Codes and Standards Wherever references are made in the Contract to codes and standards in accordance with which the Contract shall be executed, the edition or the revised version of such codes and standards current at the date twenty-eight (28) days prior to date of bid submission shall apply unless otherwise specified. During Contract execution, any changes in such codes and standards shall be applied subject to approval by the Employer and shall be treated in accordance with GC Clause 39. 20.3 Approval/Review of Technical Documents by Project Manager 20.3.1 The Contractor shall prepare or cause its Subcontractors to prepare, and furnish to the Project Manager the documents listed in the Appendix (List of Documents for Approval or Review) to the Contract Agreement for its approval or review as specified and in accordance with the requirements of GC Sub-Clause 18.2 (Program of Performance). Any part of the Facilities covered by or related to the documents to be approved by the Project Manager shall be executed only after the Project Manager’s approval thereof. GC Sub-Clauses 20.3.2 through 20.3.7 shall apply to those documents requiring the Project Manager’s approval, but not to those furnished to the Project Manager for its review only. 20.3.2 Within fourteen (14) days after receipt by the Project Manager of any document requiring the Project Manager’s approval in accordance with GC Sub-Clause 20.3.1, the Project Manager shall either return one copy thereof to the Contractor with its approval endorsed thereon or shall notify the Contractor in writing of its disapproval thereof and the reasons therefor and the modifications that the Project Manager proposes. If the Project Manager fails to take such action within the said fourteen (14) days, then the said document shall be deemed to have been approved by the Project Manager. 20.3.3 The Project Manager shall not disapprove any document, except on the grounds that the document does not comply with the Contract or that it is contrary to good engineering practice. If the Project Manager disapproves a document, he shall specify the reasons for his decision. 20.3.4 If the Project Manager disapproves the document, the Contractor shall modify the document and resubmit it for the Project Manager’s approval in accordance with GC Sub-Clause 20.3.2. If the Project Manager approves the document subject to modification(s), the Contractor shall make the required modification(s), whereupon the document shall be deemed to have been approved. 20.3.5 If any dispute or difference occurs between the Employer and the Contractor in connection with or arising out of the disapproval by the Project Manager of any document and/or any modification(s) thereto that cannot be settled between the Parties within a reasonable period, then such dispute or difference may be referred to a Dispute Board for determination in accordance with GC Sub-Clause 45.3 hereof. If such dispute or difference is referred to a Dispute Board, the Project Manager shall give instructions as to whether and, if so, how, performance of the Contract is to proceed. The Contractor shall proceed with the Contract in accordance with the Project Manager’s instructions, provided that if the Dispute Board upholds the Contractor’s view on the dispute and if the Employer has not given notice under GC Sub-Clause 45.3 hereof, then the Contractor shall be reimbursed by the Employer for any additional costs incurred by reason of such instructions and shall be relieved of such responsibility or liability in connection with the dispute and the execution of the instructions as the Dispute Board shall decide, and the Time for Completion shall be extended accordingly. 20.3.6 The Project Manager’s approval, with or without modification of the document furnished by the Contractor, shall not relieve the Contractor of any responsibility or liability imposed upon it by any provisions of the Contract except to the extent that any subsequent failure results from modifications required by the Project Manager. 20.3.7 The Contractor shall not depart from any approved document unless the Contractor has first submitted to the Project Manager an amended document and obtained the Project Manager’s approval thereof, pursuant to the provisions of this GC Sub-Clause 20.3. If the Project Manager requests any change in any already approved document and/or in any document based thereon, the provisions of GC Clause 39 shall apply to such request. |
| 21. Procurement | 21.1 Plant Subject to GC Sub-Clause 14.2, the Contractor shall procure and transport all Plant in an expeditious and orderly manner to the Site. 21.2 Employer-Supplied Plant If the Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement provides that the Employer shall furnish any specific items to the Contractor, the following provisions shall apply: 21.2.1 The Employer shall, at its own risk and expense, transport each item to the place on or near the Site as agreed upon by the parties and make such item available to the Contractor at the time specified in the program furnished by the Contractor, pursuant to GC Sub-Clause 18.2, unless otherwise mutually agreed. 21.2.2 Upon receipt of such item, the Contractor shall inspect the same visually and notify the Project Manager of any detected shortage, defect, or default. The Employer shall immediately remedy any shortage, defect, or default, or the Contractor shall, if practicable and possible, at the request of the Employer, remedy such shortage, defect, or default at the Employer’s cost and expense. After inspection, such item shall fall under the care, custody, and control of the Contractor. The provision of this GC Sub-Clause 21.2.2 shall apply to any item supplied to remedy any such shortage or default or to substitute for any defective item, or shall apply to defective items that have been repaired. 21.2.3 The foregoing responsibilities of the Contractor and its obligations of care, custody, and control shall not relieve the Employer of liability for any undetected shortage, defect, or default, nor place the Contractor under any liability for any such shortage, defect or default whether under GC Clause 27 or under any other provision of Contract. 21.3 Transportation 21.3.1 The Contractor shall at its own risk and expense transport all the materials and the Contractor’s Equipment to the Site by the mode of transport that the Contractor judges most suitable under all the circumstances. 21.3.2 Unless otherwise provided in the Contract, the Contractor shall be entitled to select any safe mode of transport operated by any person to carry the materials and the Contractor’s Equipment. 21.3.3 Upon dispatch of each shipment of materials and the Contractor’s Equipment, the Contractor shall notify the Employer by telex, cable, facsimile, or electronic means, of the description of the materials and of the Contractor’s Equipment, the point and means of dispatch, and the estimated time and point of arrival in the country where the Site is located, if applicable, and at the Site. The Contractor shall furnish the Employer with relevant shipping documents to be agreed upon between the parties. 21.3.4 The Contractor shall be responsible for obtaining, if necessary, approvals from the authorities for transportation of the materials and the Contractor’s Equipment to the Site. The Employer shall use its best endeavors in a timely and expeditious manner to assist the Contractor in obtaining such approvals, if requested by the Contractor. The Contractor shall indemnify and hold harmless the Employer from and against any claim for damage to roads, bridges, or any other traffic facilities that may be caused by the transport of the materials and the Contractor’s Equipment to the Site. 21.4 Customs Clearance The Contractor shall, at its own expense, handle all imported materials and Contractor’s Equipment at the point(s) of import and shall handle any formalities for customs clearance, subject to the Employer’s obligations under GC Sub-Clause 14.2, provided that if applicable laws or regulations require any application or act to be made by or in the name of the Employer, the Employer shall take all necessary steps to comply with such laws or regulations. In the event of delays in customs clearance that are not the fault of the Contractor, the Contractor shall be entitled to an extension in the Time for Completion, pursuant to GC Clause 40. |
| 22. Installation | 22.1 Setting Out/Supervision 22.1.1 Benchmark (a) The Contractor shall be responsible for the true and proper setting-out of the Facilities in relation to bench marks, reference marks, and lines provided to it in writing by or on behalf of the Employer. (b) If, at any time during the progress of installation of the Facilities, any error shall appear in the position, level, or alignment of the Facilities, the Contractor shall forthwith notify the Project Manager of such error and, at its own expense, immediately rectify such error to the reasonable satisfaction of the Project Manager. If such error is based on incorrect data provided in writing by or on behalf of the Employer, the expense of rectifying the same shall be borne by the Employer. 22.1.2 Contractor’s Supervision The Contractor shall give or provide all necessary superintendence during the installation of the Facilities, and the Construction Manager or its deputy shall be constantly on the Site to provide full-time superintendence of the installation. The Contractor shall provide and employ only technical personnel who are skilled and experienced in their respective callings and supervisory staff who are competent to adequately supervise the work at hand. 22.2 Labor 22.2.1 Engagement of Staff and Labor (a) Except as otherwise stated in the Specification, the Contractor shall make arrangements for the engagement of all staff and labor, local or otherwise, and for their payment, housing, feeding, and transport. (b) The Contractor shall provide and employ on the Site in the installation of the Facilities such skilled, semi-skilled, and unskilled labor as is necessary for the proper and timely execution of the Contract. The Contractor is encouraged to use local labor that has the necessary skills. (c) The Contractor shall be responsible for obtaining all necessary permit(s) and/or visa(s) from the appropriate authorities for the entry of all labor and personnel to be employed on the Site into the country where the Site is located. The Employer will, if requested by the Contractor, use his best endeavors in a timely and expeditious manner to assist the Contractor in obtaining any local, state, national, or government permission required for bringing in the Contractor’s personnel. (d) The Contractor shall at its own expense provide the means of repatriation to all of its and its Subcontractor’s personnel employed on the Contract at the Site to the place where they were recruited or to their domicile. It shall also provide suitable temporary maintenance of all such persons from the cessation of their employment on the Contract to the date programmed for their departure. In the event that the Contractor defaults in providing such means of transportation and temporary maintenance, the Employer may provide the same to such personnel and recover the cost of doing so from the Contractor. 22.2.2 Persons in the Service of Employer The Contractor shall not recruit, or attempt to recruit, staff and labor from amongst the Employer’s Personnel. 22.2.3 Labor Laws (a) The Contractor shall comply with all the relevant labor Laws applicable to the Contractor’s Personnel, including Laws relating to their employment, health, safety, welfare, immigration, and emigration, and shall allow them all their legal rights. (b) The Contractor shall at all times during the progress of the Contract use its best endeavors to prevent any unlawful, riotous, or disorderly conduct or behavior by or amongst its employees and the labor of its Subcontractors. (c) The Contractor shall, in all dealings with its labor and the labor of its Subcontractors currently employed on or connected with the Contract, pay due regard to all recognized festivals, official holidays, religious, or other customs and all local laws and regulations pertaining to the employment of labor. 22.2.4 Rates of Wages and Conditions of Labor (a) The Contractor shall pay rates of wages, and observe conditions of labor, which are not lower than those established for the trade or industry where the work is carried out. If no established rates or conditions are applicable, the Contractor shall pay rates of wages and observe conditions which are not lower than the general level of wages and conditions observed locally by employers whose trade or industry is similar to that of the Contractor. (b) The Contractor shall inform the Contractor’s Personnel about their liability to pay personal income taxes in the Country in respect of such of their salaries, wages, and allowances as are chargeable under the Laws for the time being in force, and the Contractor shall perform such duties in regard to such deductions thereof as may be imposed on him by such Laws. 22.2.5 Working Hours (a) No work shall be carried out on the Site on locally recognized days of rest, or outside the normal working hours stated in the PC, unless: (i) otherwise stated in the Contract; (ii) the Project Manager gives consent; or (iii) the work is unavoidable, or necessary for the protection of life or property or for the safety of the Facilities, in which case the Contractor shall immediately advise the Project Manager. (b) If and when the Contractor considers it necessary to carry out work at night or on public holidays so as to meet the Time for Completion and requests the Project Manager’s consent thereto, the Project Manager shall not unreasonably withhold such consent. (c) This Sub-Clause shall not apply to any work which is customarily carried out by rotary or double shifts. 22.2.6 Facilities for Staff and Labor (a) Except as otherwise stated in the Specification, the Contractor shall provide and maintain all necessary accommodation and welfare facilities for the Contractor’s Personnel. The Contractor shall also provide facilities for the Employer’s Personnel as stated in the Specification. (b) The Contractor shall not permit any of the Contractor’s Personnel to maintain any temporary or permanent living quarters within the structures forming part of the Facilities. 22.2.7 Health and Safety (a) The Contractor shall at all times take all reasonable precautions to maintain the health and safety of the Contractor’s Personnel. In collaboration with local health authorities, the Contractor shall ensure that medical staff, first aid facilities, sick bay, and ambulance service are available at all times at the Site and at any accommodation for Contractor’s and Employer’s Personnel, and that suitable arrangements are made for all necessary welfare and hygiene requirements and for the prevention of epidemics. (b) The Contractor shall appoint an accident prevention officer at the Site, responsible for maintaining safety and protection against accidents. This person shall be qualified for this responsibility, and shall have the authority to issue instructions and take protective measures to prevent accidents. Throughout the performance of the Contract, the Contractor shall provide whatever is required by this person to exercise this responsibility and authority. (c) The Contractor shall send to the Project Manager, details of any accident as soon as practicable after its occurrence. The Contractor shall maintain records and make reports concerning health, safety, and welfare of persons, and damage to property, as the Project Manager may reasonably require. 22.2.8 Funeral Arrangements In the event of the death of any of the Contractor’s personnel or accompanying members of their families, the Contractor shall be responsible for making the appropriate arrangements for their return or burial, unless otherwise specified in the PC. 22.2.9 Records of Contractor’s Personnel The Contractor shall keep accurate records of the Contractor’s personnel, including the number of each class of Contractor’s Personnel on the Site and the names, ages, gender, hours worked, and wages paid to all workers. These records shall be summarized on a monthly basis in a form approved by the Project Manager and shall be available for inspection by the Project Manager until the Contractor has completed all work. 22.2.10 Supply of Foodstuff The Contractor shall arrange for the provision of a sufficient supply of suitable food as may be stated in the Specification at reasonable prices for the Contractor’s Personnel for the purposes of or in connection with the Contract. 22.2.11 Supply of Water The Contractor shall, having regard to local conditions, provide on the Site an adequate supply of drinking and other water for the use of the Contractor’s Personnel. 22.2.12 Measures against Insect and Pest Nuisance The Contractor shall at all times take the necessary precautions to protect the Contractor’s Personnel employed on the Site from insect and pest nuisance, and to reduce their danger to health. The Contractor shall comply with all the regulations of the local health authorities, including use of appropriate insecticide. 22.2.13 Alcoholic Liquor or Drugs The Contractor shall not, otherwise than in accordance with the Laws of the Country, import, sell, give barter, or otherwise dispose of any alcoholic liquor or drugs, or permit or allow importation, sale, gift barter, or disposal by Contractor's Personnel. 22.2.14 Arms and Ammunition The Contractor shall not give, barter, or otherwise dispose of, to any person, any arms or ammunition of any kind, or allow Contractor's Personnel to do so. 22.2.15 Prohibition of All Forms of Forced or Compulsory Labor The contractor shall not employ "forced or compulsory labor" in any form. "Forced or compulsory labor" consists of all work or service, not voluntarily performed, that is extracted from an individual under threat of force or penalty. 22.2.16 Prohibition of Harmful Child Labor The Contractor shall not employ any child to perform any work that is economically exploitative, or is likely to be hazardous to, or to interfere with, the child's education, or to be harmful to the child's health or physical, mental, spiritual, moral, or social development. 22.3 Contractor’s Equipment 22.3.1 All Contractor’s Equipment brought by the Contractor onto the Site shall be deemed to be intended to be used exclusively for the execution of the Contract. The Contractor shall not remove the same from the Site without the Project Manager’s consent that such Contractor’s Equipment is no longer required for the execution of the Contract. 22.3.2 Unless otherwise specified in the Contract, upon completion of the Facilities, the Contractor shall remove from the Site all Equipment brought by the Contractor onto the Site and any surplus materials remaining thereon. 22.3.3 The Employer will, if requested, use its best endeavors to assist the Contractor in obtaining any local, state or national government permission required by the Contractor for the export of the Contractor’s Equipment imported by the Contractor for use in the execution of the Contract that is no longer required for the execution of the Contract. 22.4 Site Regulations and Safety The Employer and the Contractor shall establish Site regulations setting out the rules to be observed in the execution of the Contract at the Site and shall comply therewith. The Contractor shall prepare and submit to the Employer, with a copy to the Project Manager, proposed Site regulations for the Employer’s approval, which approval shall not be unreasonably withheld. Such Site regulations shall include, but shall not be limited to, rules in respect of security, safety of the Facilities, gate control, sanitation, medical care, and fire prevention. 22.5 Opportunities for Other Contractors 22.5.1 The Contractor shall, upon written request from the Employer or the Project Manager, give all reasonable opportunities for carrying out the work to any other contractors employed by the Employer on or near the Site. 22.5.2 If the Contractor, upon written request from the Employer or the Project Manager, makes available to other contractors any roads or ways the maintenance for which the Contractor is responsible, permits the use by such other contractors of the Contractor’s Equipment, or provides any other service of whatsoever nature for such other contractors, the Employer shall fully compensate the Contractor for any loss or damage caused or occasioned by such other contractors in respect of any such use or service, and shall pay to the Contractor reasonable remuneration for the use of such equipment or the provision of such services. 22.5.3 The Contractor shall also so arrange to perform its work as to minimize, to the extent possible, interference with the work of other contractors. The Project Manager shall determine the resolution of any difference or conflict that may arise between the Contractor and other contractors and the workers of the Employer in regard to their work. 22.5.4 The Contractor shall notify the Project Manager promptly of any defects in the other Contractors’ work that come to its notice, and that could affect the Contractor’s work. The Project Manager shall determine the corrective measures, if any, required to rectify the situation after inspection of the Facilities. Decisions made by the Project Manager shall be binding on the Contractor. 22.6 Emergency Work If, by reason of an emergency arising in connection with and during the execution of the Contract, any protective or remedial work is necessary as a matter of urgency to prevent damage to the Facilities, the Contractor shall immediately carry out such work. If the Contractor is unable or unwilling to do such work immediately, the Employer may do or cause such work to be done as the Employer may determine is necessary in order to prevent damage to the Facilities. In such event the Employer shall, as soon as practicable after the occurrence of any such emergency, notify the Contractor in writing of such emergency, the work done and the reasons therefor. If the work done or caused to be done by the Employer is work that the Contractor was liable to do at its own expense under the Contract, the reasonable costs incurred by the Employer in connection therewith shall be paid by the Contractor to the Employer. Otherwise, the cost of such remedial work shall be borne by the Employer. 22.7 Site Clearance 22.7.1 Site Clearance in Course of Performance In the course of carrying out the Contract, the Contractor shall keep the Site reasonably free from all unnecessary obstruction, store, or remove any surplus materials, clear away any wreckage, rubbish, or temporary works from the Site, and remove any Contractor’s Equipment no longer required for execution of the Contract. 22.7.2 Clearance of Site after Completion After Completion of all parts of the Facilities, the Contractor shall clear away and remove all wreckage, rubbish, and debris of any kind from the Site, and shall leave the Site and Facilities in a clean and safe condition. 22.8 Watching and Lighting The Contractor shall provide and maintain at its own expense all lighting, fencing, and watching when and where necessary for the proper execution and the protection of the Facilities, or for the safety of the owners and occupiers of adjacent property and for the safety of the public. |
| 23. Test and Inspection | 23.1 The Contractor shall at its own expense carry out at the place of manufacture and/or on the Site all such tests and/or inspections of the Plant and any part of the Facilities as are specified in the Contract. 23.2 The Employer and the Project Manager or their designated representatives shall be entitled to attend the aforesaid test and/or inspection, provided that the Employer shall bear all costs and expenses incurred in connection with such attendance including, but not limited to, all traveling and board and lodging expenses. 23.3 Whenever the Contractor is ready to carry out any such test and/or inspection, the Contractor shall give a reasonable advance notice of such test and/or inspection and of the place and time thereof to the Project Manager. The Contractor shall obtain from any relevant third Party or manufacturer any necessary permission or consent to enable the Employer and the Project Manager or their designated representatives to attend the test and/or inspection. 23.4 The Contractor shall provide the Project Manager with a certified report of the results of any such test and/or inspection. If the Employer or Project Manager or their designated representatives fails to attend the test and/or inspection, or if it is agreed between the Parties that such persons shall not do so, then the Contractor may proceed with the test and/or inspection in the absence of such persons, and may provide the Project Manager with a certified report of the results thereof. 23.5 The Project Manager may require the Contractor to carry out any test and/or inspection not required by the Contract, provided that the Contractor’s reasonable costs and expenses incurred in the carrying out of such test and/or inspection shall be added to the Contract Price. Further, if such test and/or inspection impedes the progress of work on the Facilities and/or the Contractor’s performance of its other obligations under the Contract, due allowance will be made in respect of the Time for Completion and the other obligations so affected. 23.6 If any Plant or any part of the Facilities fails to pass any test and/or inspection, the Contractor shall either rectify or replace such Plant or part of the Facilities and shall repeat the test and/or inspection upon giving a notice under GC Sub-Clause 23.3. 23.7 If any dispute or difference of opinion shall arise between the parties in connection with or arising out of the test and/or inspection of the Plant or part of the Facilities that cannot be settled between the parties within a reasonable period of time, it may be referred to an Dispute Board for determination in accordance with GC Sub-Clause 45.3. 23.8 The Contractor shall afford the Employer and the Project Manager, at the Employer’s expense, access at any reasonable time to any place where the Plant are being manufactured or the Facilities are being installed, in order to inspect the progress and the manner of manufacture or installation, provided that the Project Manager shall give the Contractor a reasonable prior notice. Without prejudice to GCC Sub-Clause 9.6, as instructed by the Project Manager, the Contractor shall also afford other relevant entities (at the Employer’s or their respective entities’ expense, as appropriate) access to the Facilities, to inspect progress and the manner of the execution of the Facilities, carry out environmental and social audit, as appropriate, or carry out any other duty as stated in the Employer’s Requirements or as instructed by the Project Manager. 23.9 The Contractor agrees that neither the execution of a test and/or inspection of Plant or any part of the Facilities, nor the attendance by the Employer or the Project Manager, nor the issue of any test certificate pursuant to GC Sub-Clause 23.4, shall release the Contractor from any other responsibilities under the Contract. 23.10 No part of the Facilities or foundations shall be covered up on the Site without the Contractor carrying out any test and/or inspection required under the Contract. The Contractor shall give a reasonable notice to the Project Manager whenever any such parts of the Facilities or foundations are ready or about to be ready for test and/or inspection; such test and/or inspection and notice thereof shall be subject to the requirements of the Contract. 23.11The Contractor shall uncover any part of the Facilities or foundations, or shall make openings in or through the same as the Project Manager may from time to time require at the Site, and shall reinstate and make good such part or parts. If any parts of the Facilities or foundations have been covered up at the Site after compliance with the requirement of GC Sub-Clause 23.10 and are found to be executed in accordance with the Contract, the expenses of uncovering, making openings in or through, reinstating, and making good the same shall be borne by the Employer, and the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been delayed or impeded in the performance of any of its obligations under the Contract. |
| 24. Completion of the Facilities | 24.1 As soon as the Facilities or any part thereof has, in the opinion of the Contractor, been completed operationally and structurally and put in a tight and clean condition as specified in the Employer’s Requirements, excluding minor items not materially affecting the operation or safety of the Facilities, the Contractor shall so notify the Employer in writing. 24.2 Within seven (7) days after receipt of the notice from the Contractor under GC Sub-Clause 24.1, the Employer shall supply the operating and maintenance personnel specified in the Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement for Pre-commissioning of the Facilities or any part thereof. Pursuant to the Appendix (Scope of Works and Supply by the Employer) to the Contract Agreement, the Employer shall also provide, within the said seven (7) day period, the raw materials, utilities, lubricants, chemicals, catalysts, facilities, services, and other matters required for Pre-commissioning of the Facilities or any part thereof. 24.3 As soon as reasonably practicable after the operating and maintenance personnel have been supplied by the Employer and the raw materials, utilities, lubricants, chemicals, catalysts, facilities, services, and other matters have been provided by the Employer in accordance with GC Sub-Clause 24.2, the Contractor shall commence Pre-commissioning of the Facilities or the relevant part thereof in preparation for Commissioning, subject to GC Sub-Clause 25.5. 24.4 As soon as all works in respect of Pre-commissioning are completed and, in the opinion of the Contractor, the Facilities or any part thereof is ready for Commissioning, the Contractor shall so notify the Project Manager in writing. 24.5 The Project Manager shall, within fourteen (14) days after receipt of the Contractor’s notice under GC Sub-Clause 24.4, either issue a Completion Certificate in the form specified in the Employer’s Requirements (Forms and Procedures), stating that the Facilities or that part thereof have reached Completion as of the date of the Contractor’s notice under GC Sub-Clause 24.4, or notify the Contractor in writing of any defects and/or deficiencies. If the Project Manager notifies the Contractor of any defects and/or deficiencies, the Contractor shall then correct such defects and/or deficiencies, and shall repeat the procedure described in GC Sub-Clause 24.4. If the Project Manager is satisfied that the Facilities or that part thereof have reached Completion, the Project Manager shall, within seven (7) days after receipt of the Contractor’s repeated notice, issue a Completion Certificate stating that the Facilities or that part thereof have reached Completion as of the date of the Contractor’s repeated notice. If the Project Manager is not so satisfied, then it shall notify the Contractor in writing of any defects and/or deficiencies within seven (7) days after receipt of the Contractor’s repeated notice, and the above procedure shall be repeated. 24.6 If the Project Manager fails to issue the Completion Certificate and fails to inform the Contractor of any defects and/or deficiencies within fourteen (14) days after receipt of the Contractor’s notice under GC Sub-Clause 24.4 or within seven (7) days after receipt of the Contractor’s repeated notice under GC Sub-Clause 24.5, or if the Employer makes use of the Facilities or part thereof, then the Facilities or that part thereof shall be deemed to have reached Completion as of the date of the Contractor’s notice or repeated notice, or as of the Employer’s use of the Facilities, as the case may be. 24.7 As soon as possible after Completion, the Contractor shall complete all outstanding minor items so that the Facilities are fully in accordance with the requirements of the Contract, failing which the Employer will undertake such completion and deduct the costs thereof from any monies owing to the Contractor. 24.8 Upon Completion, the Employer shall be responsible for the care and custody of the Facilities or the relevant part thereof, together with the risk of loss or damage thereto, and shall thereafter take over the Facilities or the relevant part thereof. |
| 25. Commissioning and Operational Acceptance | 25.1 Commissioning 25.1.1 Commissioning of the Facilities or any part thereof shall be commenced by the Contractor immediately after issue of the Completion Certificate by the Project Manager, pursuant to GC Sub-Clause 24.5, or immediately after the date of the deemed Completion, under GC Sub-Clause 24.6. 25.1.2 The Employer shall supply the operating and maintenance personnel and all raw materials, utilities, lubricants, chemicals, catalysts, facilities, services, and other matters required for Commissioning. 25.1.3 In accordance with the requirements of the Contract, the Contractor’s and Project Manager’s advisory personnel shall attend the Commissioning, including the Guarantee Test, and shall advise and assist the Employer. 25.2 Guarantee Test 25.2.1 Subject to GC Sub-Clause 25.5, the Guarantee Test and repeats thereof shall be conducted by the Contractor during Commissioning of the Facilities or the relevant part thereof to ascertain whether the Facilities or the relevant part can attain the Functional Guarantees specified in the Appendix (Functional Guarantees) to the Contract Agreement. The Employer shall promptly provide the Contractor with such information as the Contractor may reasonably require in relation to the conduct and results of the Guarantee Test and any repeats thereof. 25.2.2 If for reasons not attributable to the Contractor, the Guarantee Test of the Facilities or the relevant part thereof cannot be successfully completed within the period from the date of Completion specified in the PC or any other period agreed upon by the Employer and the Contractor, the Contractor shall be deemed to have fulfilled its obligations with respect to the Functional Guarantees, and GC Sub-Clauses 28.2 and 28.3 shall not apply. 25.3 Operational Acceptance 25.3.1 Subject to GC Sub-Clause 25.4 below, Operational Acceptance shall occur in respect of the Facilities or any part thereof when: (a) the Guarantee Test has been successfully completed and the Functional Guarantees are met; or (b) the Guarantee Test has not been successfully completed or has not been carried out for reasons not attributable to the Contractor within the period from the date of Completion specified in the PC, or any other agreed upon period as specified in GC Sub-Clause 25.2.2 above; or (c) the Contractor has paid the liquidated damages specified in GC Sub-Clause 28.3 hereof; and (d) any minor items mentioned in GC Sub-Clause 24.7 hereof relevant to the Facilities or that part thereof have been completed. 25.3.2 At any time after any of the events set out in GC Sub-Clause 25.3.1 have occurred, the Contractor may give a notice to the Project Manager requesting the issue of an Operational Acceptance Certificate in the form provided in the Employer’s Requirements (Forms and Procedures) in respect of the Facilities or the part thereof specified in such notice as of the date of such notice. 25.3.3 The Project Manager shall, after consultation with the Employer, and within seven (7) days after receipt of the Contractor’s notice, issue an Operational Acceptance Certificate. 25.3.4 If within seven (7) days after receipt of the Contractor’s notice, the Project Manager fails to issue the Operational Acceptance Certificate or fails to inform the Contractor in writing of the justifiable reasons why the Project Manager has not issued the Operational Acceptance Certificate, the Facilities or the relevant part thereof shall be deemed to have been accepted as of the date of the Contractor’s said notice. 25.4 Partial Acceptance 25.4.1 If the Contract specifies that Completion and Commissioning shall be carried out in respect of parts of the Facilities, the provisions relating to Completion and Commissioning including the Guarantee Test shall apply to each such part of the Facilities individually, and the Operational Acceptance Certificate shall be issued accordingly for each such part of the Facilities. 25.4.2 If a part of the Facilities comprises facilities such as buildings, for which no Commissioning or Guarantee Test is required, then the Project Manager shall issue the Operational Acceptance Certificate for such facility when it attains Completion, provided that the Contractor shall thereafter complete any outstanding minor items that are listed in the Operational Acceptance Certificate. 25.5 Delayed Pre-Commissioning and/or Guarantee Test 25.5.1 In the event that the Contractor is unable to proceed with the Pre-commissioning of the Facilities pursuant to GC Sub-Clause 24.3, or with the Guarantee Test pursuant to GC Sub-Clause 25.2, for reasons attributable to the Employer either on account of non-availability of other facilities under the responsibilities of other contractor(s), or for reasons beyond the Employer’s control, the provisions leading to “deemed” completion of activities such as Completion, pursuant to GC Sub-Clause 24.6, and Operational Acceptance, pursuant to GC Sub-Clause 25.3.4, and Contractor’s obligations regarding Defect Liability Period, pursuant to GC Sub-Clause 27.2, Functional Guarantee, pursuant to GC Clause 28, and Care of Facilities, pursuant to GC Clause 32, and GC Clause 41.1, Suspension, shall not apply. In this case, the following provisions shall apply. 25.5.2 When the Contractor is notified by the Project Manager that he will be unable to proceed with the activities and obligations pursuant to above Sub-Clause 25.5.1, the Contractor shall be entitled to the following: (a) the Time of Completion shall be extended for the period of suspension without imposition of liquidated damages pursuant to GC Sub-Clause 26.2; (b) payments due to the Contractor in accordance with the provision specified in the Appendix (Terms and Procedures of Payment) to the Contract Agreement, which would not have been payable in normal circumstances due to non-completion of the subject activities, shall be released to the Contractor against submission of a security in the form of a bank guarantee of equivalent amount acceptable to the Employer, and which shall become null and void when the Contractor will have complied with its obligations regarding those payments, subject to the provision of GC Sub-Clause 25.5.3 below; (c) the expenses towards the above security and extension of other securities under the contract, of which validity needs to be extended, shall be reimbursed to the Contractor by the Employer; and (d) the additional charges towards the care of the Facilities pursuant to GC Sub-Clause 32.1 shall be reimbursed to the Contractor by the Employer for the period between the notification mentioned above and the notification mentioned in GC Sub-Clause 25.5.4 below. The provision of GC Sub-Clause 33.2 shall apply to the Facilities during the same period. 25.5.3 In the event that the period of suspension under above Sub-Clause 25.5.1 actually exceeds one hundred eighty (180) days, the Employer and Contractor shall mutually agree to any additional compensation payable to the Contractor. 25.5.4 When the Contractor is notified by the Project Manager that the plant is ready for Pre-commissioning, the Contractor shall proceed without delay in performing all the specified activities and obligations under the contract. |

#### F.  Guarantees and Liabilities

| 26. Completion Time Guarantee | 26.1 The Contractor guarantees that it shall attain Completion of the Facilities (or a part for which a separate time for completion is specified) within the Time for Completion specified in the PC pursuant to GC Sub-Clause 8.2, or within such extended time to which the Contractor shall be entitled under GC Clause 40 hereof. 26.2 If the Contractor fails to attain Completion of the Facilities or any part thereof within the Time for Completion or any extension thereof under GC Clause 40, the Contractor shall pay to the Employer liquidated damages in the amount specified in the PC as a percentage rate of the Contract Price or the relevant part thereof. The aggregate amount of such liquidated damages shall in no event exceed the amount specified as “Maximum” in the PC as a percentage rate of the Contract Price. Once the “Maximum” is reached, the Employer may consider termination of the Contract, pursuant to GC Sub-Clause 42.2.2. Such payment shall completely satisfy the Contractor’s obligation to attain Completion of the Facilities or the relevant part thereof within the Time for Completion or any extension thereof under GC Clause 40. The Contractor shall have no further liability whatsoever to the Employer in respect thereof. However, the payment of liquidated damages shall not in any way relieve the Contractor from any of its obligations to complete the Facilities or from any other obligations and liabilities of the Contractor under the Contract. Save for liquidated damages payable under this GC Sub-Clause 26.2, the failure by the Contractor to attain any milestone or other act, matter or thing by any date specified in the Appendix (Time Schedule) to the Contract Agreement and/or other program of work prepared pursuant to GC Sub-Clause 18.2 shall not render the Contractor liable for any loss or damage thereby suffered by the Employer. 26.3 If the Contractor attains Completion of the Facilities or any part thereof before the Time for Completion or any extension thereof under GC Clause 40, the Employer shall pay to the Contractor a bonus in the amount specified in the PC. The aggregate amount of such bonus shall in no event exceed the amount specified as “Maximum” in the PC. |
| --- | --- |
| 27. Defect Liability | 27.1 The Contractor warrants that the Facilities or any part thereof shall be free from defects in the design, engineering, materials, and workmanship of the Plant supplied and of the work executed. 27.2 The Defect Liability Period shall be five hundred and forty (540) days from the date of Completion of the Facilities (or any part thereof) or one (1) year from the date of Operational Acceptance of the Facilities (or any part thereof), whichever first occurs, unless specified otherwise in the PC pursuant to GC Sub-Clause 27.10. If during the Defect Liability Period any defect should be found in the design, engineering, materials, and workmanship of the Plant supplied or of the work executed by the Contractor, the Contractor shall promptly, in consultation and agreement with the Employer regarding appropriate remedying of the defects, and at its cost, repair, replace, or otherwise make good as the Contractor shall determine at its discretion, such defect as well as any damage to the Facilities caused by such defect. The Contractor shall not be responsible for the repair, replacement, or making good of any defects or of any damage to the Facilities arising out of or resulting from any of the following causes: (a) improper operation or maintenance of the Facilities by the Employer; (b) operation of the Facilities outside specifications provided in the Contract; or (c) normal wear and tear. 27.3 The Contractor’s obligations under this GC Clause 27 shall not apply to: (a) any materials that are supplied by the Employer under GC Sub-Clause 21.2, are normally consumed in operation, or have a normal life shorter than the Defect Liability Period stated herein; (b) any designs, specifications or other data designed, supplied, or specified by or on behalf of the Employer or any matters for which the Contractor has disclaimed responsibility herein; or (c) any other materials supplied or any other work executed by or on behalf of the Employer, except for the work executed by the Employer under GC Sub-Clause 27.7. 27.4 The Employer shall give the Contractor a notice stating the nature of any such defect together with all available evidence thereof, promptly following the discovery thereof. The Employer shall afford all reasonable opportunity for the Contractor to inspect any such defect. 27.5 The Employer shall afford the Contractor all necessary access to the Facilities and the Site to enable the Contractor to perform its obligations under this GC Clause 27. The Contractor may, with the consent of the Employer, remove from the Site any Plant or any part of the Facilities that are defective if the nature of the defect, and/or any damage to the Facilities caused by the defect, is such that repairs cannot be expeditiously carried out at the Site. 27.6 If the repair, replacement or making good is of such a character that it may affect the efficiency of the Facilities or any part thereof, the Employer may give to the Contractor a notice requiring that tests of the defective part of the Facilities shall be made by the Contractor immediately upon completion of such remedial work, whereupon the Contractor shall carry out such tests. If such part fails the tests, the Contractor shall carry out further repair, replacement or making good, as the case may be, until that part of the Facilities passes such tests. The tests shall be agreed upon by the Employer and the Contractor. 27.7 If the Contractor fails to commence the work necessary to remedy such defect or any damage to the Facilities caused by such defect within a reasonable time (which shall in no event be considered to be less than 15 days), the Employer may, following notice to the Contractor, proceed to do such work, and the reasonable costs incurred by the Employer in connection therewith shall be paid to the Employer by the Contractor or may be deducted by the Employer from any monies due the Contractor or claimed under the Performance Security. 27.8 If the Facilities or any part thereof cannot be used by reason of such defect and/or making good of such defect, the Defect Liability Period of the Facilities or such part, as the case may be, shall be extended by a period equal to the period during which the Facilities or such part cannot be used by the Employer because of any of the aforesaid reasons. 27.9 Except as provided in GC Clauses 27 and 33, the Contractor shall be under no liability whatsoever and howsoever arising, and whether under the Contract or at law, in respect of defects in the Facilities or any part thereof, the Plant, design, or engineering, or work executed that appear after Completion of the Facilities or any part thereof, except where such defects are the result of the gross negligence, fraud, criminal, or willful action of the Contractor. 27.10 In addition, any such component of the Facilities and during the period of time as may be specified in the PC shall be subject to an extended Defect Liability Period. Such obligation of the Contractor shall be in addition to the Defect Liability Period specified under GC Sub-Clause 27.2. |
| 28. Functional Guarantees | 28.1 The Contractor guarantees that during the Guarantee Test, the Facilities and all parts thereof shall attain the Functional Guarantees specified in the Appendix (Functional Guarantees) to the Contract Agreement, subject to, and upon the conditions therein specified. 28.2 If, for reasons attributable to the Contractor, the minimum level of the Functional Guarantees specified in the Appendix (Functional Guarantees) to the Contract Agreement are not met either in whole or in part, the Contractor shall at its cost and expense make such changes, modifications, and/or additions to the Plant or any part thereof as may be necessary to meet at least the minimum level of such Guarantees. The Contractor shall notify the Employer upon completion of the necessary changes, modifications, and/or additions, and shall request the Employer to repeat the Guarantee Test until the minimum level of the Guarantees has been met. If the Contractor eventually fails to meet the minimum level of Functional Guarantees, the Employer may consider termination of the Contract, pursuant to GC Sub-Clause 42.2.2. 28.3 If, for reasons attributable to the Contractor, the Functional Guarantees specified in the Appendix (Functional Guarantees) to the Contract Agreement are not attained either in whole or in part, but the minimum level of the Functional Guarantees specified in the said Appendix to the Contract Agreement is met, the Contractor shall, at the Contractor’s option, either: (a) make such changes, modifications, and/or additions to the Facilities or any part thereof that are necessary to attain the Functional Guarantees at its cost and expense, and shall request the Employer to repeat the Guarantee Test; or (b) pay liquidated damages to the Employer in respect of the failure to meet the Functional Guarantees in accordance with the provisions in the Appendix (Functional Guarantees) to the Contract Agreement. 28.4 The payment of liquidated damages under GC Sub-Clause 28.3, up to the limitation of liability specified in the Appendix (Functional Guarantees) to the Contract Agreement, shall completely satisfy the Contractor’s guarantees under GC Sub-Clause 28.3, and the Contractor shall have no further liability whatsoever to the Employer in respect thereof. Upon the payment of such liquidated damages by the Contractor, the Project Manager shall issue the Operational Acceptance Certificate for the Facilities or any part thereof in respect of which the liquidated damages have been so paid. |
| 29. Patent Indemnity | 29.1 The Contractor shall, subject to the Employer’s compliance with GC Sub-Clause 29.2, indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions, or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, which the Employer may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright, or other intellectual property right registered or otherwise existing at the date of the Contract by reason of (a) the installation of the Facilities by the Contractor or the use of the Facilities in the country where the Site is located, and (b) the sale of the products produced by the Facilities in any country. Such indemnity shall not cover any use of the Facilities or any part thereof other than for the purpose indicated by or to be reasonably inferred from the Contract, any infringement resulting from the use of the Facilities or any part thereof, or any products produced thereby in association or combination with any other equipment, plant, or materials not supplied by the Contractor, pursuant to the Contract Agreement. 29.2 If any proceedings are brought or any claim is made against the Employer arising out of the matters referred to in GC Sub-Clause 29.1, the Employer shall promptly give the Contractor a notice thereof, and the Contractor may at its own expense and in the Employer’s name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim. If the Contractor fails to notify the Employer within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Employer shall be free to conduct the same on its own behalf. Unless the Contractor has so failed to notify the Employer within the twenty-eight (28) day period, the Employer shall make no admission that may be prejudicial to the defense of any such proceedings or claim. The Employer shall, at the Contractor’s request, afford all available assistance to the Contractor in conducting such proceedings or claim, and shall be reimbursed by the Contractor for all reasonable expenses incurred in so doing. 29.3 The Employer shall indemnify and hold harmless the Contractor and its employees, officers, and Subcontractors from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, which the Contractor may suffer as a result of any infringement or alleged infringement of any patent, utility model, registered design, trademark, copyright, or other intellectual property right registered or otherwise existing at the date of the Contract arising out of or in connection with any design, data, drawing, specification, or other documents or materials provided or designed by or on behalf of the Employer. |
| 30. Limitation of Liability | 30.1 Except in cases of criminal negligence or willful misconduct: (a) the Contractor shall not be liable to the Employer, whether in contract, tort, or otherwise, for any indirect or consequential loss or damage, loss of use, loss of production, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the Contractor to pay liquidated damages to the Employer; and (b) the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed a multiple of the Contract Price specified in the PC or, if a multiple is not so specified, the total Contract Price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment, or to any obligation of the Contractor to indemnify the Employer with respect to patent infringement. |

#### G.  Risk Distribution

| 31. Transfer of Ownership | 31.1 Ownership of the Plant (including spare parts) to be imported into the country where the Site is located shall be transferred to the Employer upon loading on to the mode of transport to be used to convey the Plant from the country of origin to that country. 31.2 Ownership of the Plant (including spare parts) procured in the country where the Site is located shall be transferred to the Employer when the Plant are brought on to the Site. 31.3 Ownership of the Contractor’s Equipment used by the Contractor and its Subcontractors in connection with the Contract shall remain with the Contractor or its Subcontractors. 31.4 Ownership of any Plant in excess of the requirements for the Facilities shall revert to the Contractor upon Completion of the Facilities or at such earlier time when the Employer and the Contractor agree that the Plant in question are no longer required for the Facilities. 31.5 Notwithstanding the transfer of ownership of the Plant, the responsibility for care and custody thereof together with the risk of loss or damage thereto shall remain with the Contractor pursuant to GC Clause 32 (Care of Facilities) hereof until Completion of the Facilities or the part thereof in which such Plant are incorporated. |
| --- | --- |
| 32. Care of Facilities | 32.1 The Contractor shall be responsible for the care and custody of the Facilities or any part thereof until the date of Completion of the Facilities pursuant to GC Clause 24 or, where the Contract provides for Completion of the Facilities in parts, until the date of Completion of the relevant part, and shall make good at its own cost any loss or damage that may occur to the Facilities or the relevant part thereof from any cause whatsoever during such period. The Contractor shall also be responsible for any loss or damage to the Facilities caused by the Contractor or its Subcontractors in the course of any work carried out, pursuant to GC Clause 27. Notwithstanding the foregoing, the Contractor shall not be liable for any loss or damage to the Facilities or that part thereof caused by reason of any of the matters specified or referred to in paragraphs (a), (b) and (c) of GC Sub-Clauses 32.2 and 38.1. 32.2 If any loss or damage occurs to the Facilities or any part thereof or to the Contractor’s temporary facilities by reason of: (a) insofar as they relate to the country where the Site is located, nuclear reaction, nuclear radiation, radioactive contamination, pressure wave caused by aircraft or other aerial objects, or any other occurrences that an experienced contractor could not reasonably foresee, or if reasonably foreseeable could not reasonably make provision for or insure against, insofar as such risks are not normally insurable on the insurance market and are mentioned in the general exclusions of the policy of insurance, including War Risks and Political Risks, taken out under GC Clause 34 hereof; (b) any use or occupation by the Employer or any third Party other than a Subcontractor, authorized by the Employer of any part of the Facilities; or (c) any use of or reliance upon any design, data, or specification provided or designated by or on behalf of the Employer, or any such matter for which the Contractor has disclaimed responsibility herein, the Employer shall pay to the Contractor all sums payable in respect of the Facilities executed, notwithstanding that the same be lost, destroyed, or damaged, and will pay to the Contractor the replacement value of all temporary facilities and all parts thereof lost, destroyed, or damaged. If the Employer requests the Contractor in writing to make good any loss or damage to the Facilities thereby occasioned, the Contractor shall make good the same at the cost of the Employer in accordance with GC Clause 39. If the Employer does not request the Contractor in writing to make good any loss or damage to the Facilities thereby occasioned, the Employer shall either request a change in accordance with GC Clause 39, excluding the performance of that part of the Facilities thereby lost, destroyed or damaged, or, where the loss or damage affects a substantial part of the Facilities, the Employer shall terminate the Contract pursuant to GC Sub-Clause 42.1 hereof. 32.3 The Contractor shall be liable for any loss of or damage to any Contractor’s Equipment, or any other property of the Contractor used or intended to be used for purposes of the Facilities, except (i) as mentioned in GC Sub-Clause 32.2 with respect to the Contractor’s temporary facilities, and (ii) where such loss or damage arises by reason of any of the matters specified in GC Sub-Clauses 32.2 (b) and (c) and 38.1. 32.4 With respect to any loss or damage caused to the Facilities or any part thereof or to the Contractor’s Equipment by reason of any of the matters specified in GC Sub-Clause 38.1, the provisions of GC Sub-Clause 38.3 shall apply. |
| 33. Loss of or Damage to Property; Accident or Injury to Workers; Indemnification | 33.1 Subject to GC Sub-Clause 33.3, the Contractor shall indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions, or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, in respect of the death or injury of any person or loss of or damage to any property other than the Facilities whether accepted or not, arising in connection with the supply and installation of the Facilities and by reason of the negligence of the Contractor or its Subcontractors, or their employees, officers, or agents, except any injury, death, or property damage caused by the negligence of the Employer, its contractors, employees, officers, or agents. 33.2 If any proceedings are brought or any claim is made against the Employer that might subject the Contractor to liability under GC Sub-Clause 33.1, the Employer shall promptly give the Contractor a notice thereof and the Contractor may at its own expense and in the Employer’s name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim. If the Contractor fails to notify the Employer within twenty-eighty (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Employer shall be free to conduct the same on its own behalf. Unless the Contractor has so failed to notify the Employer within the twenty-eight (28) day period, the Employer shall make no admission that may be prejudicial to the defense of any such proceedings or claim. The Employer shall, at the Contractor’s request, afford all available assistance to the Contractor in conducting such proceedings or claim, and shall be reimbursed by the Contractor for all reasonable expenses incurred in so doing. 33.3 The Employer shall indemnify and hold harmless the Contractor and its employees, officers, and Subcontractors from any liability for loss of or damage to property of the Employer, other than the Facilities not yet taken over, that is caused by fire, explosion, or any other perils, in excess of the amount recoverable from insurances procured under GC Clause 34, provided that such fire, explosion, or other perils were not caused by any act or failure of the Contractor. 33.4 The Party entitled to the benefit of an indemnity under this GC Clause 33 shall take all reasonable measures to mitigate any loss or damage which has occurred. If the Party fails to take such measures, the other Party’s liabilities shall be correspondingly reduced. |
| 34. Insurance | 34.1 To the extent specified in the Appendix (Insurance Requirements) to the Contract Agreement, the Contractor shall at its expense take out and maintain in effect, or cause to be taken out and maintained in effect, during the performance of the Contract, the insurances set forth below in the sums and with the deductibles and other conditions specified in the said Appendix. The identity of the insurers and the form of the policies shall be subject to the approval of the Employer, who should not unreasonably withhold such approval. (a) Cargo Insurance During Transport Covering loss or damage occurring while in transit from the Contractor’s or Subcontractor’s works or stores until arrival at the Site, to the Plant (including spare parts therefor) and to the Contractor’s Equipment. (b) Installation All Risks Insurance Covering physical loss or damage to the Facilities at the Site, occurring prior to Completion of the Facilities, with an extended maintenance coverage for the Contractor’s liability in respect of any loss or damage occurring during the Defect Liability Period while the Contractor is on the Site for the purpose of performing its obligations during the Defect Liability Period. (c) Third Party Liability Insurance Covering bodily injury or death suffered by third parties including the Employer’s personnel, and loss of or damage to property occurring in connection with the supply and installation of the Facilities. (d) Automobile Liability Insurance Covering use of all vehicles used by the Contractor or its Subcontractors, whether or not owned by them, in connection with the execution of the Contract. (e) Workers’ Compensation In accordance with the statutory requirements applicable in any country where the Contract or any part thereof is executed. (f) Employer’s Liability In accordance with the statutory requirements applicable in any country where the Contract or any part thereof is executed. (g) Other Insurances Such other insurances as may be specifically agreed upon by the parties hereto as listed in the Appendix (Insurance Requirements) to the Contract Agreement. 34.2 The Employer shall be named as co-insured under all insurance policies taken out by the Contractor pursuant to GC Sub-Clause 34.1, except for the Workers’ Compensation, and Employer’s Liability Insurances, and the Contractor’s Subcontractors shall be named as co-insureds under all insurance policies taken out by the Contractor pursuant to GC Sub-Clause 34.1 except for the Cargo Insurance During Transport, Workers’ Compensation, and Employer’s Liability Insurances. All insurer’s rights of subrogation against such co-insureds for losses or claims arising out of the performance of the Contract shall be waived under such policies. 34.3 The Contractor shall, in accordance with the provisions of the Appendix (Insurance Requirements) to the Contract Agreement, deliver to the Employer certificates of insurance or copies of the insurance policies as evidence that the required policies are in full force and effect. The certificates shall provide that no less than twenty-one (21) days’ notice shall be given to the Employer by insurers prior to cancellation or material modification of a policy. 34.4 The Contractor shall ensure that, where applicable, its Subcontractor(s) shall take out and maintain in effect adequate insurance policies for their personnel and vehicles and for work executed by them under the Contract, unless such Subcontractors are covered by the policies taken out by the Contractor. 34.5 The Employer shall at its expense take out and maintain in effect during the performance of the Contract those insurances specified in the Appendix (Insurance Requirements) to the Contract Agreement, in the sums and with the deductibles and other conditions specified in the said Appendix. The Contractor and the Contractor’s Subcontractors shall be named as co-insureds under all such policies. All insurers’ rights of subrogation against such co-insureds for losses or claims arising out of the performance of the Contract shall be waived under such policies. The Employer shall deliver to the Contractor satisfactory evidence that the required insurances are in full force and effect. The policies shall provide that not less than twenty-one (21) days’ notice shall be given to the Contractor by all insurers prior to any cancellation or material modification of the policies. If so requested by the Contractor, the Employer shall provide copies of the policies taken out by the Employer under this GC Sub-Clause 34.5. 34.6 If the Contractor fails to take out and/or maintain in effect the insurances referred to in GC Sub-Clause 34.1, the Employer may take out and maintain in effect any such insurances and may from time to time deduct from any amount due the Contractor under the Contract any premium that the Employer shall have paid to the insurer, or may otherwise recover such amount as a debt due from the Contractor. If the Employer fails to take out and/or maintain in effect the insurances referred to in GC 34.5, the Contractor may take out and maintain in effect any such insurances and may from time to time deduct from any amount due the Employer under the Contract any premium that the Contractor shall have paid to the insurer, or may otherwise recover such amount as a debt due from the Employer. If the Contractor fails to or is unable to take out and maintain in effect any such insurances, the Contractor shall nevertheless have no liability or responsibility towards the Employer, and the Contractor shall have full recourse against the Employer for any and all liabilities of the Employer herein. 34.7 Unless otherwise provided in the Contract, the Contractor shall prepare and conduct all and any claims made under the policies effected by it pursuant to this GC Clause 34, and all monies payable by any insurers shall be paid to the Contractor. The Employer shall give to the Contractor all such reasonable assistance as may be required by the Contractor. With respect to insurance claims in which the Employer’s interest is involved, the Contractor shall not give any release or make any compromise with the insurer without the prior written consent of the Employer. With respect to insurance claims in which the Contractor’s interest is involved, the Employer shall not give any release or make any compromise with the insurer without the prior written consent of the Contractor. |
| 35. Unforeseen Conditions | 35.1 If, during the execution of the Contract, the Contractor shall encounter on the Site any physical conditions other than climatic conditions, or artificial obstructions that could not have been reasonably foreseen prior to the date of the Contract Agreement by an experienced contractor on the basis of reasonable examination of the data relating to the Facilities including any data as to boring tests, provided by the Employer, and on the basis of information that it could have obtained from a visual inspection of the Site if access thereto was available, or other data readily available to it relating to the Facilities, and if the Contractor determines that it will in consequence of such conditions or obstructions incur additional cost and expense or require additional time to perform its obligations under the Contract that would not have been required if such physical conditions or artificial obstructions had not been encountered, the Contractor shall promptly, and before performing additional work or using additional Plant or Contractor’s Equipment, notify the Project Manager in writing of: (a) the physical conditions or artificial obstructions on the Site that could not have been reasonably foreseen; (b) the additional work and/or Plant and/or Contractor’s Equipment required, including the steps which the Contractor will or proposes to take to overcome such conditions or obstructions; (c) the extent of the anticipated delay; and (d) the additional cost and expense that the Contractor is likely to incur. On receiving any notice from the Contractor under this GC Sub-Clause 35.1, the Project Manager shall promptly consult with the Employer and Contractor and decide upon the actions to be taken to overcome the physical conditions or artificial obstructions encountered. Following such consultations, the Project Manager shall instruct the Contractor, with a copy to the Employer, of the actions to be taken. 35.2 Any reasonable additional cost and expense incurred by the Contractor in following the instructions from the Project Manager to overcome such physical conditions or artificial obstructions referred to in GC Sub-Clause 35.1 shall be paid by the Employer to the Contractor as an addition to the Contract Price. - If the Contractor is delayed or impeded in the performance of the Contract because of any such physical conditions or artificial obstructions referred to in GC Sub-Clause 35.1, the Time for Completion shall be extended in accordance with GC Clause 40. |
| 36. Change in Laws and Regulations | 36.1 If, after the date twenty-eight (28) days prior to the date of Bid submission, in the country where the Site is located, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated, or changed, which shall be deemed to include any change in interpretation or application by the competent authorities, that subsequently affects the costs and expenses of the Contractor and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been affected in the performance of any of its obligations under the Contract. Notwithstanding the foregoing, such additional or reduced costs shall not be separately paid or credited if the same has already been accounted for in the price adjustment provisions where applicable, in accordance with the PC, pursuant to GC Sub-Clause 11.2. |
| 37. Force Majeure | 37.1 “Force Majeure” shall mean any event beyond the reasonable control of the Employer or of the Contractor, as the case may be, and which is unavoidable notwithstanding the reasonable care of the Party affected, and shall include, without limitation, the following: (a) war, hostilities, or warlike operations whether a state of war be declared or not, invasion, act of foreign enemy and civil war; (b) rebellion, revolution, insurrection, mutiny, usurpation of civil or military government, conspiracy, riot, civil commotion, and terrorist acts; (c) confiscation, nationalization, mobilization, commandeering or requisition by or under the order of any government or de jure or de facto authority or ruler or any other act or failure to act of any local state or national government authority; (d) strike, sabotage, lockout, embargo, import restriction, port congestion, lack of usual means of public transportation and communication, industrial dispute, shipwreck, shortage or restriction of power supply, epidemics, quarantine, and plague; (e) earthquake, landslide, volcanic activity, fire, flood or inundation, tidal wave, typhoon or cyclone, hurricane, storm, lightning, or other inclement weather condition, nuclear, and pressure waves or other natural or physical disaster; and (f) shortage of labor, materials, or utilities where caused by circumstances that are themselves Force Majeure. 37.2 If either Party is prevented, hindered, or delayed from or in performing any of its obligations under the Contract by an event of Force Majeure, then it shall notify the other in writing of the occurrence of such event and the circumstances thereof within fourteen (14) days after the occurrence of such event. 37.3 The Party who has given such notice shall be excused from the performance or punctual performance of its obligations under the Contract for so long as the relevant event of Force Majeure continues and to the extent that such Party’s performance is prevented, hindered, or delayed. The Time for Completion shall be extended in accordance with GC Clause 40. 37.4 The Party or Parties affected by the event of Force Majeure shall use reasonable efforts to mitigate the effect thereof upon its or their performance of the Contract and to fulfill its or their obligations under the Contract, but without prejudice to either Party’s right to terminate the Contract under GC Sub-Clauses 37.6 and 38.5. 37.5 No delay or nonperformance by either Party hereto caused by the occurrence of any event of Force Majeure shall: (a) constitute a default or breach of the Contract; or (b) give rise to any claim for damages or additional cost or expense occasioned thereby, subject to GC Sub-Clauses 32.2, 38.3 and 38.4 if and to the extent that such delay or nonperformance is caused by the occurrence of an event of Force Majeure. 37.6 If the performance of the Contract is substantially prevented, hindered, or delayed for a single period of more than sixty (60) days or an aggregate period of more than one hundred and twenty (120) days on account of one or more events of Force Majeure during the currency of the Contract, the parties will attempt to develop a mutually satisfactory solution, failing which either Party may terminate the Contract by giving a notice to the other, but without prejudice to either Party’s right to terminate the Contract under GC Sub-Clause 38.5. 37.7 In the event of termination pursuant to GC Sub-Clause 37.6, the rights and obligations of the Employer and the Contractor shall be as specified in GC Sub-Clauses 42.1.2 and 42.1.3. 37.8 Notwithstanding GC Sub-Clause 37.5, Force Majeure shall not apply to any obligation of the Employer to make payments to the Contractor herein. |
| 38. War Risks | 38.1 “War Risks” shall mean any event specified in paragraphs (a) and (b) of GC Sub-Clause 37.1 and any explosion or impact of any mine, bomb, shell, grenade, or other projectile, missile, munitions or explosive of war, occurring or existing in or near the country (or countries) where the Site is located. 38.2 Notwithstanding anything contained in the Contract, the Contractor shall have no liability whatsoever for or with respect to: (a) destruction of or damage to Facilities, Plant, or any part thereof; (b) destruction of or damage to property of the Employer or any third Party; or (c) injury or loss of life if such destruction, damage, injury or loss of life is caused by any war risks, and the Employer shall indemnify and hold the Contractor harmless from and against any and all claims, liabilities, actions, lawsuits, damages, costs, charges, or expenses arising in consequence of or in connection with the same. 38.3 If the Facilities or any Plant or Contractor’s Equipment or any other property of the Contractor used or intended to be used for the purposes of the Facilities shall sustain destruction or damage by reason of any war risks, the Employer shall pay the Contractor for: (a) any part of the Facilities or the Plant so destroyed or damaged to the extent not already paid for by the Employer and so far as may be required by the Employer, and as may be necessary for completion of the Facilities; (b) replacing or making good any Contractor’s Equipment or other property of the Contractor so destroyed or damaged; and (c) replacing or making good any such destruction or damage to the Facilities or the Plant or any part thereof. If the Employer does not require the Contractor to replace or make good any such destruction or damage to the Facilities, the Employer shall either request a change in accordance with GC Clause 39, excluding the performance of that part of the Facilities thereby destroyed or damaged or, where the loss, destruction, or damage affects a substantial part of the Facilities, shall terminate the Contract, pursuant to GC Sub-Clause 42.1. If the Employer requires the Contractor to replace or make good on any such destruction or damage to the Facilities, the Time for Completion shall be extended in accordance with GC Clause 40. 38.4 Notwithstanding anything contained in the Contract, the Employer shall pay the Contractor for any increased costs or incidentals to the execution of the Contract that are in any way attributable to, consequent on, resulting from, or in any way connected with any war risks, provided that the Contractor shall as soon as practicable notify the Employer in writing of any such increased cost. 38.5 If during the performance of the Contract any war risks shall occur that financially or otherwise materially affect the execution of the Contract by the Contractor, the Contractor shall use its reasonable efforts to execute the Contract with due and proper consideration given to the safety of its and its Subcontractors’ personnel engaged in the work on the Facilities, provided, however, that if the execution of the work on the Facilities becomes impossible or is substantially prevented for a single period of more than sixty (60) days or an aggregate period of more than one hundred and twenty (120) days on account of any war risks, the parties will attempt to develop a mutually satisfactory solution, failing which either Party may terminate the Contract by giving a notice to the other. 38.6 In the event of termination pursuant to GC Sub-Clauses 38.3 or 38.5, the rights and obligations of the Employer and the Contractor shall be specified in GC Sub-Clauses 42.1.2 and 42.1.3. |

#### H. Change in Contract Elements

| 39. Change in the Facilities | 39.1 Introducing a Change 39.1.1 Subject to GC Sub-Clauses 39.2.5 and 39.2.7, the Employer shall have the right to propose, and subsequently require, that the Project Manager order the Contractor from time to time during the performance of the Contract to make any change, modification, addition, or deletion to, in or from the Facilities hereinafter called “Change,” provided that such Change falls within the general scope of the Facilities and does not constitute unrelated work and that it is technically practicable, taking into account both the state of advancement of the Facilities and the technical compatibility of the Change envisaged with the nature of the Facilities as specified in the Contract. 39.1.2 The Contractor may from time to time during its performance of the Contract propose to the Employer with a copy to the Project Manager, any Change that the Contractor considers necessary or desirable to improve the quality, efficiency, or safety of the Facilities. The Employer may at its discretion approve or reject any Change proposed by the Contractor, provided that the Employer shall approve any Change proposed by the Contractor to ensure the safety of the Facilities. 39.1.3 Notwithstanding GC Sub-Clauses 39.1.1 and 39.1.2, no change made necessary because of any default of the Contractor in the performance of its obligations under the Contract shall be deemed to be a Change, and such change shall not result in any adjustment of the Contract Price or the Time for Completion. 39.1.4 The procedure on how to proceed with and execute Changes is specified in GC Sub-Clauses 39.2 and 39.3, and further details and forms are provided in the Employer’s Requirements (Forms and Procedures). 39.2 Changes Originating from Employer 39.2.1 If the Employer proposes a Change pursuant to GC Sub-Clause 39.1.1, it shall send to the Contractor a “Request for Change Proposal,” requiring the Contractor to prepare and furnish to the Project Manager as soon as reasonably practicable a “Change Proposal,” which shall include the following: (a) brief description of the Change; (b) effect on the Time for Completion; (c) estimated cost of the Change; (d) effect on Functional Guarantees (if any); (e) effect on the Facilities; and (f) effect on any other provisions of the Contract. 39.2.2 Prior to preparing and submitting the “Change Proposal,” the Contractor shall submit to the Project Manager an “Estimate for Change Proposal,” which shall be an estimate of the cost of preparing and submitting the Change Proposal. Upon receipt of the Contractor’s Estimate for Change Proposal, the Employer shall do one of the following: (a) accept the Contractor’s estimate with instructions to the Contractor to proceed with the preparation of the Change Proposal; (b) advise the Contractor of any part of its Estimate for Change Proposal that is unacceptable and request the Contractor to review its estimate; or (c) advise the Contractor that the Employer does not intend to proceed with the Change. 39.2.3 Upon receipt of the Employer’s instruction to proceed under GC Sub-Clause 39.2.2 (a), the Contractor shall, with proper expedition, proceed with the preparation of the Change Proposal, in accordance with GC Sub-Clause 39.2.1. 39.2.4 The pricing of any Change shall, as far as practicable, be calculated in accordance with the rates and prices included in the Contract. If such rates and prices are inequitable, the parties thereto shall agree on specific rates for the valuation of the Change. 39.2.5 If before or during the preparation of the Change Proposal it becomes apparent that the aggregate effect of compliance therewith and with all other Change Orders that have already become binding upon the Contractor under this GC Clause 39 would be to increase or decrease the Contract Price as originally set forth in Article 2 (Contract Price) of the Contract Agreement by more than fifteen percent (15%), the Contractor may give a written notice of objection thereto prior to furnishing the Change Proposal as aforesaid. If the Employer accepts the Contractor’s objection, the Employer shall withdraw the proposed Change and shall notify the Contractor in writing thereof. The Contractor’s failure to so object shall neither affect its right to object to any subsequent requested Changes or Change Orders herein, nor affect its right to take into account, when making such subsequent objection, the percentage increase or decrease in the Contract Price that any Change not objected to by the Contractor represents. 39.2.6 Upon receipt of the Change Proposal, the Employer and the Contractor shall mutually agree upon all matters therein contained. Within fourteen (14) days after such agreement, the Employer shall, if it intends to proceed with the Change, issue the Contractor with a Change Order. If the Employer is unable to reach a decision within fourteen (14) days, it shall notify the Contractor with details of when the Contractor can expect a decision. If the Employer decides not to proceed with the Change for whatever reason, it shall, within the said period of fourteen (14) days, notify the Contractor accordingly. Under such circumstances, the Contractor shall be entitled to reimbursement of all costs reasonably incurred by it in the preparation of the Change Proposal, provided that these do not exceed the amount given by the Contractor in its Estimate for Change Proposal submitted in accordance with GC Sub-Clause 39.2.2. 39.2.7 If the Employer and the Contractor cannot reach agreement on the price for the Change, an equitable adjustment to the Time for Completion, or any other matters identified in the Change Proposal, the Employer may nevertheless instruct the Contractor to proceed with the Change by issue of a “Pending Agreement Change Order.” Upon receipt of a Pending Agreement Change Order, the Contractor shall immediately proceed with effecting the Changes covered by such Order. The parties shall thereafter attempt to reach agreement on the outstanding issues under the Change Proposal. If the parties cannot reach agreement within sixty (60) days from the date of issue of the Pending Agreement Change Order, then the matter may be referred to the Dispute Board in accordance with the provisions of GC Sub-Clause 45.3. 39.3 Changes Originating from Contractor 39.3.1 If the Contractor proposes a Change pursuant to GC Sub-Clause 39.1.2, the Contractor shall submit to the Project Manager a written “Application for Change Proposal,” giving reasons for the proposed Change and including the information specified in GC Sub-Clause 39.2.1. Upon receipt of the Application for Change Proposal, the parties shall follow the procedures outlined in GC Sub-Clauses 39.2.6 and 39.2.7. However, should the Employer choose not to proceed, the Contractor shall not be entitled to recover the costs of preparing the Application for Change Proposal. |
| --- | --- |
| 40. Extension of Time for Completion | 40.1 The Time(s) for Completion specified in the PC shall be extended if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: (a) any Change in the Facilities as provided in GC Clause 39; (b) any occurrence of Force Majeure as provided in GC Clause 37, unforeseen conditions as provided in GC Clause 35, or other occurrence of any of the matters specified or referred to in paragraphs (a), (b) and (c) of GC Sub-Clause 32.2; (c) any suspension order given by the Employer under GC Clause 41 hereof or reduction in the rate of progress pursuant to GC Sub-Clause 41.2; (d) any changes in laws and regulations as provided in GC Clause 36; (e) any default or breach of the Contract by the Employer, or any activity, act or omission of the Employer, or the Project Manager, or any other contractors employed by the Employer; (f) any delay on the part of a sub-contractor, provided such delay is due to a cause for which the Contractor himself would have been entitled to an extension of time under this Sub-Clause; (g) delays attributable to the Employer or caused by customs; or (h) any other matter specifically mentioned in the Contract by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor. 40.2 Except where otherwise specifically provided in the Contract, the Contractor shall submit to the Project Manager a notice of a claim for an extension of the Time for Completion, together with particulars of the event or circumstance justifying such extension as soon as reasonably practicable after the commencement of such event or circumstance. As soon as reasonably practicable after receipt of such notice and supporting particulars of the claim, the Employer and the Contractor shall agree upon the period of such extension. In the event that the Contractor does not accept the Employer’s estimate of a fair and reasonable time extension, the Contractor shall be entitled to refer the matter to a Dispute Board, pursuant to GC Sub-Clause 45.3. 40.3 The Contractor shall at all times use its reasonable efforts to minimize any delay in the performance of its obligations under the Contract. In all cases where the Contractor has given a notice of a claim for an extension of time under GC Sub-Clause 40.2, the Contractor shall consult with the Project Manager in order to determine the steps (if any) which can be taken to overcome or minimize the actual or anticipated delay. The Contractor shall there after comply with all reasonable instructions, which the Project Manager shall give in order to minimize such delay. If compliance with such instructions shall cause the Contractor to incur extra costs and the Contractor is entitled to an extension of time under GC Sub-Clause 40.1, the amount of such extra costs shall be added to the Contract Price. |
| 41. Suspension | 41.1 The Employer may request the Project Manager, by notice to the Contractor, to order the Contractor to suspend performance of any or all of its obligations under the Contract. Such notice shall specify the obligation of which performance is to be suspended, the effective date of the suspension and the reasons therefor. The Contractor shall thereupon suspend performance of such obligation, except those obligations necessary for the care or preservation of the Facilities, until ordered in writing to resume such performance by the Project Manager. If, by virtue of a suspension order given by the Project Manager, other than by reason of the Contractor’s default or breach of the Contract, the Contractor’s performance of any of its obligations is suspended for an aggregate period of more than ninety (90) days, then at any time thereafter and provided that at that time such performance is still suspended, the Contractor may give a notice to the Project Manager requiring that the Employer shall, within twenty-eight (28) days of receipt of the notice, order the resumption of such performance or request and subsequently order a change in accordance with GC Clause 39, excluding the performance of the suspended obligations from the Contract. If the Employer fails to do so within such period, the Contractor may, by a further notice to the Project Manager, elect to treat the suspension, where it affects a part only of the Facilities, as a deletion of such part in accordance with GC Clause 39 or, where it affects the whole of the Facilities, as termination of the Contract under GC Sub-Clause 42.1. 41.2 If (a) the Employer has failed to pay the Contractor any sum due under the Contract within the specified period, has failed to approve any invoice or supporting documents without just cause pursuant to the Appendix (Terms and Procedures of Payment) to the Contract Agreement, or commits a substantial breach of the Contract, the Contractor may give a notice to the Employer that requires payment of such sum, with interest thereon as stipulated in GC Sub-Clause 12.3, requires approval of such invoice or supporting documents, or specifies the breach and requires the Employer to remedy the same, as the case may be. If the Employer fails to pay such sum together with such interest, fails to approve such invoice or supporting documents or give its reasons for withholding such approval, or fails to remedy the breach or take steps to remedy the breach within fourteen (14) days after receipt of the Contractor’s notice; or (b) the Contractor is unable to carry out any of its obligations under the Contract for any reason attributable to the Employer, including but not limited to the Employer’s failure to provide possession of or access to the Site or other areas in accordance with GC Sub-Clause 10.2, or failure to obtain any governmental permit necessary for the execution and/or completion of the Facilities, then the Contractor may by fourteen (14) days’ notice to the Employer suspend performance of all or any of its obligations under the Contract, or reduce the rate of progress. 41.3 If the Contractor’s performance of its obligations is suspended, or the rate of progress is reduced pursuant to this GC Clause 41, then the Time for Completion shall be extended in accordance with GC Sub-Clause 40.1, and any and all additional costs or expenses incurred by the Contractor as a result of such suspension or reduction shall be paid by the Employer to the Contractor in addition to the Contract Price, except in the case of suspension order or reduction in the rate of progress by reason of the Contractor’s default or breach of the Contract. 41.4 During the period of suspension, the Contractor shall not remove from the Site any Plant, any part of the Facilities or any Contractor’s Equipment, without the prior written consent of the Employer. |
| 42. Termination | 42.1 Termination for Employer’s Convenience 42.1.1 The Employer may at any time terminate the Contract for any reason by giving the Contractor a notice of termination that refers to this GC Sub-Clause 42.1. 42.1.2 Upon receipt of the notice of termination under GC Sub-Clause 42.1.1, the Contractor shall, either immediately or upon the date specified in the notice of termination: (a) cease all further work, except for such work as the Employer may specify in the notice of termination for the sole purpose of protecting that part of the Facilities already executed, or any work required to leave the Site in a clean and safe condition; (b) terminate all subcontracts, except those to be assigned to the Employer pursuant to paragraph (d) (ii) below; (c) remove all Contractor’s Equipment from the Site, repatriate the Contractor’s and its Subcontractors’ personnel from the Site, remove from the Site any wreckage, rubbish and debris of any kind, and leave the whole of the Site in a clean and safe condition; and (d) subject to the payment specified in GC Sub-Clause 42.1.3: (i) deliver to the Employer the parts of the Facilities executed by the Contractor up to the date of termination; (ii) to the extent legally possible, assign to the Employer all right, title and benefit of the Contractor to the Facilities and to the Plant as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Contractor and its Subcontractors; and (iii) deliver to the Employer all non-proprietary drawings, specifications and other documents prepared by the Contractor or its Subcontractors as at the date of termination in connection with the Facilities. 42.1.3 In the event of termination of the Contract under GC Sub-Clause 42.1.1, the Employer shall pay to the Contractor the following amounts: (a) the Contract Price, properly attributable to the parts of the Facilities executed by the Contractor as of the date of termination; (b) the costs reasonably incurred by the Contractor in the removal of the Contractor’s Equipment from the Site and in the repatriation of the Contractor’s and its Subcontractors’ personnel; (c) any amounts to be paid by the Contractor to its Subcontractors in connection with the termination of any subcontracts, including any cancellation charges; (d) costs incurred by the Contractor in protecting the Facilities and leaving the Site in a clean and safe condition pursuant to paragraph (a) of GC Sub-Clause 42.1.2; and (e) the cost of satisfying all other obligations, commitments and claims that the Contractor may in good faith have undertaken with third parties in connection with the Contract and that are not covered by paragraphs (a) through (d) above. 42.2 Termination for Contractor’s Default 42.2.1 The Employer, without prejudice to any other rights or remedies it may possess, may terminate the Contract forthwith in the following circumstances by giving a notice of termination and its reasons therefor to the Contractor, referring to this GC Sub-Clause 42.2: (a) if the Contractor becomes bankrupt or insolvent, has a receiving order issued against it, compounds with its creditors, or, if the Contractor is a corporation, a resolution is passed or order is made for its winding up, other than a voluntary liquidation for the purposes of amalgamation or reconstruction, a receiver is appointed over any part of its undertaking or assets, or if the Contractor takes or suffers any other analogous action in consequence of debt; (b) if the Contractor assigns or transfers the Contract or any right or interest therein in violation of the provision of GC Clause 43; and (c) if the Contractor, in the judgment of the Employer has engaged in integrity violations, as defined in GC Clause 6, in competing for or in executing the Contract. 42.2.2 If the Contractor: (a) has abandoned or repudiated the Contract; (b) has without valid reason failed to commence work on the Facilities promptly or has suspended, other than pursuant to GC Sub-Clause 41.2, the progress of Contract performance for more than twenty-eight (28) days after receiving a written instruction from the Employer to proceed; (c) persistently fails to execute the Contract in accordance with the Contract or persistently neglects to carry out its obligations under the Contract without just cause; and (d) refuses or is unable to provide sufficient materials, services or labor to execute and complete the Facilities in the manner specified in the program furnished under GC Sub-Clause 18.2 at rates of progress that give reasonable assurance to the Employer that the Contractor can attain Completion of the Facilities by the Time for Completion as extended, then the Employer may, without prejudice to any other rights it may possess under the Contract, give a notice to the Contractor, stating the nature of the default and requiring the Contractor to remedy the same. If the Contractor fails to remedy or to take steps to remedy the same within fourteen (14) days of its receipt of such notice, then the Employer may terminate the Contract forthwith by giving a notice of termination to the Contractor that refers to this GC Sub-Clause 42.2. 42.2.3 Upon receipt of the notice of termination under GC Sub-Clauses 42.2.1 or 42.2.2, the Contractor shall, either immediately or upon such date as is specified in the notice of termination: (a) cease all further work, except for such work as the Employer may specify in the notice of termination for the sole purpose of protecting that part of the Facilities already executed, or any work required to leave the Site in a clean and safe condition; (b) terminate all subcontracts, except those to be assigned to the Employer pursuant to paragraph (d) below; (c) deliver to the Employer the parts of the Facilities executed by the Contractor up to the date of termination; (d) to the extent legally possible, assign to the Employer all right, title and benefit of the Contractor to the Facilities and to the Plant as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Contractor and its Subcontractors; and (e) deliver to the Employer all drawings, specifications and other documents prepared by the Contractor or its Subcontractors as of the date of termination in connection with the Facilities. 42.2.4 The Employer may enter upon the Site, expel the Contractor, and complete the Facilities itself or by employing any third Party. The Employer may, to the exclusion of any right of the Contractor over the same, take over and use with the payment of a fair rental rate to the Contractor, with all the maintenance costs to the account of the Employer and with an indemnification by the Employer for all liability including damage or injury to persons arising out of the Employer’s use of such equipment, any Contractor’s Equipment owned by the Contractor and on the Site in connection with the Facilities for such reasonable period as the Employer considers expedient for the supply and installation of the Facilities. Upon completion of the Facilities or at such earlier date as the Employer thinks appropriate, the Employer shall give notice to the Contractor that such Contractor’s Equipment will be returned to the Contractor at or near the Site and shall return such Contractor’s Equipment to the Contractor in accordance with such notice. The Contractor shall thereafter without delay and at its cost remove or arrange removal of the same from the Site. 42.2.5 Subject to GC Sub-Clause 42.2.6, the Contractor shall be entitled to be paid the Contract Price attributable to the Facilities executed as of the date of termination, the value of any unused or partially used Plant on the Site, and the costs, if any, incurred in protecting the Facilities and in leaving the Site in a clean and safe condition pursuant to paragraph (a) of GC Sub-Clause 42.2.3. Any sums due the Employer from the Contractor accruing prior to the date of termination shall be deducted from the amount to be paid to the Contractor under this Contract. 42.2.6 If the Employer completes the Facilities, the cost of completing the Facilities by the Employer shall be determined. If the sum that the Contractor is entitled to be paid, pursuant to GC Sub-Clause 42.2.5, plus the reasonable costs incurred by the Employer in completing the Facilities, exceeds the Contract Price, the Contractor shall be liable for such excess. If such excess is greater than the sums due the Contractor under GC Sub-Clause 42.2.5, the Contractor shall pay the balance to the Employer, and if such excess is less than the sums due the Contractor under GC Sub-Clause 42.2.5, the Employer shall pay the balance to the Contractor. The Employer and the Contractor shall agree, in writing, on the computation described above and the manner in which any sums shall be paid. 42.3 Termination by Contractor 42.3.1 If (a) the Employer has failed to pay the Contractor any sum due under the Contract within the specified period, has failed to approve any invoice or supporting documents without just cause pursuant to the Appendix (Terms and Procedures of Payment) to the Contract Agreement, or commits a substantial breach of the Contract, the Contractor may give a notice to the Employer that requires payment of such sum, with interest thereon as stipulated in GC Sub-Clause 12.3, requires approval of such invoice or supporting documents, or specifies the breach and requires the Employer to remedy the same, as the case may be. If the Employer fails to pay such sum together with such interest, fails to approve such invoice or supporting documents or give its reasons for withholding such approval, fails to remedy the breach or take steps to remedy the breach within fourteen (14) days after receipt of the Contractor’s notice; or (b) the Contractor is unable to carry out any of its obligations under the Contract for any reason attributable to the Employer, including but not limited to the Employer’s failure to provide possession of or access to the Site or other areas or failure to obtain any governmental permit necessary for the execution and/or completion of the Facilities, then the Contractor may give a notice to the Employer thereof, and if the Employer has failed to pay the outstanding sum, to approve the invoice or supporting documents, to give its reasons for withholding such approval, or to remedy the breach within twenty-eight (28) days of such notice, or if the Contractor is still unable to carry out any of its obligations under the Contract for any reason attributable to the Employer within twenty-eight (28) days of the said notice, the Contractor may by a further notice to the Employer referring to this GC Sub-Clause 42.3.1, forthwith terminate the Contract. 42.3.2 The Contractor may terminate the Contract forthwith by giving a notice to the Employer to that effect, referring to this GC Sub-Clause 42.3.2, if the Employer becomes bankrupt or insolvent, has a receiving order issued against it, compounds with its creditors, or, being a corporation, if a resolution is passed or order is made for its winding up (other than a voluntary liquidation for the purposes of amalgamation or reconstruction), a receiver is appointed over any part of its undertaking or assets, or if the Employer takes or suffers any other analogous action in consequence of debt. 42.3.3 If the Contract is terminated under GC Sub-Clauses 42.3.1 or 42.3.2, then the Contractor shall immediately: (a) cease all further work, except for such work as may be necessary for the purpose of protecting that part of the Facilities already executed, or any work required to leave the Site in a clean and safe condition; (b) terminate all subcontracts, except those to be assigned to the Employer pursuant to paragraph (d) (ii); (c) remove all Contractor’s Equipment from the Site and repatriate the Contractor’s and its Subcontractors’ personnel from the Site; and (d) subject to the payment specified in GC Sub-Clause 42.3.4: (i) deliver to the Employer the parts of the Facilities executed by the Contractor up to the date of termination; (ii) to the extent legally possible, assign to the Employer all right, title and benefit of the Contractor to the Facilities and to the Plant as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Contractor and its Subcontractors; and (iii) deliver to the Employer all drawings, specifications and other documents prepared by the Contractor or its Subcontractors as of the date of termination in connection with the Facilities. 42.3.4 If the Contract is terminated under GC Sub-Clauses 42.3.1 or 42.3.2, the Employer shall pay to the Contractor all payments specified in GC Sub-Clause 42.1.3, and reasonable compensation for all loss, except for loss of profit, or damage sustained by the Contractor arising out of, in connection with or in consequence of such termination. 42.3.5 Termination by the Contractor pursuant to this GC Sub-Clause 42.3 is without prejudice to any other rights or remedies of the Contractor that may be exercised in lieu of or in addition to rights conferred by GC Sub-Clause 42.3. 42.4 In this GC Clause 42, the expression “Facilities executed” shall include all work executed, Installation Services provided, and all Plant acquired, or subject to a legally binding obligation to purchase, by the Contractor and used or intended to be used for the purpose of the Facilities, up to and including the date of termination. 42.5 In this GC Clause 42, in calculating any monies due from the Employer to the Contractor, account shall be taken of any sum previously paid by the Employer to the Contractor under the Contract, including any advance payment paid pursuant to the Appendix (Terms and Procedures of Payment) to the Contract Agreement. |
| 43. Assignment | 43.1 Neither the Employer nor the Contractor shall, without the express prior written consent of the other Party which consent shall not be unreasonably withheld, assign to any third Party the Contract or any part thereof, or any right, benefit, obligation or interest therein or thereunder, except that the Contractor shall be entitled to assign either absolutely or by way of charge any monies due and payable to it or that may become due and payable to it under the Contract. |

#### I.  Claims, Disputes, and Arbitration

| 44. Contractor’s Claims | 44.1 If the Contractor considers himself to be entitled to any extension of the Time for Completion and/or any additional payment, under any Clause of these Conditions or otherwise in connection with the Contract, the Contractor shall submit a notice to the Project Manager, describing the event or circumstance giving rise to the claim. The notice shall be given as soon as practicable, and not later than twenty-eight (28) days after the Contractor became aware, or should have become aware, of the event or circumstance. If the Contractor fails to give notice of a claim within such period of twenty-eight (28) days, the Time for Completion shall not be extended, the Contractor shall not be entitled to additional payment, and the Employer shall be discharged from all liability in connection with the claim. Otherwise, the following provisions of this Sub-Clause shall apply. The Contractor shall also submit any other notices, which are required by the Contract, and supporting particulars for the claim, all as relevant to such event or circumstance. The Contractor shall keep such contemporary records as may be necessary to substantiate any claim, either on the Site or at another location acceptable to the Project Manager. Without admitting the Employer’s liability, the Project Manager may, after receiving any notice under this Sub-Clause, monitor the record keeping and/or instruct the Contractor to keep further contemporary records. The Contractor shall permit the Project Manager to inspect all these records, and shall (if instructed) submit copies to the Project Manager. Within forty-two (42) days after the Contractor became aware (or should have become aware) of the event or circumstance giving rise to the claim, or within such other period as may be proposed by the Contractor and approved by the Project Manager, the Contractor shall send to the Project Manager a fully detailed claim, which includes full supporting particulars of the basis of the claim and of the extension of time and/or additional payment claimed. If the event or circumstance giving rise to the claim has a continuing effect: - this fully detailed claim shall be considered as interim; - the Contractor shall send further interim claims at monthly intervals, giving the accumulated delay and/or amount claimed, and such further particulars as the Project Manager may reasonably require; and - the Contractor shall send a final claim within twenty-eight (28) days after the end of the effects resulting from the event or circumstance, or within such other period as may be proposed by the Contractor and approved by the Project Manager. Within forty-two (42) days after receiving a claim or any further particulars supporting a previous claim, or within such other period as may be proposed by the Project Manager and approved by the Contractor, the Project Manager shall respond with approval, or with disapproval and detailed comments. He may also request any necessary further particulars, but shall nevertheless give his response on the principles of the claim within such time. Each payment certificate shall include such amounts for any claim as have been reasonably substantiated as due under the relevant provision of the Contract. Unless and until the particulars supplied are sufficient to substantiate the whole of the claim, the Contractor shall only be entitled to payment for such part of the claim as he has been able to substantiate. The Project Manager shall agree with the Contractor or estimate: (i) the extension (if any) of the Time for Completion (before or after its expiry) in accordance with GC Clause 40, and/or (ii) the additional payment (if any) to which the Contractor is entitled under the Contract. The requirements of this Sub-Clause are in addition to those of any other Sub-Cause, which may apply to a claim. If the Contractor fails to comply with this or another Sub-Clause in relation to any claim, any extension of time and/or additional payment shall take account of the extent (if any) to which the failure has prevented or prejudiced proper investigation of the claim, unless the claim is excluded under the second paragraph of this Sub-Clause. In the event that the Contractor and the Employer cannot agree on any matter relating to a claim, either Party may refer the matter to the Dispute Board pursuant to GC 45 hereof. |
| --- | --- |
| 45. Disputes and Arbitration | 45.1 Appointment of the Dispute Board Disputes shall be referred to a Dispute Board for decision in accordance with GC Sub-Clause 45.3. The Parties shall appoint a Dispute Board by the date stated in the PC. The Dispute Board shall comprise, as stated in the PC, either one or three suitably qualified persons (“the members”), each of whom shall be fluent in the language for communication defined in the Contract and shall be a professional experienced in the type of activities involved in the performance of the Contract and with the interpretation of contractual documents. If the number is not so stated and the Parties do not agree otherwise, the Dispute Board shall comprise three persons, one of whom shall serve as chairman. If the Parties have not jointly appointed the Dispute Board twenty-one (21) days before the date stated in the PC and the Dispute Board is to comprise three persons, each Party shall nominate one member for the approval of the other Party. The first two members shall recommend and the Parties shall agree upon the third member, who shall act as chairman. However, if a list of potential members is included in the PC, the members shall be selected from those on the list, other than anyone who is unable or unwilling to accept appointment to the Dispute Board. The agreement between the Parties and either the sole member or each of the three members shall incorporate by reference the General Conditions of Dispute Board Agreement contained in the Appendix to these General Conditions, with such amendments as are agreed between them. The terms of the remuneration of either the sole member or each of the three members, including the remuneration of any expert whom the Dispute Board consults, shall be mutually agreed upon by the Parties when agreeing the terms of appointment of the member or such expert (as the case may be). Each Party shall be responsible for paying one-half of this remuneration. If a member declines to act or is unable to act as a result of death, disability, resignation or termination of appointment, a replacement shall be appointed in the same manner as the replaced person was required to have been nominated or agreed upon, as described in this Sub-Clause. The appointment of any member may be terminated by mutual agreement of both Parties, but not by the Employer or the Contractor acting alone. Unless otherwise agreed by both Parties, the appointment of the Dispute Board (including each member) shall expire when the Operational Acceptance Certificate has been issued in accordance with GC Sub-Clause 25.3. |
|  | 45.2 Failure to Agree Dispute Board If any of the following conditions apply, namely: the Parties fail to agree upon the appointment of the sole member of the Dispute Board by the date stated in the first paragraph of GC Sub-Clause 45.1; either Party fails to nominate a member (for approval by the other Party) of a Dispute Board of three persons by such date; the Parties fail to agree upon the appointment of the third member (to act as chairman) of the Dispute Board by such date; or the Parties fail to agree upon the appointment of a replacement person within forty-two (42) days after the date on which the sole member or one of the three members declines to act or is unable to act as a result of death, disability, resignation, or termination of appointment, then the appointing entity or official named in the PC shall, upon the request of either or both of the Parties and after due consultation with both Parties, appoint this member of the Dispute Board. This appointment shall be final and conclusive. Each Party shall be responsible for paying one-half of the remuneration of the appointing entity or official. |
|  | 45.3 Obtaining Dispute Board’s Decision If a dispute (of any kind whatsoever) arises between the Parties in connection with the performance of the Contract, including any dispute as to any certificate, determination, instruction, opinion or valuation of the Project Manager, either Party may refer the dispute in writing to the Dispute Board for its decision, with copies to the other Party and the Project Manager. Such reference shall state that it is given under this Sub-Clause. For a Dispute Board of three persons, the Dispute Board shall be deemed to have received such reference on the date when it is received by the chairman of the Dispute Board. Both Parties shall promptly make available to the Dispute Board all such additional information, further access to the Site, and appropriate facilities, as the Dispute Board may require for the purposes of making a decision on such dispute. The Dispute Board shall be deemed to be not acting as arbitrator(s). Within eighty-four (84) days after receiving such reference, or within such other period as may be proposed by the Dispute Board and approved by both Parties, the Dispute Board shall give its decision, which shall be reasoned and shall state that it is given under this Sub-Clause. The decision shall be binding on both Parties, who shall promptly give effect to it unless and until it shall be revised in an amicable settlement or an arbitral award as described below. Unless the Contract has already been abandoned, repudiated or terminated, the Contractor shall continue to proceed with the performance of the Facilities in accordance with the Contract. If either Party is dissatisfied with the Dispute Board’s decision, then either Party may, within 28 days after receiving the decision, give notice to the other Party of its dissatisfaction and intention to commence arbitration. If the Dispute Board fails to give its decision within the period of eighty-four (84) days (or as otherwise approved) after receiving such reference, then either Party may, within twenty-eight (28) days after this period has expired, give notice to the other Party of its dissatisfaction and intention to commence arbitration. In either event, this notice of dissatisfaction shall state that it is given under this Sub-Clause, and shall set out the matter in dispute and the reason(s) for dissatisfaction. Except as stated in GC Sub-Clauses 45.6 and 45.7, neither Party shall be entitled to commence arbitration of a dispute unless a notice of dissatisfaction has been given in accordance with this Sub-Clause. If the Dispute Board has given its decision as to a matter in dispute to both Parties, and no notice of dissatisfaction has been given by either Party within twenty-eighty (28) days after it received the Dispute Board’s decision, then the decision shall become final and binding upon both Parties. |
|  | 45.4 Amicable Settlement Where notice of dissatisfaction has been given under GC Sub-Clause 45.3 above, both Parties shall attempt to settle the dispute amicably before the commencement of arbitration. However, unless both Parties agree otherwise, arbitration may be commenced on or after the fifty-sixth (56) day after the day on which notice of dissatisfaction and intention to commence arbitration was given, even if no attempt at amicable settlement has been made. |
|  | 45.5 Arbitration Any dispute between the Parties arising out of or in connection with the Contract not settled amicably in accordance with GC Sub-Clause 45.4 and in respect of which the Dispute Board’s decision (if any) has not become final and binding shall be finally settled by arbitration. Unless otherwise agreed by both Parties, arbitration shall be conducted as follows: - if the Contract is with foreign Contractors (or if the lead partner is a foreign Contractor, in case of a JVA), international arbitration with proceedings administered by the International Chamber of Commerce (ICC) and conducted under the ICC Rules of Arbitration, by one or more arbitrators appointed in accordance with said arbitration rules; - if the Contract is with domestic Contractors, arbitration with proceedings conducted in accordance with the laws of the Employer’s country. The place of arbitration shall be a neutral location determined in accordance with the applicable rules of arbitration; and the arbitration shall be conducted in the language for communications defined in GC Sub-Clause 5.3 (Law and Language). The arbitrator(s) shall have full power to open up, review and revise any certificate, determination, instruction, opinion or valuation of the Project Manager, and any decision of the Dispute Board, relevant to the dispute. Nothing shall disqualify the Project Manager from being called as a witness and giving evidence before the arbitrator(s) on any matter whatsoever relevant to the dispute. Neither Party shall be limited in the proceedings before the arbitrator(s) to the evidence or arguments previously put before the DB to obtain its decision, or to the reasons for dissatisfaction given in its notice of dissatisfaction. Any decision of the Dispute Board shall be admissible in evidence in the arbitration. Arbitration may be commenced prior to or after completion of the Facilities. The obligations of the Parties, the Project Manager and the Dispute Board shall not be altered by reason of any arbitration being conducted during the progress of the execution of the Facilities. |
|  | 45.6 Failure to Comply with Dispute Board’s Decision - In the event that a Party fails to comply with a Dispute Board decision which has become final and binding, then the other Party may, without prejudice to any other rights it may have, refer the failure itself to arbitration under GC Sub-Clause 45.5. GC Sub-Clauses 45.3 and 45.4 shall not apply to this reference. |
|  | 45.7 Expiry of Dispute Board’s Appointment If a dispute arises between the Parties in connection with the performance of the Contract, and there is no Dispute Board in place, whether by reason of the expiry of the Dispute Board’s appointment or otherwise: - (a) GC Sub-Clauses 45.3 and 45.4 shall not apply; and (b) the dispute may be referred directly to arbitration under GC Sub-Clause 45.5. |

APPENDIX A

General Conditions of Dispute Board Agreement

  - Definitions

Each “Dispute Board Agreement” is a tripartite agreement by and between:

- the “Employer”;

- the “Contractor”; and

- the “Member” who is defined in the Dispute Board Agreement as being:

- the sole member of the "Dispute Board" and, where this is the case, all references to the “Other Members” do not apply; or

- one of the three persons who are jointly called the “Dispute Board” (or “dispute board”) and, where this is the case, the other two persons are called the “Other Members.”

The Employer and the Contractor have entered (or intend to enter) into a contract, which is called the "Contract" and is defined in the Dispute Board Agreement, which incorporates this Appendix. In the Dispute Board Agreement, words and expressions which are not otherwise defined shall have the meanings assigned to them in the Contract.

  - General Provisions

Unless otherwise stated in the Dispute Board Agreement, it shall take effect on the latest of the following dates:

- the Commencement Date defined in the Contract;

- when the Employer, the Contractor and the Member have each signed the Dispute Board Agreement; or

- when the Employer, the Contractor and each of the Other Members (if any) have respectively each signed a dispute board agreement.

This employment of the Member is a personal appointment. At any time, the Member may give not less than seventy (70) days’ notice of resignation to the Employer and to the Contractor, and the Dispute Board Agreement shall terminate upon the expiry of this period.

  - Warranties

The Member warrants and agrees that he/she is and shall be impartial and independent of the Employer, the Contractor and the Project Manager. The Member shall promptly disclose, to each of them and to the Other Members (if any), any fact or circumstance which might appear inconsistent with his/her warranty and agreement of impartiality and independence.

When appointing the Member, the Employer and the Contractor relied upon the Member’s representations that he/she is:

- experienced in the work, which the Contractor is to carry out under the Contract;

- experienced in the interpretation of contract documentation; and

- fluent in the language for communications defined in the Contract.

  - General Obligations of the Member

The Member shall:

- have no interest financial or otherwise in the Employer, the Contractor or the Project Manager, nor any financial interest in the Contract except for payment under the Dispute Board Agreement;

- not previously have been employed as a consultant or otherwise by the Employer, the Contractor, or the Project Manager, except in such circumstances as were disclosed in writing to the Employer and the Contractor before they signed the Dispute Board Agreement;

- have disclosed in writing to the Employer, the Contractor, and the Other Members (if any), before entering into the Dispute Board Agreement and to his/her best knowledge and recollection, any professional or personal relationships with any director, officer, or employee of the Employer, the Contractor, or the Project Manager, and any previous involvement in the overall project of which the Contract forms part;

- not, for the duration of the Dispute Board Agreement, be employed as a consultant or otherwise by the Employer, the Contractor, or the Project Manager, except as may be agreed in writing by the Employer, the Contractor, and the Other Members (if any);

- comply with the annexed procedural rules and with GC Sub-Clause 45.3;

- not give advice to the Employer, the Contractor, the Employer’s Personnel, or the Contractor’s Personnel concerning the conduct of the Contract, other than in accordance with the annexed procedural rules;

- not while a Member enter into discussions or make any agreement with the Employer, the Contractor, or the Project Manager regarding employment by any of them, whether as a consultant or otherwise, after ceasing to act under the Dispute Board Agreement;

- ensure his/her availability for all site visits and hearings as are necessary;

- become conversant with the Contract and with the progress of the Facilities (and of any other parts of the project of which the Contract forms part) by studying all documents received, which shall be maintained in a current working file;

- treat the details of the Contract and all the Dispute Board’s activities and hearings as private and confidential, and not publish or disclose them without the prior written consent of the Employer, the Contractor, and the Other Members (if any); and

- be available to give advice and opinions on any matter relevant to the Contract when requested by both the Employer and the Contractor, subject to the agreement of the Other Members (if any).

  - General Obligations of the Employer and the Contractor

The Employer, the Contractor, the Employer’s Personnel and the Contractor’s Personnel shall not request advice from or consultation with the Member regarding the Contract, otherwise than in the normal course of the Dispute Board’s activities under the Contract and the Dispute Board Agreement. The Employer and the Contractor shall be responsible for compliance with this provision, by the Employer’s Personnel and the Contractor’s Personnel respectively.

The Employer and the Contractor undertake to each other and to the Member that the Member shall not, except as otherwise agreed in writing by the Employer, the Contractor, the Member and the Other Members (if any):

- be appointed as an arbitrator in any arbitration under the Contract;

- be called as a witness to give evidence concerning any dispute before arbitrator(s) appointed for any arbitration under the Contract; or

- be liable for any claims for anything done or omitted in the discharge or purported discharge of the Member’s functions, unless the act or omission is shown to have been in bad faith.

The Employer and the Contractor hereby jointly and severally indemnify and hold the Member harmless against and from claims from which he is relieved from liability under the preceding paragraph.

Whenever the Employer or the Contractor refers a dispute to the Dispute Board under GC Sub-Clause 45.3, which will require the Member to make a site visit and attend a hearing, the Employer or the Contractor shall provide appropriate security for a sum equivalent to the reasonable expenses to be incurred by the Member. No account shall be taken of any other payments due or paid to the Member.

  - Payment

The Member shall be paid as follows, in the currency named in the Dispute Board Agreement:

- a retainer fee per calendar month, which shall be considered as payment in full for:

- being available on twenty-eight (28) days’ notice for all site visits and hearings;

- becoming and remaining conversant with all project developments and maintaining relevant files;

- all office and overhead expenses including secretarial services, photocopying and office supplies incurred in connection with his duties; and

- all services performed hereunder except those referred to in sub-paragraphs (b) and (c) of this Clause.

The retainer fee shall be paid with effect from the last day of the calendar month in which the Dispute Board Agreement becomes effective; until the last day of the calendar month in which the Completion Certificate is issued for the whole of the Facilities.

With effect from the first day of the calendar month following the month in which Completion Certificate is issued for the whole of the Facilities, the retainer fee shall be reduced by one-third. This reduced fee shall be paid until the first day of the calendar month in which the Member resigns or the Dispute Board Agreement is otherwise terminated.

- a daily fee, which shall be considered as payment in full for:

(i)	each day or part of a day up to a maximum of two (2) days’ travel time in each direction for the journey between the Member’s home and the site, or another location of a meeting with the Other Members (if any);

(ii)	each working day on site visits, hearings, or preparing decisions; and

(iii)	each day spent reading submissions in preparation for a hearing.

- all reasonable expenses, including necessary travel expenses (air fare in less than first class, hotel and subsistence and other direct travel expenses) incurred in connection with the Member’s duties, as well as the cost of telephone calls, courier charges, facsimiles, and telexes, and use of the internet: a receipt shall be required for each item in excess of five percent (5%) of the daily fee referred to in sub-paragraph (b) of this Clause.

- any taxes properly levied in the Country on payments made to the Member (unless a national or permanent resident of the Country) under this Clause 6.

The retainer and daily fees shall be as specified in the Dispute Board Agreement. Unless it specifies otherwise, these fees shall remain fixed for the first twenty-four (24) calendar months, and shall thereafter be adjusted by agreement between the Employer, the Contractor and the Member, at each anniversary of the date on which the Dispute Board Agreement became effective.

If the parties fail to agree on the retainer fee or the daily fee, the appointing entity or official named in the PC shall determine the amount of the fees to be used.

The Member shall submit invoices for payment of the monthly retainer and air fares quarterly in advance. Invoices for other expenses and for daily fees shall be submitted following the conclusion of a site visit or hearing. All invoices shall be accompanied by a brief description of activities performed during the relevant period and shall be addressed to the Contractor.

The Contractor shall pay each of the Member’s invoices in full within fifty-six (56) calendar days after receiving each invoice and shall apply to the Employer (in the Statements under the Contract) for reimbursement of one-half of the amounts of these invoices. The Employer shall then pay the Contractor in accordance with the Contract.

If the Contractor fails to pay to the Member the amount to which he/she is entitled under the Dispute Board Agreement, the Employer shall pay the amount due to the Member and any other amount which may be required to maintain the operation of the Dispute Board; and without prejudice to the Employer’s rights or remedies. In addition to all other rights arising from this default, the Employer shall be entitled to reimbursement of all sums paid in excess of one-half of these payments, plus all costs of recovering these sums and financing charges calculated at the rate specified in accordance with GC Sub-Clause 12.3.

If the Member does not receive payment of the amount due within seventy (70) days after submitting a valid invoice, the Member may (i) suspend his/her services (without notice) until the payment is received, and/or (ii) resign his/her appointment by giving notice under Clause 7.

  - Termination

At any time: (i) the Employer and the Contractor may jointly terminate the Dispute Board Agreement by giving forty-two (42) days’ notice to the Member, or (ii) the Member may resign as provided for in Clause 2.

If the Member fails to comply with the Dispute Board Agreement, the Employer and the Contractor may, without prejudice to their other rights, terminate it by notice to the Member. The notice shall take effect when received by the Member.

If the Employer or the Contractor fails to comply with the Dispute Board Agreement, the Member may, without prejudice to his other rights, terminate it by notice to the Employer and the Contractor. The notice shall take effect when received by them both.

Any such notice, resignation and termination shall be final and binding on the Employer, the Contractor and the Member. However, a notice by the Employer or the Contractor, but not by both, shall be of no effect.

  - Default of the Member

If the Member fails to comply with any of his obligations under Clause 4 concerning his impartiality or independence in relation to the Employer or the Contractor, he/she shall not be entitled to any fees or expenses hereunder and shall, without prejudice to their other rights, reimburse each of the Employer and the Contractor for any fees and expenses received by the Member and the Other Members (if any), for proceedings or decisions (if any) of the Dispute Board which are rendered void or ineffective by the said failure to comply.

  - Disputes

Any dispute or claim arising out of or in connection with this Dispute Board Agreement, or the breach, termination or invalidity thereof, shall be finally settled by institutional arbitration. If no other arbitration institute is agreed, the arbitration shall be conducted under the Rules of Arbitration of the International Chamber of Commerce by one arbitrator appointed in accordance with these Rules of Arbitration.

Annex - DISPUTE BOARD GUIDELINES

1. 	Unless otherwise agreed by the Employer and the Contractor, the Dispute Board shall visit the site at intervals of not more than one hundred and forty (140) days, including times of critical construction events, at the request of either the Employer or the Contractor. Unless otherwise agreed by the Employer, the Contractor, and the Dispute Board, the period between consecutive visits shall not be less than seventy (70) days, except as required to convene a hearing as described below.

2.	The timing of and agenda for each site visit shall be as agreed jointly by the Dispute Board, the Employer, and the Contractor, or in the absence of agreement, shall be decided by the Dispute Board. The purpose of site visits is to enable the Dispute Board to become and remain acquainted with the progress of the Contract and of any actual or potential problems or claims, and, as far as reasonable, to prevent potential problems or claims from becoming disputes.

3.	Site visits shall be attended by the Employer, the Contractor, and the Project Manager and shall be coordinated by the Employer in cooperation with the Contractor. The Employer shall ensure the provision of appropriate conference facilities and secretarial and copying services. At the conclusion of each site visit and before leaving the site, the Dispute Board shall prepare a report on its activities during the visit and shall send copies to the Employer and the Contractor.

4.	The Employer and the Contractor shall furnish to the Dispute Board one copy of all documents which the Dispute Board may request, including Contract documents, progress reports, variation instructions, certificates, and other documents pertinent to the performance of the Contract. All communications between the Dispute Board and the Employer or the Contractor shall be copied to the other Party. If the Dispute Board comprises three persons, the Employer and the Contractor shall send copies of these requested documents and these communications to each of these persons.

5.	If any dispute is referred to the Dispute Board in accordance with GC Sub-Clause 45.3, the Dispute Board shall proceed in accordance with GC Sub-Clause 45.3 and these Guidelines. Subject to the time allowed to give notice of a decision and other relevant factors, the Dispute Board shall:

- (a)	act fairly and impartially as between the Employer and the Contractor, giving each of them a reasonable opportunity of putting his case and responding to the other’s case; and

- (b)	adopt procedures suitable to the dispute, avoiding unnecessary delay or expense.

6.	The Dispute Board may conduct a hearing on the dispute, in which event it will decide on the date and place for the hearing and may request that written documentation and arguments from the Employer and the Contractor be presented to it prior to or at the hearing.

7.	Except as otherwise agreed in writing by the Employer and the Contractor, the Dispute Board shall have power to adopt an inquisitorial procedure, to refuse admission to hearings or audience at hearings to any persons other than representatives of the Employer, the Contractor, and the Project Manager, and to proceed in the absence of any Party who received notice of the hearing; but shall have discretion to decide whether and to what extent this power may be exercised.

8.	The Employer and the Contractor empower the Dispute Board, among other things, to:

- (a)	establish the procedure to be applied in deciding a dispute;

- (b)	decide upon the Dispute Board’s own jurisdiction, and as to the scope of any dispute referred to it;

- (c)	conduct any hearing as it thinks fit, not being bound by any rules or procedures other than those contained in the Contract and these Guidelines;

- (d)	take the initiative in ascertaining the facts and matters required for a decision;

- (e)	make use of its own specialist knowledge, if any;

- (f)	decide upon the payment of financing charges in accordance with the Contract;

- (g)	decide upon any provisional relief such as interim or conservatory measures;

- (h)	open up, review and revise any certificate, decision, determination, instruction, opinion or valuation of the Project Manager, relevant to the dispute; and

- (i)	appoint, should the Dispute Board so consider necessary and the Parties agree, a suitable expert at the cost of the Parties to give advice on a specific matter relevant to the dispute.

9.	The Dispute Board shall not express any opinions during any hearing concerning the merits of any arguments advanced by the Parties. Thereafter, the Dispute Board shall make and give its decision in accordance with GC Sub-Clause 45.3, or as otherwise agreed by the Employer and the Contractor in writing. If the Dispute Board comprises three persons:

- (a)	it shall convene in private after a hearing, in order to have discussions and prepare its decision;

- (b)	it shall endeavour to reach a unanimous decision: if this proves impossible the applicable decision shall be made by a majority of the Members, who may require the minority Member to prepare a written report for submission to the Employer and the Contractor; and

- (c)	if a Member fails to attend a meeting or hearing, or to fulfil any required function, the other two Members may nevertheless proceed to make a decision, unless:

(i)	either the Employer or the Contractor does not agree that they do so; or

(ii)	the absent Member is the chairman and he/she instructs the other Members to not make a decision.

Section VIII: Particular Conditions

The following Particular Conditions (PC) shall supplement the General Conditions (GC). Whenever there is a conflict, the provisions herein shall prevail over those in the GC. The clause number of the PC is the corresponding clause number of the GC.

| PC 1. Definitions | The Employer is: [insert Employer’s name] The Project Manager is: [insert Project Manager’s name] The Bank is: The Export-Import Bank of Korea Country of Origin: countries as indicated in Section V (Eligible Countries ) |
| --- | --- |
| PC 5. Law and Language | PC 5.1 The Contract shall be interpreted in accordance with the laws of: [insert name of Employer’s country] PC 5.2 The ruling language is: English PC 5.3 The language for communications is: English |
| PC 7. Scope of Facilities [Spare Parts] (GC Clause 7) | PC 7.1 The Contractor shall install a permanent plaque as part of the Works to enhance accountability and transparency before the Engineer issues the Performance Certificate to the Contractor. The plaque shall display the following information, but is not limited to: - the name of the Contract; - Acknowledgement of the Contract funded by the EDCF from the Korean Government; - the name of the Employer; and - the name of the Engineer and the Contractor. PC 7.3 The Contractor agrees to supply spare parts for a period of years: [insert the same number of years as in Clause 16.1 (b) of the BDS of the Instructions to Bidders] [Where appropriate use the following additional provision to PC 7.3, otherwise delete the provision from this Clause PC 7.3] The Contractor shall carry sufficient inventories to ensure an ex-stock supply of consumable spares for the Plant. Other spare parts and components shall be supplied as promptly as possible, but at the most within six (6) months of placing the order and opening the letter of credit. In addition, in the event of termination of the production of spare parts, advance notification will be made to the Employer of the pending termination, with sufficient time to permit the Employer to procure the needed requirement. Following such termination, the Contractor will furnish to the extent possible and at no cost to the Employer the blueprints, drawings and specifications of the spare parts, if requested. |
| PC 8. Time for Commencement and Completion | PC 8.1 The Contractor shall commence work on the Facilities within [insert number of days as appropriate, in words and figures] days from the Effective Date for determining Time for Completion as specified in the Contract Agreement. PC 8.2 The Time for Completion of the whole of the Facilities shall be [insert number of days (months) in words and figures] from the Effective Date as described in the Contract Agreement. [Where appropriate use the following additional provision to PC 8.2, otherwise delete the provision] The Time for Completion for parts of the Facilities shall be [insert days (months) in words and figures] from the Effective Date as described in the Contract Agreement. [and where applicable] Sample Provision The Time for Completion for parts of the Facilities: Description Time for Completion [Each part of the Facilities subject to a specific Time for Completion shall be listed and briefly described with its respective Time for Completion specified in days, in words and figures.] |
| PC 9. Contractor’s Responsibilities | PC 9.8 The Contractor shall comply with all applicable national, provincial, and local environmental laws and regulations, along with “EDCF Safeguard Policy”. The Contractor shall (a) establish an operational system for managing environmental and social impacts, (b) carry out all of the monitoring and mitigation measures set forth in the Environmental and Social Management Plan ("ESMP") attached hereto as _____________ [Insert the reference of attachment] and (c) allocate the budget required to ensure that such measures are carried out. The Contractor shall submit _____________ [Insert submission period according to “EDCF Safeguard Policy” ] reports on the carrying out of such measures to the Employer. |
| PC 11. Contract Price | [This provision is to be inserted only if Contract Price is subject to adjustment, otherwise delete the provision.] PC 11.1 The Contract Price shall be stated in Korean Won converted by using the exchange rate applicable to the calculation of the amount of the Loan under the provisions of the Loan Agreement. [Should a portion of the Contract Price be permitted to be denominated in other currencies pursuant to the provisions of the Loan Agreement, please provide details herein.] PC 11.2 The Contract Price shall be adjusted in accordance with the provisions of Appendix 2 (Price Adjustment) to the Contract Agreement and shall be paid in Korean Won. [Should a portion of the Contract Price be permitted to be paid in other currencies pursuant to the provisions of the Loan Agreement, please provide details herein.] |
| PC 13. Securities | PC 13.2.2 The Advance Payment Security shall be in the form attached hereto in Section IX (Contract Forms), or another form acceptable to the Employer. The Advance Payment Security shall be issued by a bank, insurance company, or financial institution in the Employer’s country or the Contractor's country whose credit rating is equal or above A- (A3) (equivalent) rated by an international credit rating agency (e.g., S&P, Fitch, or Moody's). [The credit rating may be adjusted based on the financial situations in either the Employer’s or the Contractor’s country] PC 13.3.1 The amount of Performance Security, as a percentage of the Contract Price for the Facility or for the part of the Facility for which a separate Time for Completion is provided, shall be: [insert amount. The amount of the Performance Security is usually expressed as a percentage of the Contract Price. The percentage varies according to the Employer’s perceived risk and impact of nonperformance by the Contractor. A 10% percentage is used under normal circumstances]. PC 13.3.2 The Performance Security shall be in the form attached hereto in Section IX (Contract Forms), or another form acceptable to the Employer. The Performance Security shall be issued by a bank, insurance company, or financial institution in the Employer’s country or the Contractor's country whose credit rating is equal or above A- (A3) (equivalent) rated by an international credit rating agency (e.g., S&P, Fitch, or Moody's). [The credit rating may be adjusted based on the financial situations in either the Employer’s or the Contractor’s country] PC 13.3.3 The Performance Security shall not be reduced on the date of the Operational Acceptance. or PC 13.3.3 The Performance Security shall be reduced to ten percent (10%) of the value of the component covered by the extended defect liability to cover the Contractor’s extended defect liability in accordance with the provision in the PC, pursuant to GC Sub-Clause 27.10. |
| PC 14. Taxes and Duties | PC 14.1 In accordance with the Loan Agreement, all taxes, duties and levies, including but not limited to import duties and Value-Added Tax, imposed on goods, works, Plant and Installation Services in [insert the name of the Borrower’s country], provided and/or purchased from any countries by the Contractor, subcontractors and/or local suppliers of any countries under the Loan Agreement for the implementation of the Project shall either be exempted or borne by the Borrower. Without prejudice to the foregoing, the Employer shall: (i) use its best endeavours to enable the Contractor, subcontractors and/or local suppliers to benefit from any such tax exemption or savings in a timely and expeditious manner; and (ii) pay or reimburse, as the case may be, such taxes, duties and levies as are agreed to be borne by the Borrower under the Loan Agreement immediately after they are due and payable. |
| PC 22. Installation | PC22.2.5 Working Hours Normal working hours are: [insert normal working hours] PC 22.2.8 Funeral Arrangements: [insert any other specific arrangements] |
| PC 25. Commissioning and Operational Acceptance | PC 25.2.2 The Guarantee Test of the Facilities shall be successfully completed within [insert number of days, written in words and figures] from the date of Completion. |
| PC 26. Completion Time Guarantee | PC 26.2 Applicable rate for liquidated damages: [insert a percentage of the Contract Price, or part thereof, in words and figures. The applicable rate should be 0.1% per 1-day delay, 0.5% per 1-week delay] The above rate applies to the price of the part of the Facilities, as quoted in the Price Schedule, for that part for which the Contractor fails to achieve Completion within the particular Time for Completion. Maximum deduction for liquidated damages: [insert a percentage of the Contract Price. The maximum shall not exceed ten percent (10%) of the Contract Price]. PC 26.3 Applicable (amount or rate) for the bonus for early Completion: [insert appropriate amount or rate as a percentage of the Contract Price, or part thereof, in words and figures, per week of early Completion of the Facilities or part thereof, in accordance with the Time for Completion specified in PC 8.2.] Maximum bonus: [insert the maximum amount which should be related to the benefit the Employer will gain in operating the Facilities, or part thereof, earlier than anticipated.] [For a Contract without a bonus, the following provision should be used.] PC 26.3 No bonus will be given for earlier Completion of the Facilities or part thereof. |
| PC 27. Defect Liability | PC 27.10 The critical components covered under the extended defect liability are ____________________, and the period shall be ________________ (to be inserted only when an extended defect liability is requested). |
| PC 30. Limitation of Liability | [Use the following provision only if the aggregate liability is different from the total Contract Price; otherwise delete the provision.] PC 30.1 (b) The multiplier of the Contract Price is: [insert multiplier] |
| PC 45. Disputes and Arbitration | PC 45.1 The Dispute Board shall be appointed within twenty-eight (28) days after the Effective Date. The Dispute Board shall be: [insert either “one sole member” or “a DB of three members.”] [For a Contract estimated to cost above US$ 50 million, the DB shall comprise of three members. For a Contract estimated to cost between US$ 20 million and US$ 50 million, the DB may comprise of three members or a sole member. For a Contract estimated to cost less than US$ 20 million, a sole member is recommended.] PC 45.1 List of potential DB members: [insert names of potential members, if no list is available, delete the provision] Proposed by Employer [Attach CVs to the bidding document and the Contract] 1._____________________ 2.______________________ 3.______________________ Proposed by Contractor [Attach CVs to the Contract] 1.________________________ 2._________________________ 3._________________________ PC 45.2 Appointment (if not agreed) to be made by: [Insert appointing entity or official] |

Section IX: Contract Forms

Table of Forms

Notification of Intention to Award	347

Notification of Award	349

Contract Agreement	350

Appendix 1. Terms and Procedures of Payment	354

Appendix 2. Price Adjustment	357

Appendix 3. Insurance Requirements	359

Appendix 4. Time Schedule	363

Appendix 5. List of Major Items of Plant and Installation Services and List of

Approved Subcontractors	364

Appendix 6: Scope of Works and Supply by the Employer	365

Appendix 7. List of Documents for Approval or Review	366

Appendix 8. Functional Guarantees	367

Form of Performance Security	369

Form of Advance Payment Security	371

### Notification of Intention to Award

[Note: Notification of Intention to Award shall only be included if the Standstill provision is applicable in accordance with ITB 40.1 in the case of one envelope procedure (or ITB 41.1 in the case of two envelope procedure). If the Standstill Period is applied, this Notification of Intention to Award shall be sent simultaneously to each authorized representative of the Bidders who submitted a Bid.]

[Date of Notification]

[Note: insert the date that this Notification is transmitted to all Bidders. The Notification must be sent to all Bidders simultaneously.]

For the attention of Bidder’s authorized representative

Name: [insert authorized representative’s name]

Address: [insert authorized representative’s address]

Telephone/Fax numbers: [insert authorized representative’s telephone/fax numbers]

Email Address: [insert authorized representative’s email address]

This is to notify you of our intention to award the contract [insert the name of contract]. You have three (3) Business Days, from the date of this notification to request for a debriefing in relation to the evaluation of your Bid. The transmission of this Notification begins the Standstill Period, within which a procurement related complaint in relation to the intention to award the contract can be filed in accordance with the procedures and requirements set out in [ITB 46.1 to ITB 46.5 in the case of one envelope procedure (or ITB 47.1 to ITB 47.5 in the case of two envelope procedure)].

The summary of the evaluation are as follows:

1. List of Bidders

| Name of Bidder | Bid Price as Read Out at Bid Opening | Evaluated Bid Price |
| --- | --- | --- |

2. The successful Bidder

| Name: | [insert name of successful Bidder] |
| --- | --- |
| Address: | [insert address of the successful Bidder] |
| Contract price: | [insert contract price of the successful Bidder] |

3. Reason/s why your Bid was unsuccessful

[Note: State the reason/s why this Bidder’s Bid was unsuccessful. Do NOT include: (a) a point by point comparison with another Bidder’s Bid or (b) information that is marked confidential by the Bidder in its Bid.]

If you have any questions regarding this Notification, please do not hesitate to contact us.

On behalf of [insert the name of the Client]:

Signature: ________________________________________

Name: _______________________________________

Title/position: ________________________________________

Telephone: ________________________________________

Email:	________________________________________

### Notification of Award

[Employer's letterhead]

Letter of Acceptance

[date]

To:  [Name and address of the contractor]

This is to notify you that your Bid dated [date] for execution of the [name of the contract and identification number, as given in the Bid Data Sheet] for the Contract Price in the aggregate of [amounts in words and figures] [name of currency], as corrected and modified in accordance with the Instructions to Bidders is hereby accepted by our Agency.

You are requested to furnish the Performance Security within twenty-eight (28) days in accordance with the Conditions of Contract and any additional security required as a result of the evaluation of your bid, using for that purpose one of the Performance Security Forms included in Section IX (Contract Forms) of the Bidding Document.

Authorized Signature:

Name and Title of Signatory:

Name of Agency:

Attachment:  Contract Agreement

### Contract Agreement

THIS AGREEMENT made on the [insert number] day of [insert month], [insert year], BETWEEN

(1) [name of the employer], a corporation incorporated under the laws of [country of the Employer] and having its principal place of business at [address of the Employer] (hereinafter called “the Employer”), and (2) [name of the contractor], a corporation incorporated under the laws of [country of the contractor] and having its principal place of business at [address of the contractor] (hereinafter called “the Contractor”).

WHEREAS the Employer desires to engage the Contractor to design, manufacture, test, deliver, install, complete and commission certain Facilities, viz. [list of facilities] (“the Facilities”) and the Contractor have agreed to such engagement upon and subject to the terms and conditions hereinafter appearing.

NOW IT IS HEREBY AGREED as follows:

| Article 1. Contract Documents | 1.1 Contract Documents (Reference GC Clause 2) The following documents shall constitute the Contract between the Employer and the Contractor, and each shall be read and construed as an integral part of the Contract: - This Contract Agreement and the Appendices hereto - Letter of Technical Bid - Letter of Price Bid - Particular Conditions - General Conditions - Specification - Drawings - Other completed Bidding Forms submitted with the Bid - Any other documents forming part of the Employer’s Requirements - [Any other documents shall be added here] [For One-envelope; substitute “Letter of Bid and Price Schedules submitted by the Contractor” for (b) and (c), and adjust the serial signs accordingly.] 1.2 Order of Precedence (Reference GC Clause 2) In the event of any ambiguity or conflict between the Contract Documents listed above, the order of precedence shall be the order in which the Contract Documents are listed in Article 1.1 (Contract Documents) above. 1.3 Definitions (Reference GC Clause 1) Capitalized words and phrases used herein shall have the same meanings as are ascribed to them in the General Conditions. |
| --- | --- |
| Article 2. Contract Price and Terms of Payment | 2.1 Contract Price (Reference GC Clause 11) The Employer hereby agrees to pay to the Contractor the Contract Price in consideration of the performance by the Contractor of its obligations hereunder. The Contract Price shall be [insert Contract Price in in words and figures, expressed in the Contract currency(ies)] as specified in Price Schedule No. 5 (Grand Summary), or such other sums as may be determined in accordance with the terms and conditions of the Contract. 2.2 Terms of Payment (Reference GC Clause 12) The Contract Price shall be paid by the Employer to the Contractor at the times, in the manner, and in accordance with the provisions of Appendix 1 (Terms and Procedures of Payment) hereto. The Employer shall instruct its bank to issue an irrevocable confirmed documentary credit made available to the Contractor in a bank in the country of the Contractor. The credit shall be for an amount of [amount equal to the total named in Schedule 1 less the advance payment to be made for plant and mandatory spare parts supplied from abroad]; and shall be subject to the Uniform Customs and Practice for Documentary Credits 1993 Revision, ICC Publication No. 600. In the event that the amount payable under Schedule No. 1 is adjusted in accordance with GC 11.2 or with any of the other terms of the Contract, the Employer shall arrange for the documentary credit to be amended accordingly. |
| Article 3. Effective Date | 3.1 Effective Date (Reference GC Clause 1) The Effective Date upon which the period until the Time for Completion of the Facilities shall be counted from is the date when all of the following conditions have been fulfilled: - This Contract Agreement has been duly executed for and on behalf of the Employer and the Contractor; - The Contractor has submitted to the Employer the performance security and the advance payment guarantee; - The Employer has paid the Contractor the advance payment; - The Contractor has been advised that the documentary credit referred to in Article 2.2 above has been issued in its favor; and - Approval in writing of this Contract by the Bank according to the Loan Agreement. Each party shall use its best efforts to fulfill the above conditions for which it is responsible as soon as practicable. 3.2 If the conditions listed under 3.1 are not fulfilled within two (2) months from the date of this Contract notification because of reasons not attributable to the Contractor, the parties shall discuss and agree on an equitable adjustment to the Contract Price and the Time for Completion and/or other relevant conditions of the Contract. |
| Article 4. Communications | 4.1 The address of the Employer for notice purposes, pursuant to GC 4.1 is: [Employer's address]. 4.2 The address of the Contractor for notice purposes, pursuant to GC 4.1 is: [Contractor's address]. |
| Article 5. Appendixes | 5.1 The Appendices listed in the attached List of Appendices shall be deemed to form an integral part of this Contract Agreement. 5.2 Reference in the Contract to any Appendix shall mean the Appendices attached hereto, and the Contract shall be read and construed accordingly. |

IN WITNESS WHEREOF the Employer and the Contractor have caused this Agreement to be duly executed by their duly authorized representatives the day and year first above written.

Signed by, for and on behalf of the Employer

[Signature]

[Title]

in the presence of

Signed by, for and on behalf of the Contractor

[Signature]

[Title]

in the presence of

APPENDICES

Appendix 1:	Terms and Procedures of Payment

Appendix 2:	Price Adjustment

Appendix 3:	Insurance Requirements

Appendix 4:	Time Schedule

Appendix 5:	List of Major Items of Plant and Installation Services and List of Approved Subcontractors

Appendix 6:	Scope of Works and Supply by the Employer

Appendix 7:	List of Documents for Approval or Review

Appendix 8:	Functional Guarantees

#### Appendix 1. Terms and Procedures of Payment

In accordance with the provisions of GC Clause 12 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, based on the Price Breakdown given in the section on Price Schedules. Payments will be made in the currencies in which the Contract Price has been stated in the Contractor’s bid unless otherwise agreed between the parties. Applications for payment in respect of part deliveries may be made by the Contractor as work proceeds.

(A)  Terms of Payment

Schedule No. 1 - Plant and Mandatory Spare Parts Supplied from Abroad

In respect of plant and mandatory spare parts supplied from abroad, the following payments shall be made:

----- percent (--%) of the total CIP amount as an advance payment within twenty-one (21) days after receipt of invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer. The advance payment security may be reduced in proportion to the value of the plant and mandatory spare parts delivered to the site, as evidenced by delivery documents.

----- percent (--%) of the total or pro rata CIP or amount upon Incoterm “CIP,” upon delivery to the carrier within forty-five (45) days after receipt of invoice and documents.

[Employer to state the required documents, such as a negotiable bill of lading, a non-negotiable sea way bill, an airway bill, a railway consignment note, a road consignment note, insurance certificate, etc.]

----- percent (--%) of the total or pro rata CIP or amount upon issue of the Completion Certificate, within forty-five (45) days after receipt of invoice.

----- percent (--%) of the total or pro rata CIP or amount upon issue of the Operational Acceptance Certificate, within 45 days after receipt of invoice.

Schedule No. 2 - Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country

In respect of plant and mandatory spare parts supplied from within the Employer’s country, the following payments shall be made:

----- percent (--%) of the total EXW amount as an advance payment within twenty-one (21) days after receipt of invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer. The advance payment security may be reduced in proportion to the value of the plant and mandatory spare parts delivered to the site, as evidenced by delivery documents.

----- percent (--%) of the total or pro rata EXW amount upon Incoterm “Ex-Works,” upon delivery to the carrier within forty-five (45) days after receipt of invoice and documents.

[Employer to state the required documents, such as a railway consignment note, a road consignment note, insurance certificate, etc.]

----- percent (--%) of the total or pro rata EXW amount upon issue of the Completion Certificate, within forty-five (45) days after receipt of invoice.

----- percent (--%) of the total or pro rata EXW amount upon issue of the Operational Acceptance Certificate, within forty-five (45) days after receipt of invoice.

Schedule No. 3 - Design Services

In respect of design services for both the foreign currency and the local currency portions, the following payments shall be made:

----- percent (--%) of the total design services amount as an advance payment within twenty-one (21) days after receipt of invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer.

----- percent (--%) of the total or pro rata design services amount upon approval of design in accordance with GC Clause 20 by the Project Manager within forty-five (45) days after receipt of invoice.

Schedule No. 4 - Installation and Other Services

In respect of installation services for both the foreign and local currency portions, the following payments shall be made:

----- percent (--%) of the total installation and other services amount as an advance payment within twenty-one (21) days after receipt of invoice and an irrevocable advance payment security for the equivalent amount made out in favor of the Employer.  The advance payment security may be reduced in proportion to the value of work performed by the Contractor as evidenced by the invoices for installation services.

----- percent (--%) of the measured value of work performed by the Contractor, as identified in the said Program of Performance, during the preceding month, as evidenced by the Employer’s authorization of the Contractor’s application, will be made monthly within forty-five (45) days after receipt of invoice.

----- percent (--%) of the total or pro rata value of installation services performed by the Contractor as evidenced by the Employer’s authorization of the Contractor’s monthly applications, upon issue of the Completion Certificate, within forty-five (45) days after receipt of invoice.

----- percent (--%) of the total or pro rata value of installation services performed by the Contractor as evidenced by the Employer’s authorization of the Contractor’s monthly applications, upon issue of the Operational Acceptance Certificate, within forty-five (45) days after receipt of invoice.

In the event that the Employer fails to make any payment on its respective due date, the Employer shall pay to the Contractor interest on the amount of such delayed payment at the rate of _____________ percent (_____ %) per month for period of delay until payment has been made in full.

(B)  Payment Procedures

When applying for certification and making payments, the procedures shall be as follows:

[Insert appropriate procedures, usually Letters of Credit, including forms and certificates annexed as appropriate by the Employer in the Bidding Documents.]

#### Appendix 2. Price Adjustment

Where the Contract Period (excluding the Defects Liability Period) exceeds eighteen (18) months, it is normal procedure that prices payable to the Contractor shall be subject to adjustment during the performance of the Contract to reflect changes occurring in the cost of labor and material components. In such cases the bidding document shall include in this form a formula of the following general type, pursuant to PCC Sub-Clause 11.2. Where Contracts are of a shorter duration than eighteen (18) months or in cases where there is to be no Price Adjustment, the following provision shall not be included. Instead, it shall be indicated under this form that the prices are to remain firm and fixed for the duration of the Contract.

Sample Price Adjustment Formula

If in accordance with GC 11.2, prices shall be adjustable, the following method shall be used to calculate the price adjustment:

Prices payable to the Contractor, in accordance with the Contract, shall be subject to adjustment during performance of the Contract to reflect changes in the cost of labor and material components, in accordance with the following formula:

in which:

P1	=	adjustment amount payable to the Contractor

P0	=	Contract price (base price)

a	=	percentage of fixed element in Contract price (a =   %)

b	=	percentage of labor component in Contract price (b =  %)

c	=	percentage of material and equipment component in Contract price (c =  %)

L0, L1	=	labor indices applicable to the appropriate industry in the country of origin on the base date and the date for adjustment, respectively

M0, M1=	material and equipment indices in the country of origin on the base date and the date for adjustment, respectively

N.B.  a+b+c= 100%.

[The Bidder shall propose the coefficients b and c in its Bid. The formula, including all coefficients, shall be determined and finalized at Contract negotiations.]

Conditions Applicable To Price Adjustment

The Bidder shall indicate the source of labor and materials indices,  and source of exchnage rate (if applicable) and the base date indices in its Bid.

| Item | Source of Indices Used | Base Date Indices |
| --- | --- | --- |

The base date shall be the date twenty-eight (28) days prior to the deadline for submission of the bid.

For Plant or components supplied under Schedules No.1, No.2 and No.3, the date of adjustment shall be the mid-point of the sequences shown in the Program of Performance submitted by the Bidder, pursuant to GC 18.2, for design or manufacture of the Plant or components.

In respect of Installation Services provided under Schedule No.4, the adjustment shall apply to the monthly measured value of work performed by the Contractor during the preceding month. The adjustment shall be made monthly to the payments for Installation Services effected as provided in Appendix 1 of the Contract Agreement.

The following conditions shall apply:

- No price increase will be allowed beyond the original delivery date unless covered by an extension of time awarded by the Employer under the terms of the Contract. No price increase will be allowed for periods of delay for which the Contractor is responsible. The Employer will, however, be entitled to any price decrease occurring during such periods of delay;

- If the currency in which the Contract price, P0, is expressed is different from the currency of the country of origin of the labor and/or materials indexes, a correction factor will be applied to avoid incorrect adjustments of the Contract price. The correction factor shall correspond to the ratio of exchange rates between the two currencies on the base date and the date for adjustment as defined above; and

- No price adjustment shall be payable on the portion of the Contract price paid to the Contractor as an advance payment.

#### Appendix 3. Insurance Requirements

[Details to be completed by the Employer prior to issuing the Bidding Documents. In the event that the Employer provides any insurance under the Contract, appropriate details must also be given.]

(A)  Types of Insurance to Be Taken Out by the Contractor

In accordance with the provisions of GC Clause 34, the Contractor shall at its expense take out and maintain in effect, or cause to be taken out and maintained in effect, during the performance of the Contract, the insurances set forth below in the sums and with the deductibles and other conditions specified. The identity of the insurers and the form of the policies shall be subject to the approval of the Employer, such approval not to be unreasonably withheld.

(a)  Cargo Insurance

Covering loss or damage occurring, while in transit from the supplier’s or manufacturer’s works or stores until arrival at the Site, to the Facilities (including spare parts therefore) and to the construction equipment to be provided by the Contractor or its Subcontractors.

| Amount | Deductible limits | Parties insured | From | To |
| --- | --- | --- | --- | --- |
| [in currency(ies)] | [in currency(ies)] | [names] | [place] | [place] |

(b)  Installation All Risks Insurance

Covering physical loss or damage to the Facilities at the Site, occurring prior to Operational Acceptance of the Facilities, with an extended maintenance coverage for the Contractor’s liability in respect of any loss or damage occurring during the defect liability period while the Contractor is on the Site for the purpose of performing its obligations during the defect liability period.

| Amount | Deductible limits | Parties insured |
| --- | --- | --- |
| [in currency(ies)] | [in currency(ies)] | [names] |

(c)  Third Party Liability Insurance

Covering bodily injury or death suffered by third parties (including the Employer’s personnel) and loss of or damage to property (including the Employer’s property and any parts of the Facilities that have been accepted by the Employer) occurring in connection with the supply and installation of the Facilities.

| Amount | Deductible limits | Parties insured | From | To |
| --- | --- | --- | --- | --- |
| [in currency(ies)] | [in currency(ies)] | [names] | [place] | [place] |

(d)  Automobile Liability Insurance

Covering use of all vehicles used by the Contractor or its Subcontractors (whether owned by them or not) in connection with the supply and installation of the Facilities.  Comprehensive insurance in accordance with statutory requirements.

(e)  Workers’ Compensation

In accordance with the statutory requirements applicable in any country where the Facilities or any part thereof is executed.

(f)  Employer’s Liability

In accordance with the statutory requirements applicable in any country where the Facilities or any part thereof is executed.

(g) Other Insurance

The Contractor is also required to take out and maintain at its own cost the following types of insurance:

Details:

| Amount | Deductible limits | Parties insured | From | To |
| --- | --- | --- | --- | --- |
| [in currency(ies)] | [in currency(ies)] | [names] | [place] | [place] |

The Employer shall be named as co-insured under all insurance policies taken out by the Contractor pursuant to GC Sub-Clause 34.1, except for the Third Party Liability, Workers’ Compensation, and Employer’s Liability Insurance, and the Contractor’s Subcontractors shall be named as co-insureds under all insurance policies taken out by the Contractor pursuant to GC Sub-Clause 34.1, except for the Cargo, Workers’ Compensation and Employer’s Liability Insurances. All insurer’s rights of subrogation against such co-insureds for losses or claims arising out of the performance of the Contract shall be waived under such policies.

(B)  Types of Insurance to Be Taken Out by the Employer

The Employer shall at its expense take out and maintain in effect during the performance of the Contract the following insurance policies.

Details:

| Amount | Deductible limits | Parties insured | From | To |
| --- | --- | --- | --- | --- |
| [in currency(ies)] | [in currency(ies)] | [names] | [place] | [place] |

#### Appendix 4. Time Schedule

[The Employer should normally provide a Time Schedule to be followed by the Contractor during the performance of the Contract. This schedule should be provided with the Bidding Documents under this Appendix. All completion times indicated must be in accordance with the information regarding Time(s) for Completion given in the Bid Data Sheet.

Except under exceptional circumstances, the Time Schedule should indicate periods of time (e.g., weeks or months) and not specify calendar dates. All periods should be shown from the Effective Date of the Contract.

Should it become necessary to amend the Time Schedule to reflect any agreements made with the selected Bidder prior to award of Contract, the amended Time Schedule shall replace the original Time Schedule prior to signature of the Contract Agreement.

If the Bidding Documents contain no Time Schedule, the Bidder shall be required to submit with its Bid a detailed program, normally in the form of a bar chart, showing how and the order in which it intends to perform the Contract and showing the key events requiring action or decision by the Employer. In preparing this Program, the Bidder shall adhere to the Time(s) for Completion given in the Bid Data Sheet or give its reasons for not adhering thereto. The Time Schedule submitted by the selected Bidder and amended as necessary prior to award of Contract shall be included as Appendix to the Contract Agreement before the Contract is signed.]

#### Appendix 5. List of Major Items of Plant and Installation Services and List of Approved Subcontractors

[Prior to issuing the Bidding Documents, the Employer has established a list of major item of Plant and Installation Services for which approval of the Employer is required. Prior to award of Contract, the details of approved Subcontractors, including manufacturers shall be completed, indicating those Subcontractors proposed by the Bidder in the corresponding Attachment to its Bid that are approved by the Employer for engagement by the Contractor during the performance of the Contract.]

A list of major items of Plant and Installation Services is provided below.

The following Subcontractors and/or Manufacturers are approved for carrying out the items of the Facilities indicated. Where more than one Subcontractor is listed, the Contractor is free to choose between them, but it must notify the Employer of its choice in good time prior to appointing any selected Subcontractor. In accordance with GC Sub-Clause 19.1, the Contractor is free to submit proposals for Subcontractors for additional items from time to time. No Subcontracts shall be placed with any such Subcontractors for additional items until the Subcontractors have been approved in writing by the Employer and their names have been added to this list of Approved Subcontractors.

| Major Items of Plant and Installation Services | Approved Subcontractors and Manufacturers | Nationality |
| --- | --- | --- |

#### Appendix 6: Scope of Works and Supply by the Employer

[Prior to issuing the Bidding Documents, the Employer shall indicate in this Appendix details of all Personnel and Facilities it will provide for use by the Contractor and indicate, where applicable, the charges that it will make in respect of their use.

The Employer shall also identify any part(s) of the facilities it intends to carry out itself (or by other contractors), and any plant, equipment or materials that it proposes to purchase itself and supply to the Contractor for incorporation in the facilities, indicating, where applicable, the charges that it will make in respect thereof.]

The following Personnel, Facilities, works, and supplies will be provided or supplied by the Employer, and the provisions of GC Clauses 10, 21, and 24 shall apply as appropriate.

All Personnel, Facilities, works, and supplies will be provided by the Employer in good time so as not to delay the performance of the Contractor, in accordance with the approved Time Schedule and Program of Performance pursuant to GC Sub-Clause 18.2.

Unless otherwise indicated, all Personnel, Facilities, works, and supplies will be provided free of charge to the Contractor.

| Personnel | Charge to Contractor (if any) |
| --- | --- |

| Facilities | Charge to Contractor (if any) |
| --- | --- |

| Works | Charge to Contractor (if any) |
| --- | --- |

| Supplies | Charge to Contractor (if any) |
| --- | --- |

#### Appendix 7. List of Documents for Approval or Review

Pursuant to GC Sub-Clause 20.3.1, the Contractor shall prepare, or cause its Subcontractor to prepare, and present to the Project Manager in accordance with the requirements of GC Sub-Clause 18.2 (Program of Performance), the following documents for

(A)  Approval

1.

2.

3.

(B)  Review

1.

2.

3.

#### Appendix 8. Functional Guarantees

- General

This Appendix sets out:

- the functional guarantees referred to in GC Clause 28 (Functional Guarantees);

- the preconditions to the validity of the functional guarantees, either in production and/or consumption, set forth below;

- the minimum level of the functional guarantees; and

- the formula for calculating liquidated damages for failure to attain the functional guarantees.

- Preconditions

The Contractor gives the functional guarantees (specified herein) for the facilities, subject to the following preconditions being fully satisfied:

[List any conditions for the carrying out of the Guarantee Test referred to in GC Clause 25.2.]

- Functional Guarantees

Subject to compliance with the foregoing preconditions, the Contractor guarantees are as follows:

- Production Capacity: [List here the production capacity that the Contractor is to guarantee, making sure to use, as functional guarantees, the figures offered by the Contractor in its Bid]

and/or

- Raw Materials and Utilities Consumption: [List here the guaranteed items of consumption per unit of production (e.g., kg, tons, kcal, kWh, etc.) that the Contractor is to guarantee, making sure to use, as functional guarantees, the figures offered by the Contractor in its Bid]

- Failure in Guarantees and Liquidated Damages

- Failure to Attain Guaranteed Production Capacity

If the production capacity of the facilities attained in the guarantee test, pursuant to GC Sub-Clause 25.2, is less than the guaranteed figure specified in para. 3.1 above, but the actual production capacity attained in the guarantee test is not less than the minimum level specified in para. 4.3 below, and the Contractor elects to pay liquidated damages to the Employer in lieu of making changes, modifications and/or additions to the Facilities, pursuant to GC Sub-Clause 28.3, then the Contractor shall pay liquidated damages at the rate of [insert amount in the Contract currency(ies)] for every complete one percent (1%) of the deficiency in the production capacity of the Facilities, or at a proportionately reduced rate for any deficiency, or part thereof, of less than a complete one percent (1%).

- Raw Materials and Utilities Consumption in Excess of Guaranteed Level

[To be specified in the appropriate wording for the type of Facilities, if there are consumption guarantees.]

If the actual measured figure of specified raw materials and utilities consumed per unit (or their average total cost of consumption) exceeds the guaranteed figure specified in para. 3.2 above (or their specified average total cost of consumption), but the actual consumption attained in the guarantee test, pursuant to GC Sub-Clause 25.2, is not more than the maximum level specified in para. 4.3 below, and the Contractor elects to pay liquidated damages to the Employer in lieu of making changes, modifications and/or additions to the Facilities pursuant to GC Sub-Clause 28.3, then the Contractor shall pay liquidated damages at the rate of [amount in the Contract currency(ies)] for every complete 1% of the excess consumption of the Facilities, or part thereof, of less than a complete one percent (1%).

[The rate of liquidated damages specified in paras. 4.1 and 4.2 above shall be at least equivalent to the rate specified in Section III, Evaluation and Qualification Criteria for the comparison of functional guarantees provided by the Bidders.]

- Minimum Levels

Notwithstanding the provisions of this paragraph, if as a result of the guarantee test(s), the following minimum levels of performance guarantees (and consumption guarantees) are not attained by the Contractor, the Contractor shall at its own cost make good any deficiencies until the Facilities reach any of such minimum performance levels, pursuant to GC Sub-Clause 28.2:

- production capacity of the Facilities attained in the guarantee test:  ninety-five percent (95%) of the guaranteed production capacity (the values offered by the Contractor in its Bid for functional guarantees represents one hundred percent (100%)).

and/or

- average total cost of consumption of all the raw materials and utilities of the Facilities:  one hundred and five percent (105%) of the guaranteed figures (the figures offered by the Contractor in its Bid for functional guarantees represents one hundred percent 100%).

- Limitation of Liability

Subject to para. 4.3 above, the Contractor’s aggregate liability to pay liquidated damages for failure to attain the functional guarantees shall not exceed [insert percentage in words and figures (the percentage specified shall not exceed ten percent (10%) of the Contract Price)]  percent (_____ %) of the Contract price.

### Form of Performance Security

[Guarantor letterhead or SWIFT identifier code]

Beneficiary: [insert name and address of the Employer]

Date: [insert date of issue]

Performance Guarantee No.: [insert guarantee reference number]

Guarantor: [insert name and address of place of issue, unless indicated in the letterhead]

We have been informed that [insert name of the contractor] (hereinafter called “the Applicant”) has entered into Contract No. [insert reference number of the contract] dated [date] with the Beneficiary, for the execution of [insert name of contract and brief description of Plant and Installation Services] (hereinafter called "the Contract").

Furthermore, we understand that, according to the conditions of the Contract, a performance guarantee is required.

At the request of the Applicant, we [name of the Guarantor] as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of [insert amount in words] [insert amount in figures], such sum being payable in the types and proportions of currencies in which the Contract Price is payable, upon receipt by us of the Beneficiary’s first demand in writing accompanied by a written statement stating that the Applicant is in breach of its obligation(s) under the Contract, without the Beneficiary needing to prove or to show grounds for your demand or the sum specified therein.

This guarantee shall be reduced by half upon our receipt of:

- a copy of the Operational Acceptance Certificate; or

- a registered letter from the Applicant (i) attaching a copy of its notice requesting issuance of the Operational Acceptance Certificate and (ii) stating that the Project Manager has failed to issue such Certificate within the time required or provide in writing justifiable reasons why such Certificate has not been issued, so that Operational Acceptance is deemed to have occurred.

This guarantee shall expire no later than the earlier of:

- twelve (12) months after our receipt of either (a) or (b) above;

- eighteen (18) months after our receipt of:

- a copy of the Completion Certificate;

- a registered letter from the Applicant, attaching a copy of the notice to the project manager that the Facilities are ready for commissioning, and stating that fourteen (14) days have elapsed from receipt of such notice (or seven (7) days have elapsed if the notice was a repeated notice) and the Project Manager has failed to issue a Completion Certificate or inform the Applicant in writing of any defects or deficiencies; or

- a registered letter from the Applicant stating that no Completion Certificate has been issued but the Employer is making use of the Facilities; or

- the [date] day of [month], [year].

Consequently, any demand for payment under this guarantee must be received by us at this office on or before that date.

After the Guarantee expiry, this Guarantee shall be automatically null and void and be cancelled whether it is returned to us or not.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758, except that the supporting statement under Article 15(a) is hereby excluded.

[Signature(s) and seal of Guarantor (where appropriate)]

[Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.]

### Form of Advance Payment Security

[Guarantor letterhead or SWIFT identifier code]

Beneficiary: [insert name and address of the Employer]

Date: [insert date of issue]

Advance Payment Guarantee No.: [insert guarantee reference number]

Guarantor: [insert name and address of place of issue, unless indicated in the letterhead]

We have been informed that [insert name of the contractor] (hereinafter called "the Applicant") has entered into Contract No. [insert reference number of the contract] dated [date] with the Beneficiary, for the execution of [insert name of contract and brief description of Plant and Installation Services] (hereinafter called "the Contract").

Furthermore, we understand that, according to the Conditions of the Contract, an advance payment in the sum of [insert amount in words] ([insert amount in figures]) is to be made against an advance payment guarantee.

At the request of the Contractor, we [name of the Guarantor] hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of [insert amount in words] ([insert amount in figures]) upon receipt by us of Beneficiary’s first demand in writing accompanied by a written statement stating that the Applicant is in breach of its obligation under the Contract because the Applicant:

    - has used the advance payment for purposes other than the costs of mobilization and cash flow support in respect of the Facilities; or

    - has failed to repay the advance payment when it has become due and payable in accordance with the conditions of the Contract, specifying the amount payable by the Applicant.

It is a condition for any claim and payment under this guarantee to be made that the advance payment referred to above must have been received by the Applicant on its account number [contractor’s account number] at [name and address of the Guarantor].

The maximum amount of this guarantee shall be progressively reduced by the amount of the advance payment repaid by the Applicant as indicated in copies of interim statements or payment certificates, which shall be presented to the Guarantor. This guarantee shall become valid and in full effect from the date upon which the amount of the advance payment is made to the Applicant’s Guarantor account specified in this guarantee and shall expire, at the latest, upon the Guarantor’s receipt of documentation indicating full repayment by the Applicant of the amount of the advance payment, or on the ___ day of _______, 2___, whichever is earlier. Consequently, any demand for payment under this guarantee must be received by the Guarantor at its office on or before that date.

After the Guarantee expiry, this Guarantee shall be automatically null and void and be cancelled whether it is returned to us or not.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758, except that the supporting statement under Article 15(a) is hereby excluded.

[Signature(s) and seal of Guarantor (where appropriate)]

[Note: All italicized text (including footnotes) is for use in preparing this form and shall be deleted from the final product.]

1	Day, month, year; for example, 31 July 2020, or other unambiguous, internationally understood representation of the date

2	Substitute “has applied for” in case an advance procurement action is approved by the Export-Import Bank of Korea

3	Insert the following if applicable: “This Contract will be jointly financed by [insert: the name of Co-financing Agency]. Bidding will be governed by the Export-Import Bank of Korea’s eligibility rules and procedures.”

4	Insert the following if applicable: “The delivery/construction period is [insert: number of days/months/years or dates].”

5	Bidding documents may require Bidders to have specific experience and/or certain capabilities necessary to perform the contract; such restrictions should be included in this paragraph.

6	If this is not the address stated at the bottom of the Invitation of Bids, revise the text accordingly and include the address where the bidding documents may be inspected.

7	For example, 09:00 to 17:00 hours.

8	The fee chargeable should only be nominal to defray reproduction and mailing costs, to ensure that only bona fide bidders will request bidding documents and not so high as to discourage bidders.

9	For example, cashier’s check, direct deposit to a specified bank and account number, etc.

10	The delivery procedure is usually airmail for overseas delivery and surface mail or courier for local delivery. If urgency or security dictates, courier services may also be required.

11	The amount of bid security should be stated as a fixed amount or as a minimum percentage (approximately 2-3%) of the Bid Price. Alternatively, if a bid security is not required, the paragraph should so state.

12	The place for bid opening may not be the same as that for inspection or issuance of documents or for bid submission. If they differ, each address must appear at the end of the notice and be numbered; as, for example, (1), (2), (3). The text in the paragraph would then refer to address (1), (2), etc. However, only one office should be specified for submission of bids, and this location should be as close as possible to the place where bids will be opened to shorten the time between bid submission and opening.

The amount of the Bond shall be denominated in the currency of the Employer’s Country or the equivalent amount in a freely convertible currency.

The amount of the Bond shall be denominated in the currency of the Employer’s Country or the equivalent amount in a freely convertible currency.

The guarantor shall insert an amount representing the percentage of the contract price specified in the contract and denominated either in the currency(ies) of the contract or a freely convertible currency acceptable to the Employer.

This text shall be revised as and where necessary to take into account (i) partial acceptance of the Facilities in accordance with GC Sub-Clause 25.4.

Insert the date twenty-eight days after the expected expiration date of the Defect Liability Period. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [six months][one year], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”

The Guarantor shall insert an amount representing the amount of the advance payment and denominated either in the currency(ies) of the advance payment as specified in the Contract, or in a freely convertible currency acceptable to the Employer.

Insert the expected expiration date of the Time for Completion. The Employer should note that in the event of an extension of the time for completion of the Contract, the Employer would need to request an extension of this guarantee from the Guarantor. Such request must be in writing and must be made prior to the expiration date established in the guarantee. In preparing this guarantee, the Employer might consider adding the following text to the form, at the end of the penultimate paragraph: “The Guarantor agrees to a one-time extension of this guarantee for a period not to exceed [e.g. six months], in response to the Employer’s written request for such extension, such request to be presented to the Guarantor before the expiry of the guarantee.”